ALFRED NZO DISTRICT MUNICIPALITY SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN FOR 2012/13

1.	MUNICIPAL MANAGER’S OFFICE

  - OFFICE OF THE EXECUTIVE MAYOR

| NATIONAL KEY PERFORMANCE AREA |  | SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | SPECIAL PROGRAMMES |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | EXEC MANAGER IN THE OFFICE OF THE EXEC MAYOR |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Special Programme (Poverty Alleviation) |  | To ensure sustainable communities free from poverty |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of households assisted through Special programme |  | 31 December 2012 |  | Low levels of households under poverty lines. |  |  | 400 Households |  | 800 households |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 200 | 200 |  | 200 | 200 |
| Happy Letters from Beneficiaries |  | 31 December 2012 |  | Data profiling |  |  | 31 December 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 800 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Identification of Needy Households | 01 Jul 2012 |  | 31 July 2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| - Implementation of the Programme | 01 August 2012 |  | 31 December 2012 |  | 200 000 | 200 000 |  | 200 000 |  |  | 200 000 |  |  |

  - COMMUNICATION’S UNIT

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |  |
| Newsletter and Leaflets |  | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/Backlog |  | (Annual Target) 2012/13 |  |  |  |  |  |
| Approved Newsletter and leaflets produced. |  | 30 June 2013 |  | Well informed communities about government programmes |  | Four newsletters and one pamphlet |  | 04 Newsletters produced annually. 08 Leaflets produced |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | Quarterly Targets |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | -01 Newsletter -02 Leaflets |  | -01 Newsletter -02 Leaflets | -01 Newsletter -02 Leaflets |  | -01 Newsletter -02 Leaflets |
| Newsletter and leaflets copies and supply chain documents. |  | 30 June 2013 |  | Distribution report |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION |  | R400 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Collect information from different departments/project visits. | 01 July 2012 |  | 30 May 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Layout and design | 01 July 2012 |  | 30 May 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Editing of stories by Core Team | 01 July 2012 |  | 30 May 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Put out tender notice | 01 August 2012 |  | 30 May 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Appointment of Service Provider | 01 August 2012 |  | 30 May 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Printing of newsletter and leaflets | 01 July 2012 |  | 30 June 2013 |  | 100 000 |  | 100 000 |  | 100 000 |  |  | 100 000 |  |
| - Distribution | 30 August 2012 |  | 30 June 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |
| Community outreaches |  | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/Backlog |  | (Annual Target) 2012/13 |  |  |  |
| Approved action plan for community outreaches. |  | 30 June 2013 |  | Communities accessing government services and information. |  | 06 Community outreaches were conducted |  | 08 Community Outreaches |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | Quarterly Targets |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 02 | 02 | 02 | 02 |
| Exit Report, Pictures and supply chain documents. |  | 30 June 2013 |  | Council resolution |  | 30 June 2013 |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION |  | R500 000 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  | QUARTER 4 |  |
| - Develop a quarterly Mayoral/Exco plan | 01 July 2012 |  | 30 June 2013 |  | Nil |  | Nil | Nil |  | Nil |  |
| - Conduct Communications environmental assessment - (Core Team Meetings) | 01 July 2012 |  | 30 June 2013 |  | Nil |  | Nil | Nil |  | Nil |  |
| Consolidate communications report (Core Team) | 01 July 2012 |  | 30 June 2013 |  | Nil |  | Nil | Nil |  | Nil |  |
| Procurement of promotional material, publicity adverts and posters, logistics for the outreach, catering. | 01 July 2013 |  | 30 July 2013 |  | R125 000 |  | R125 000 | R125 000 |  | R125 000 |  |
| Compilation of exit report of the outreaches. | 01 July 2012 |  | 30 July 2013 |  | Nil |  | Nil | Nil |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |  |  |
| Memorial Lectures | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | Baseline/Prior Year Performance/ Backlog |  | (Annual Target) 2012/13 |  |  |  |  |  |
| Approved communication plan for the memorial lectures. | 30 June 2013 |  | Profiling struggle stalwarts Alfred Nzo and O. R. Tambo. |  |  | 01 Memorial Lecture Done |  | 02 Memorial Lectures to be conducted. |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | Quarterly Targets |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | 0 | 01 O.R.Tambo Lecture |  | 0 |  | 01 Alfred Nzo Lecture |
| Council Resolution | 30 June 2013 |  | Pictures, attendance register, exit report. |  |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION | R500 000 |  | VOTE NUMBER |  |  | V3 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  |  | QUARTER 3 |  | QUARTER 4 |  |
| - Develop a communication plan for the memorial lectures. - Core Team Sittings |  | 01 October 2012 |  | 30 June 2013 | Nil |  | Nil |  |  | Nil |  | Nil |  |
| - Conduct Communications environmental assessment |  | 01 October 2012 |  | 30 June 2013 | Nil |  | Nil |  |  | Nil |  | Nil |  |
| Conduct DCF Core Team Meetings to present communication plan. |  | 01 October 2012 |  | 30 June 2013 | Nil |  | Nil |  |  | Nil |  | Nil |  |
| Procurement of promotional material, publicity adverts and posters, logistics for the outreach, meetings. |  | 01 October 2012 |  | 30 June 2013 | Nil |  | R 250 000 |  |  | Nil |  | R 250 000 |  |
| Exit report of the outreach |  | 01 October 2012 |  | 30 June 2013 | Nil |  | Nil |  |  | Nil |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |
| Open Council Day |  | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/ Backlog | (Annual Target) 2012/13 |  |  |  |  |  |
| Approved communication plan for the Open Council Day |  | 30 June 2013 |  | Communities being informed about municipal programme of action. |  | None | 01 Open Council Day |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE | Quarterly Targets |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | 0 |  | 0 | 0 |  | 01 |
| Council Resolution |  | 30 June 2013 |  | Attendance registers, pictures, exit report. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION |  | R350 000 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Communication Plan Development | 01 May 2013 |  | 30 June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |
| - Design and layout of promotional material | 01 May 2013 |  | 30 June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |
| Placement of adverts, procurement of banners, leaflets, radio interviews, roadshows, promotional material | 01 June 2013 |  | 30 June 2013 |  | Nil | Nil |  | Nil |  |  | R 350 000 |  |
| Exit Reports | 29 June 2013 |  | 30 June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |
| Publicity Costs | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/ Prior Year Performance/ Backlog |  | (Annual Target) 2012/13 |  |  |  |  |
| Approved publicity communication plan | 30 June 2013 |  | Well informed communities about municipal programmes. |  | 30 public activities done |  | 40 publicity activities done |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | Quarterly Targets |  |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | 10 | 10 | 10 |  | 10 |
| Communication strategy action plan | 30 June 2013 |  | Clippings, voice overs, pictures, posters, leaflets |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION | R350 000 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| - Identification of key programmes with publicity Implications. | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Design and layout of publicity products, adverts and products. | 01 July 2012 | 30 Jun3e 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Placement of adverts, procurement of banners, leaflets, radio interviews, roadshows, promotional material | 01 July 2012 | 30 June 2013 |  | R 80 000 |  | R 100 000 | R 60 000 |  |  | R 110 000 |  |
| Exit Reports | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |  |
| Branding and Marketing | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/Backlog |  | (Annual Target) 2012/13 |  |  |  |  |  |
| Approved branding and marketing plan. | 30 June 2013 |  | Well branded and marketed municipality |  | Branding manual was developed. |  | -Branding manual done and marketing plan developed. -New logo developed. -10 Distribution Stands -10 Municipal Signage. -Communication and branding Strategy Reviewed and approved. |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | Quarterly Targets |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | 01 |  | 01 | 01 |  | 01 |
| Communication strategy action plan | 30 June 2013 |  | Pictures of products, branding manual, logo |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION | R1 500 000 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Logo Development finalized. |  | 01 August 2012 |  | 30 2013 | Nil | Nil |  | Nil |  |  | Nil |  |
| - Design and layout of new logo. |  | 01 July 2012 |  |  | Nil | Nil |  | Nil |  |  | Nil |  |
| - DCF Core Team |  | 01 July 2012 |  | 30 June 2013 | Nil | Nil |  | Nil |  |  | Nil |  |
| - Core Team Meetings |  | 01 July 2012 |  | 30 June 2013 | Nil | Nil |  | Nil |  |  | Nil |  |
| - Communication and branding Strategy Review Session |  | 01 October 2012 |  | 30 December 2013 | Nil | Nil |  | Nil |  |  | Nil |  |
| Payment of designers of the logo, branding manual and development of branding and marketing plan. |  | 01 August 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |
| Procurement of the promotional material, signage, distribution stands, strategy workshops. |  |  |  |  | R 500 000 | R 500 000 |  | R 300 000 |  |  | R 200 000 |  |
| Exit Reports |  | 01 July 2012 |  | 30 June 2013 | Nil | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |  |  |
| Audio Visuals | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/ Backlog |  | (Annual Target) 2012/13 |  |  |  |  |  |
| Approved procurement of credible working equipment. | 01 August 2012 |  |  | Well-functioning equipment to capture municipal programmes. |  | 01 Video Camera 2 digital cameras. |  | -01 Video Camera -01 Equipment Storage Safe -01 PA System -02 Loudhailers -01 Flat Screen Tv (Foyer), -01 Projector, -05 Laptops, |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | 30 June 2013 |  | Quarterly Targets |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | 01 |  | 01 | 01 |  | 01 |
| Communication strategy action plan | 01 August 2012 |  |  | Invoices, video recordings, pictures, |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION | R270 000 |  |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Identification of available audio visual equipment. |  | 01 July 2012 | 30 July 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Development of available audio visual asset register |  | 01 July 2012 | 30 July 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Request for quotations from service providers |  | 01 August 2012 | 30 August 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Procurement of audio visuals. |  | 01 September 2012 | 30 October 2012 |  | R 150 000 |  | R 50 000 |  | R 50 000 |  |  | R 20 000 |  |
| Exit Reports |  | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |
| Braille and Translation |  | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/Backlog |  | (Annual Target) 2012/13 |  |  |  |  |
| Approved Action plan to on the communication strategy. |  | 30 June 2013 |  | All sectors of society informed about government programmes. . |  | None |  | 02 Newsletter or leaflets translated into Sotho, Xhosa and braille. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 01 | 01 |  | 01 | 01 |
| Copies of translated newsletter and braille. |  | 01 September 2012 |  | Copies of publication translated |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION |  | R100 000 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Identification of services providers to translate and also produce in braille | 01 August 2012 |  | 30 August 2012 | Nil | Nil |  | Nil |  |  | Nil |  |  |
| - Editing of information. | 01 August 2012 |  | 30 June 2013 | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Printing of the publications. | 01 September 2012 |  | 30 June 2013 | R 25 000 | R 25 000 |  | R 25 000 |  |  | R 25 000 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  | NDABUKO MASUMPA |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVE(S)/ IDP OBJECTIVE(S |  |  |  |  |  |  |  |  |  |  |  |
| Road Signage |  | To ensure effective implementation of the communication strategy |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | Baseline/Prior Year Performance/Backlog |  | (Annual Target) 2012/13 |  |  |  |  |
| Approved action plan on road signage. |  | 30 June 2012 |  |  | Clear road signage developed for the district. |  | None |  | 07 Road signage developed. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 01 | 01 |
| Communication strategy action plan. |  | 30 June 2012 |  |  | Pictures of road signage. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL BUDGET ALLOCATION |  | R50 000 |  |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/INPUTS/ INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Identification of roads to be branded. | 01 October 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Appointment of service provider. | 20 January 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Procurement of services and goods. | 01 March 2012 |  | 30 June 2013 | Nil |  | Nil |  | R 25 000 |  |  | R 25 000 |  |  |

1.3  INTERNAL AUDIT UNIT

| NATIONAL KEY PERFORMANCE AREA | GOOD GOVERNANCE AND PUBLIC PARTCIPATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | INTERNAL AUDIT SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | INTERNAL AUDIT MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct Internal Audits as per approved Internal Audit Plan. | To provide innovative and effective internal audit services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |
| Internal Audit Reports | Quarterly |  |  |  |  | Improve Audit Opinion |  |  |  |  |  | Disclaimer Audit Opinion |  |  |  |  | Top 10 risks be audited. (10 Audit engagement be audited) |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  |  | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 2 |  |  | 3 |  | 3 |
| Internal Audit Report with Management Comments and Audit Committee meeting minutes. | Quarterly |  |  |  |  | Continuous identification system of internal control gaps and improved system of internal controls |  |  |  |  |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R800 000.00 |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  | TIMEFRAMES |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | START DATE |  |  |  | END DATE |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  | QUARTER 3 |  |  |  |  | QUARTER 4 |  |  |
| - Compile Internal Audit Strategic and operational plans |  |  |  | 01 Jul 2012 |  |  |  | 10 July 2012 |  | Nil |  |  |  | Nil |  |  | Nil |  |  |  |  | Nil |  |  |
| - Conduct internal Audits as per approved internal audit plan (two Audit engagements) |  |  |  | 01 July 2012 |  |  |  | 30 Sep 2012 |  | Nil |  |  |  | Nil |  |  | Nil |  |  |  |  | Nil |  |  |
| - Conduct internal Audits as per approved internal audit plan (two Audit engagements) |  |  |  | 01 Oct 2012 |  |  |  | 31 Dec 2012 |  | Nil |  |  |  | Nil |  |  | Nil |  |  |  |  | Nil |  |  |
| - Conduct internal Audits as per approved internal audit plan (three Audit engagements co-sourced projects included) |  |  |  | 02 Jan 2013 |  |  |  | 31 Mar 2013 |  | R200 000.00 |  |  |  | R300 000.00 |  |  | R100 000.00 |  |  |  |  | R200 000.00 |  |  |
| - Conduct internal Audits as per approved internal audit plan (three Audit engagements) |  |  |  | 01 April 2013 |  |  |  | 30 Jun 2013 |  | Nil |  |  |  | Nil |  |  | Nil |  |  |  |  | Nil |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE AND PUBLIC PARTCIPATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | INTERNAL AUDIT SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | INTERNAL AUDIT MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support Audit Committee |  | Ensure effective Audit Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |
| Number of Audit Committee seating |  | Quarterly |  |  |  |  | Clean Administration |  |  |  | Inadequate Audit Committee |  |  |  | 6 Audit Meetings |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 |  | Q3 |  |  | Q4 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 Meeting |  |  | 1 Meeting |  | 2 Meetings |  |  | 2 Meetings |  |
| Audit Committee meeting minutes |  | Quarterly |  |  |  |  | Audit Committee reports |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 650 000.00 |  |  |  |  | VOTE NUMBER |  |  |  | Audit Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  | QUARTER 3 |  |  |  |  | QUARTER 4 |  |  |  |
| Review Internal Audit reports |  |  | 01 Jul 2012 |  | 30 Sept 2012 |  |  |  | R108 000.00 |  |  |  | - |  |  | - |  |  |  |  | - |  |  |  |
| Review Internal Audit reports |  |  | 01 Oct 2012 |  | 31 Dec 2012 |  |  |  | - |  |  |  | R108 000.00 |  |  | - |  |  |  |  | - |  |  |  |
| Review Internal Audit reports |  |  | 02 Jan 2013 |  | 31 Mar 2013 |  |  |  | - |  |  |  | - |  |  | R108.000 |  |  |  |  | - |  |  |  |
| Review Internal Audit reports |  |  | 01 Apr 2013 |  | 30 June 2013 |  |  |  | -- |  |  |  | - |  |  | - |  |  |  |  | R108 000.00 |  |  |  |
| Review Internal Audit reports (performance management) |  |  | 02 Jan 2013 |  | 31 Mar 2013 |  |  |  | - |  |  |  |  |  |  | R109 000.00 |  |  |  |  | - |  |  |  |
| Review Internal Audit reports (performance management) |  |  | 01 Apr 2013 |  | 30 June 2013 |  |  |  | - |  |  |  | - |  |  | - |  |  |  |  | R109 000.00 |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | GOOD GOVERNANCE AND PUBLIC PARTCIPATION |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | INTERNAL AUDIT SERVICES |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | INTERNAL AUDIT MANAGER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Compile Audit Methodology |  | To provide innovative and effective internal audit services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Audit Methodology |  | 31 Dec 2012 |  | Compliance with International Internal Audit Standards |  |  | Lack of Audit Methodology |  | An adopted Audit Methodology |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | Compile audit methodology |  |  |  |
| Audit Committee meeting minutes |  | 31 Dec 2012 |  | Audit Committee reports |  |  | Ongoing |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  | VOTE NUMBER |  |  | Internal Audit |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Compile audit methodology | 01 Jul 2012 |  | 30 Sept 2012 |  |  | R200 000 |  |  |  |  |  |  |  |

  - RISK MANAGEMENT UNIT

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Review of Risk management framework. |  | To assist and advise ANDM management on the identification, prioritisation and management of risks across the organisation to improve the achievement of objectives by 2013 to 2017. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Reviewed and approved Risk Management Framework. |  | 30 September 2012 |  | Risk Management Framework aligned with COBIT framework and developments in the COSO framework. | Risk Management Framework 2009 |  |  | Reviewed and approved risk management framework. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | -Workshop for the -Adoption of Framework | - |  | - | - |
| Changes on the framework and Council resolution |  | 30 September 2012 |  | IT Risk assessment incorporated on the framework | 30 September 2012 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R100 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Workshop of the risk management framework | 01 July 2012 |  | 30 July 2012 | 100 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| - Adoption of the framework by Council | 01 September 2012 |  | 30 September 2012 | Nil |  | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Conduct risk assessments workshops |  | To assist and advise ANDM management on the identification, prioritisation and management of risks across the organisation to improve the achievement of objectives by 2013 to 2017. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Approved Business risk register, IT risk register, Fraud risk register and action plans |  | 30 June 2013 |  |  | Identification of key risks, identification of controls, implementation of action plans and enhanced reasonable likelihood to achieve institutional objectives |  | Strategic risk register 2012. |  | Facilitated business, IT and Fraud risk assessments as well as development of Action plan.. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | Updated risk register | Updated risk register |  | Updated risk register | Updated risk register |
| Risk registers, action plans and Council Resolution |  | 30 June 2013 |  |  | Risk registers, action plans and monthly reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R160 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Operational Risk assessments | 01 October 2012 |  | 31 December 2012 | Nil |  | R50 000.00 |  | Nil |  |  | Nil |  |  |
| - Operational Risk assessments | 01 January 2013 |  | 31 March 2013 | Nil |  | Nil |  | R50 000.00 |  |  | Nil |  |  |
| - Strategic Risk assessments | 01 April 2013 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | R60 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Risk management awareness workshops |  | To assist and advise ANDM management on the identification, prioritisation and management of risks across the organisation to improve the achievement of objectives by 2013 to 2017. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of awareness workshops conducted |  | 30 June 2013 |  |  | Better understanding of risk management |  | - |  | 3 Workshops |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | - | - |  | 3 | - |
| Agenda, attendance registers and presentation slides |  | 30 June 2013 |  |  | Reduced number of risks on the risk register and risk management item reported on management meetings. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R150 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Conduct awareness workshops | 01 February 2013 |  | 31 March 2013 | Nil |  | Nil |  | R150 000 |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Review of Fraud prevention plan and Antcorruption Strategy | To assist and advise management in ensuring that ANDM complies with all relevant laws and regulations by 2014. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Reviewed and adopted Fraud prevention Plan and Anti Corruption Strategy | 31 December 2012 |  | Reduced exposure to fraud and corruption |  | Fraud prevention plan 2008 |  | Fraud Prevention Plan and Anticorruption Strategy |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  |  | Development compliance register | Monitoring |  | Monitoring |
| Council resolution | 31 December 2012 |  | Quartely Reports on implementation of Fruad Prevention Action Plan |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R200 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Conduct Fraud Risk assessment | 01 August 2012 | 30 August 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Development of Fraud prevention Pln and Anti-corruption strategy | 01 September 2012 | 31 December 2012 |  | R50 000.00 |  | R150 000.00 |  | Nil |  |  | Nil |  |
| - Monitor implementation and report quartely | 14 January 2013 | 30 June 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Conduct annual fraud awareness workshops. |  | To assist ANDM in ensuring an efficient, economical and transparent business that is free from fraud and corruption by 2017. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of Workshops conducted |  | 30 June 2013 |  |  | Better understanding of fraud risk management |  |  |  | 3 Awareness Workshops |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | - | 1 |  | 1 | 1 |
| Agenda, attendance registers and presentation slides |  | 30 June 2013 |  |  | Reduced number of fraud cases |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 600 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Fraud awareness workshops | 01 October 2012 |  | 30 June 2013 | Nil |  | R200 000.00 |  | R200 000.00 |  |  | R200 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate the engagement of fraud or forensic invastigators. |  | To assist ANDM in ensuring an efficient, economical and transparent business that is free from fraud and corruption by 2017. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Forensic investigations |  | 30 June 2013 |  |  | Implemnetation of the recommendations of forensic report |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| Service level agreement between the service provider and ANDM |  | 30 June 2013 |  |  | Forensic reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R100 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Fraud investigation | 01 July 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | R100 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good governance and public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Risk Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Risk and Compliance Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Capacitate LMs on risk Management (workshops and establishment of RM Units) |  | To assist and advise Local Municipalities under ANDM on the identification, prioritisation and management of risks across the organisation to improve the achievement of objectives by 2013 to 2017. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of workshops and appointment of risk Champions in the LMs |  | 30 June 2013 |  |  | Identification of key risks, identification of controls, implementation of action plans and enhanced reasonable likelihood to achieve institutional objectives by LMs |  | None |  | 4 Local Municipalities |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 4 |
| Attendance Regsters and signed Memorandum of Understanding |  | 30 June 2013 |  |  | Risk Registers |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Undertake preliminary engagement meetings with LMs | 01 July 2012 |  | 31 July 2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| - Provide assistance to LMS on the facilitation of the risk assessment | 01 October 2012 |  | 30 June 2013 | Nil |  | R100 000.00 |  | Nil |  |  | R100 000.00 |  |  |

1.5	COUNCIL SUPPORT UNIT

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Development of the Council Calendar |  | To ensure effective functioning of council and council structures |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Approved Council Calendar |  | 30 September 2012 |  | An Approved Council Calendar and adhered to |  | 2011/2012 Approved Council Calendar |  |  | Council Calendar Approved and Four Council Sittings |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 Council Sitting | 1 Council Sitting |  | 1 Council Sitting | 1 Council Sitting |
| Council Resolution |  | 30 September 2012 |  | Minutes of Council and Committee sittings per quarter |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R150 000.00 |  | VOTE NUMBER |  | 110544019 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Develop and facilitate the approval of the Council Calendar | 01 July 2012 |  | 30 September 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| - Coordinate Council and Committee Sittings | 01 July 2012 |  | 30 June 2013 |  | R37 500.00 |  | R37 500.00 | R37 500.00 |  |  | R37 500.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Development of MPAC Programme of Action | To improve functioning of oversight structures, systems and processes |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Adopted MPAC Oversight Report for Annual Report 2011/2012 | 29 March 2013 |  | MPAC Oversight Report |  | Established MPAC |  | -Approved MPAC Oversight Report by Council. -Four meetings |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  | MPAC Quarterly Report |  | MPAC Quarterly Report |  | MPAC Quarterly Report | MPAC Quarterly Report |
| Council Resolution | 30 June 2013 |  | An adopted MPAC Oversight Report on annual report 2011/2012 |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R200 000.00 |  | VOTE NUMBER |  | 110544074 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |  |
| - Formulate MPAC Programme of Action | 01 July 2012 | 31 July 2012 |  | Nil |  | Nil |  | Nil |  | Nil |  |  |
| - Coordinate MPAC Sittings | 01 July 2012 | 30 June 2013 |  | R7 500.00 |  | R7 500.00 |  | R7 500.00 |  | R7 500.00 |  |  |
| - Conduct workshop on MPAC programme | 01 July 2012 | 31 July 2012 |  | 20 000.00 |  | Nil |  | Nil |  | Nil |  |  |
| - Conduct public hearings | 01 February 2013 | 29 March 2013 |  | R37 500.00 |  | R37 500.00 |  | R37 500.00 |  | R37 500.00 |  |  |
| - Develop MPAC Oversight Report | 01 March 2013 | 29 March 2013 |  |  |  |  |  |  |  |  |  |  |
| - MPAC Oversight Report submitted to Council for adoption | 25 March 2013 | 29 March 2013 |  | Nil |  | Nil |  | Nil |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Update Council Resolution Register | To improve functioning of oversight structures, systems and processes |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Number Council Resolution implemented | 30 June 2013 |  | Improved Service Delivery and Council oversight Role |  |  | Council Resolution Register 2010 |  | 100% implementation of Council Resolutions |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | 25% implemntation of Resolutions |  | 25% implemntation of Resolutions | 25% implemntation of Resolutions |  | 25% implemntation of Resolutions |
| Quarterl Progress Reports on implementation of Council Resolutions | 30 June 2013 |  | Auditor General’s report on oversight role |  |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | NIL |  | VOTE NUMBER |  |  | NIL |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| - Continues update of Resolution Register |  | 01 July 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Updated Resolution Register submitted to the Municipal Manager for implementation |  | 01 July 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |
| - Develop a Resolution Tracking Register that will serve as a proof of submitted Resolution Register to the Municipal Manager. |  | 01 July 2012 |  | 30 June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Develop Public Participation Strategy and Policy | To improve functioning of oversight structures, systems and processes |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Approved Public Participation Strategy and Policy | 31 December 2012 |  | An improved Public Participation in the Municipal Affairs |  | - |  |  | Approved Public Participation Strategy and Policy |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 Pibli participation Strategy and policy |  |  |
| Council Resolution | 31 December 2012 |  | Pettions Register adopted by Council |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R250 000.00 |  | VOTE NUMBER |  | 110544082 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| - Conduct research on public participation strategy and policy | 01 July 2012 | 15 August 2012 |  | Nil |  | R250 000.00 | Nil |  |  | Nil |  |
| - Formulate a draft working document on public participation strategy and policy | 15 August 2012 | 15 September 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Tabling of draft strategy and policy to council committees | 15 September 2012 | 30 September 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Conduct policy workshop | 01 October 2012 | 31 October 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Tabling of the draft strategy and policy to Council for approval | 01 December 2012 | 15 December 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Conduct Outreach Programmes for community participation | To improve Internal and External Communication |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Number Public gatherings conducted | 30 June 2013 |  |  | An approved Public Participation in the Municipal Affairs |  | - |  |  | Cumulative number of Outreach programmes conducted |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 MPAC Public Hearing | Coordinate MPAC Roadshows | MPAC Public Hearings on annual report | IDP & Budget Roadshow |
| Attendance Registers and Public Comments | 30 June 2013 |  |  | Petitions Register adopted by Council |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R150 000.00 |  |  | VOTE NUMBER |  | 110544082 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| - Develop Outreach Porgrammes |  | 01 July 2012 | 30 September 2012 |  | Nil |  | Nil | R150 000.00 |  |  | Nil |  |
| - Conduct research/ survey on service delivery |  | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Identify areas of community concern from Complaints Register from Customer Care unit |  | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| - Conduct public hearings/ imbizos |  | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate District Speakers Forum |  | To ensure functionality of the Intergovernmental Relations (IGR) Structures |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of District Speakers Forum held |  | 30 June 2013 |  | Improved coordination of Council proceedings across the district |  |  | - |  | 4 District Speakers Forums Meetings convened |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 forum Meeting | 1 Forum Meeting |  | 1 Forum Meeting | 1 Forum Meeting |
| Attendance Register and Minutes of District Speakers’ Forum Meeting |  | 30 June 2013 |  | Quarterly Reports |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R50 000.00 |  | VOTE NUMBER |  |  | 110544082 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Arrange Technical Team meetings before the sitting of the District Speakers Forum | 01 July 2012 |  | 30 June 2013 |  | R5 000.00 | R5 000.00 |  | R5 000.00 |  |  | R5 000.00 |  |  |
| - Facilitate sitting of Forum Meetings | 01 July 2012 |  | 30 June 2013 |  | R7 500.00 | R7 500.00 |  | R7 500.00 |  |  | R7 500.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of Support to Council and its committees |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Office of the Speaker |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Coordinate District Whippery Forum |  | To ensure functionality of the Intergovernmental Relations (IGR) Structures |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number District Whippery Forums held |  | 30 June 2013 |  | Improved coordination of Council proceedings across the district |  | - |  | 4 District Whippery Forums Meetings convened |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 1 forum Meeting |  | 1 Forum Meeting | 1 Forum Meeting | 1 Forum Meeting |
| Attendance Register and Minutes of District Whippery Forum Meetings |  | 30 June 2013 |  | Quarterly Reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  | VOTE NUMBER |  | 110544075 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| - Arrange sitting of Multi-party meetings before the sitting of the District Whippery Forum | 01 July 2012 |  | 30 June 2013 |  | R12 500.00 |  | R12 500.00 |  | R12 500.00 |  | R12 500.00 |  |
| - Facilitate sitting of Forum Meetings | 01 July 2012 |  | 30 June 2013 |  | R12 500.00 |  | R12 500.00 |  | R12 500.00 |  | R12 500.00 |  |
| - Workshop councilors on reporting about their constituency work, roles and accountability to communities | 01 October 2012 |  | 31 December 2012 |  | Nil |  | Nil |  | R100 000.00l |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Public Participation |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Office of the Speaker |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |
| Coordinate District Public Participation Forum | To ensure functionality of the Ward Committees and Community Development Workers (CDWs) |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |
| Number of District Public Participation Forum meetings held | 30 June 2013 |  | An approved Public Participation in the Municipal Affairs |  | - |  | 4 District Public Participation Forum Meetings convened |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  | 1 forum Meeting | 1 Forum Meeting | 1 Forum Meeting | 1 Forum Meeting |
| Attendance Register and Minutes of District Public Participation Forum Meetings | 30 June 2013 |  | Pettions Register adopted by Council |  | 30 June 2013 |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R50 000.00 |  | VOTE NUMBER |  | 110544082 |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  | QUARTER 4 |  |
| - Arrange sitting of Ward Committee and CDW Coordinators’ meetings before the sitting of the District Public Participation Forum | 01 July 2012 | 30 June 2013 |  | R12 500.00 |  | R12 500.00 | R12 500.00 |  | R12 500.00 |  |
| - Verify the functionality of ward committees | 01 October 2012 | 29 March 2013 |  | Nil |  | Nil | Nil |  | Nil |  |
| - Conduct the audit of ward offices | 01 August 2012 | 29 March 2013 |  | Nil |  | Nil | Nil |  | Nil |  |
| - Provide necessary support to ward committees. | 01 July 2012 | 30 June 2013 |  | Nil |  | Nil | Nil |  | Nil |  |

1.6. SPECIAL PROGRAMMES UNIT

    - DISABILITY DEVELOPMENT PROGRAMMES

| NATIONAL KEY PERFORMANCE AREA |  | Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Special Groups |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager SPU |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Disability Support and Development Programmes |  | To set guidelines that will enable the ANDM to facilitate the integration of issues of people with disabilities into all policies, plans, programmes and activities of local government. To create an environment that is free of barriers, prejudice and stereotypes in order to maximize access of people with disabilities to basic services. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Review of District Disability Policy |  | 1st July 2012 |  | To have District Disability Policy that will work as a guiding document for all disability programmes |  | Policy in place but to be reviewed for implementation |  | Fully operating Disability forum with programs |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 1 awareness. 1meeting |  | 2 meetings | 1 meeting | 1meeting |
| All obstacles that prevent free, equal and effective participation of people with disabilities in decision making structures should be eliminated |  | 1st August 2012 |  | Enforcement of all legislative framework that seek to prevent prejudice, integration, discrimination and stereotypes |  | 30th June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R600 000 |  | VOTE NUMBER |  | 111544032 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Review of District Disability Policy | 01Junly 20212 |  | 30th July 2012 |  | 50 0 00 |  | Nil |  | Nil |  | Nil |  |
| District Disability Strategy | 1st August 2012 |  | 31th August 2012 |  | 50 000 |  | Nil |  | Nil |  | Nil |  |
| Awareness Campaign | 1st September 2012 |  | On going |  | 50 000 |  | ------- |  | ---------- |  | ---------- |  |
| District Disability Economic Empowerment | 1st October 2012 |  | 31st October 2012 |  | Nil |  | 150 000 |  | Nil |  | Nil |  |
| District Disability Meetings | Once a quarter |  | Last quarter of the Financial year |  | 20 000 |  | ---------- |  | ----------- |  | ------------- |  |
| Skills Development Programme | 1st October2012 |  | 31th October 2012 |  |  |  |  |  | 50 000 |  | Nil |  |
| International Day for Persons with Disabilities | 1st November 2012 |  | 03 December 2012 |  | Nil |  | Nil |  | 150 000 |  | Nil |  |
| Support and Care programme | 01 January 2013 |  |  |  | Nil |  | Nil |  | Nil |  | 50 000 |  |
| Disability and Rural Development Programmes | 1st February 2013 |  |  |  | Nil |  | Nil |  | Nil |  | 50 000 |  |
| Disability as a human rights Programme | 1st March 2013 |  | 31st March 2013 |  | Nil |  | Nil |  | Nil |  | 30 000 |  |
| Totals |  |  |  |  | 120 000 |  | 150 000 |  | 200 000 |  |  |  |

1.6.2  OLDER PERSON’S PROGRAMMS

| NATIONAL KEY PERFORMANCE AREA |  | Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Special groups |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: SPU |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Elderly programme |  | To coordinate and facilitate the integration and mainstreaming of Elderly programmes within the district to keep societal memories (norms & values) and to maintain respect and dignity for older people. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Develop District database of projects by elderly people. Coordinate and commemorate the institutionalized days. Organize Elderly awareness days Establishment of well-functional District Elderly Council. Organize intergenerational programmes Create platforms to discuss the issue of Elderly people. |  | 1st July 2012 |  | Rights of Elderly people are protected and promoted by the municipality. Policies and strategies that embrace the needs and aspirations of the elderly people are developed and implemented. The rights of the older people are protected and promoted by the municipality |  | The Structure needs to be reviewed |  |  | At least 50% of elderly be on database. 100% of the institutionalized days commemorated. One awareness per ward. At least one meeting per quarter. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1Structures 1 meeting per quarter | - 1 | - 1 | - 1 |
| Full involvement and participation of the Elderly in the mainstream of the community. |  | 1ST July 2012 |  | Legislative compliance of the institution to all laws that favors elderly people. |  | 30th April 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Develop database of Elder persons projects | 1st July 2012 |  | 30 Sept 2012 |  | 15 000 |  | - | - |  |  | - |  |
| Development of integrated District Elderly Policy | 1st Oct 2012 |  | 30th Dec 2012 |  | 100 000 |  | - | - |  |  | - |  |
| Facilitate the Elderly Economic Development and Empowerment programmes | 1st Jan 2013 |  | 30th June 2013 |  | - |  | 20 000 | 20 000 |  |  | 20 000 |  |
| Reviewal of District Older persons Forum | 1st July 2012 |  | 1st Dec 2012 |  | 20 000 |  | - | - |  |  | - |  |
| District Elderly Forum meetings | 1st July 201 |  | 30th June 2012 |  | 6 000 |  | 3 000 | 3 000 |  |  | 3 000 |  |
| Coordinate and commemorate the institutionalized days |  |  | - |  | - |  | 30 000 | - |  |  | - |  |
| International Older persons Day | 30 Nov 2012 |  | - |  | - |  | 30 000 | - |  |  | - |  |
| Golden Games | 1st Jan 2012 |  | 30 March 2012 |  | - |  | - | 50 000 |  |  | - |  |
| Organize intergenerational programme (Talk shows) | 1st Oct 2011 |  | 30th Dec 2011 |  | - |  | 20 000 | 30 000 |  |  | 20 000 |  |
| Fun day for the Elderly (Xmas Party) | 1st Oct 2011 |  | 30th Dec 2011 |  | - |  | 50 000 | Nil |  |  | - |  |
| Organize Older Persons Parliament | 1 April 2012 |  | 30th June 2012 |  | - |  | - | - |  |  | 10 000 |  |
| Easter Week end and Moral Regeneration. | Jan 2013 |  | June2013 |  | - |  | - | - |  |  | 10 000 |  |
| Older Persons in HIV and AIDS Program | Oct 2012 |  | June 2013 |  | 10 000 |  | 10 000 | 10 000 |  |  | 10 000 |  |
| TOTAL |  |  |  |  | 151 000 |  | 163 000 | 113 000 |  |  | 73 000 |  |

1.6.3	CHILDREN DEVELOPMENT PROGRAM

| NATIONAL KEY PERFORMANCE AREA | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Special Groups |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: SPU |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Children’s Programmes | To facilitate the creation of an environment that would be conducive for growth and development of our children by coordinating government and civil society within the district. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Establishment of functional structures Establishment of function children’s structures. Full involvement and participation of children on their own programmes Coordination of children’s programmes with other government departments. | 1st July 2012 |  | Mainstreaming of children’s programmes within the internal municipality programmes and Integration of children Development Plan with IDP. |  | No existing structure in place |  |  | One district Children’s council and advisory structures. Participation of children in the children support programmes. All government departments. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 1 1 | 1 1 |  | 1 1 | 1 1 |
| Existence of district children’s council active and functional | 1st July 2012 |  | SDBIP of municipal with children’s programmes. Children’s programmes integrated within IDP. |  | 30th June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R500 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Establishment of Children’s Forum | 1st July 2012 | 30 Sept 2012 |  | 5 000 |  | - | - |  |  | - |  |  |
| Development of Children’s policy | 1st July 2012 | 30 Sept 2012 |  | 80 000 |  | - | - |  |  | - |  |  |
| Establishment of Children’s Advisory Council | 01st Sept 2012 | 30 Nov 2012 |  | 5 000 |  | - | - |  |  | - |  |  |
| Establishment Children’s Net Club | 01 July 2012 | 30 June 2013 |  | 10 00 |  | - | - |  |  | - |  |  |
| Organize Children’s Parliament/Council(May Month) | 30 April 2013 | 30 June 2013 |  | 40 000 |  | - | - |  |  | - |  |  |
| Children’s Games | Jan 2013 | 201 |  | - |  | - | 50 000 |  |  |  |  |  |
| Awareness campaigns on children’s Rights and Responsibility | July 2012 | June 2013 |  | - |  | 10 000 | 10 000 |  |  | 10 000 |  |  |
| Parent Child debates | 01 Sept 2012 | 30 Nov 2012 |  | 10 000 |  | 10 000 | - |  |  | - |  |  |
| School’s health Campaigns (HIV&AIDS and substance abuse) | 01 Apr 2013 | 30 June 2013 |  | 20 000 |  | 20 000 | 20 000 |  |  | 20 000 |  |  |
| Take a girl child to work campaign | 01 April 2013 | 31 July 2013 |  | - |  | -- | - |  |  | 50 000 |  |  |
| Children in ICT | July 2012 | June 2013 |  | 10 000 |  | 10 000 | 10 000 |  |  | 10 000 |  |  |
| Children’s X –mas | Oct 2012 | Dec 2012 |  | - |  | 50 000 | - |  |  | - |  |  |
| Back to School Campaign | Jan 2013 | March 2013 |  | - |  | - | 20 000 |  |  | 20 000 |  |  |
| TOTAL |  |  |  | 180 000 |  | 100 000 | 110 000 |  |  | 110 000 |  |  |

1.6.4	GENDER PROGRAMME

| NATIONAL KEY PERFORMANCE AREA | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Special Groups |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager SPU |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| GENDER PROGRAMME | To coordinate and facilitate the integration and mainstreaming of women and men’s programs in the mainstream of the government so as to address the plight of discrimination and abuse, through Women Empowerment and Development progrms. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Establishment of men structure, women structure, young women and women’s caucus. Commemoration of institutionalized days. Awareness and capacity building | 1st July 2012 |  | Fully functioning Gender structures within the district. |  |  | Action plan for Men Gender Action plan to be reviewed. |  | Men and women working together towards the s achievement of gender based violence free society |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 1Structures 1 meeting per quarter |  | - 1 |  | - 1 | - 1 |
| Structure for men, structure women, structure young women and women’s caucus in place. All institutionalized days are commemorated. Capacity building and awareness campaigns are conducted. | 1st July 2012 |  | Executive of the structures and structures launched. Attendance registers Reports Implementation plans , attendance registers and reports |  |  | 30th June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | 600 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |  |
| Men’s sector/forum |  | 1st July 2012 |  | 30th June 2013 | 20 000 |  | - |  | - |  | - |  |  |
| Women’s forum |  | 1st July 2012 |  | 30th June 2013 | 20 000 |  | - |  | - |  | - |  |  |
| Young women’s network |  | 1st July 2012 |  | 30th June 2013 | 20 000 |  | - |  | - |  | - |  |  |
| Women’s caucus |  | 1st July 2012 |  | 30th June 2013 | 30 000 |  | - |  | - |  | - |  |  |
| National Women’s Day |  | 15 July 2012 |  | 30 Sept2012 | 20 000 |  | - |  | - |  | - |  |  |
| 16 Days of Activism |  | 1st Oct 2012 |  | 30 Dec 2012 | - |  | 50 000 |  | - |  | - |  |  |
| International Women’s Day |  | 15 January 2013 |  | 15 March 2013 | - |  | - |  | 50 000 |  | - |  |  |
| Women and HIV and AIDS |  | 1ST July 2012 |  | 30th June 2013 | 10 000 |  |  |  | 10 000 |  | 10 000 |  |  |
| Gender Based Violence Action plan review and implementation. |  | 01 Sept 2012 |  | 30 October 2012 | - |  | 100 000 |  | 40 000 |  | 30 000 |  |  |
| Men’s health awareness programme |  | 1st July 2012 |  | 30th June 2013 | - |  | - |  | - |  | 20 000 |  |  |
| Early parenthood awareness programme |  | 25 August 2012 |  | 30 October 2012 | - |  | 10 000 |  | - |  |  |  |  |
| Women with disabilities and gender based violence programme |  | 1st Oct 2012 |  | 30 March 2013 | - |  | 10 000 |  | - |  | 40 000 |  |  |
| Women Economic Development programme |  | 01November 2012 |  | 20 December2012 | - |  | 30 000 |  | 100 000 |  | - |  |  |
| TOTAL |  |  |  |  | 100 000 |  | 200 000 |  | 200 000 |  |  |  |  |

1.6.5  YOUTH DEVELOPMENT PROGRAMME

| NATIONAL KEY PERFORMANCE AREA | Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Special Groups |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager SPU |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| YOUTH DEVELOPMENT PROGRAMME | To coordinate youth empowerment, economic growth and development and expand business opportunity, and encourage youth empowerment through training and education,in collaboration with other stakeholders ,government departments and civil society. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Establishment of functioning youth structures. Full involvement and participation of youth on their own development programmes Coordination of youth programmes with other government departments and civil society to reduce (youth) unemployment rate. | June 2012 |  |  | Mainstreaming of youth programme within the internal municipality programme Integration of Youth Development Plan with IDP |  | Old Youth forum to reviewed. |  |  | Fully functioning district Youth council. 20% of projects should involve and owned by youth. All government departments and related civil society. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 1 meeting per quarter | 1 meeting per quarter | 1 meeting per quarter | 1 meeting per quarter |
| Exististance of active and vibrant District Youth Council. that seats and addresses developmental challenges faced by district youth. Existance of sustainable youth projects. Youth owned businesses. Improved literacy levels and unemployment | 1st July 2012 |  |  | SDBIP of municipal with youth programmes. Youth programmes integrated with IDP. |  | 30th June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | 800 000 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Establishment and support of functioning Youth Council |  | 1st July 2012 | 30th July 2013 |  | 10 000 |  | - | - |  |  | - |  |
| Coordinate and organize District youth council meetings. |  | 1st July 2012 | 30 June 2013 |  | 3 000 |  | 5 000 | 5 000 |  |  | 5 000 |  |
| (Review / develop youth policy) Youth strategic |  | 1st July 2012 | 30th Sept 2012 |  | 100 000 |  | - | - |  |  | - |  |
| Centralization of the database for all Youth Projects in the district. |  | 1st July 2012 | 30th June 2013 |  | - |  | - | - |  |  | - |  |
| Develop database of unemployed qualified youth. |  | 1st July 2012 | 30th June 2012 |  | - |  | - | - |  |  | - |  |
| Organize youth Parliament |  | 1st July 2012 | 30th Dec 2012 |  | - |  | 50 000 | - |  |  | - |  |
| Educational sessions |  | 1st July 2012 | 30th June 2013 |  | - |  | 20 000 | 30 000 |  |  | 50 000 |  |
| Carrier Exhibitions |  | 1st July 2012 | 30th August 2012 |  |  |  | - | 50 000 |  |  | - |  |
| Youth Bash |  | 1st Nov 2012 | 20th Dec 2012 |  | - |  | 100 000 | - |  |  | - |  |
| Youth against HIV and AIDS |  | 1st July 2012 | 30th June 2013 |  | 5000 |  | 5 000 | 15 000 |  |  | 10 000 |  |
| Youth Cultural Festival |  | 1st Aug 2012 | 30th Oct 2012 |  | 50 000 |  | - | - |  |  | - |  |
| Youth Information Days |  | 1st June 2012 | 30th July 2013 |  | 5 000 |  | 5 000 | 5 000 |  |  | 5 000 |  |
| Youth Against CRIME Stop |  | 1st July 2012 | 30th June 2013 |  | 5 000 |  | 10 000 | 10 000 |  |  | 10 000 |  |
| Youth Institutionalized Day June 16 |  | 31st April 2013 | 30th June 2013 |  | - |  | - | - |  |  | R100 000 |  |
| MS ANDM (Beauty Pageant) |  | 1st July 2012 | 30th Sept 2012 |  | 100 000 |  | - | - |  |  | - |  |
| Executive Mayoral Cup |  | 1st April 2013 | 30th June 2013 |  | - |  | - | - |  |  | 50 000 |  |
| Youth Economic Sessions |  | 1st April 2013 | 30th June 2013 |  | - |  | 50 000 | - |  |  | 50 000 |  |
| Total |  |  |  |  | 278 000 |  | 245 000 | 115 000 |  |  | - 000 |  |

1.6.6 EDUCATION AND AWARENESS PROGRAMMES

| NATIONAL KEY PERFORMANCE AREA |  | Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Special Groups |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager SPU |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| HIV and AIDS EDUCATION AND AWARENESS PROGRAMME |  | To provide HIV and AIDS Information and Education that will be relevant, effective, accessible, affordable and culturally appropriate to the Alfred Nzo Community especially in rural areas. To sensitize communities about the disease and its impact in the socio-economic development of the individual, family and the community at large. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Procurement and distribution of Information and education material (IEC) for the district. Integration of HIV and AIDS Programme with SPU. Increase user friendly, community based condom sites. Coordinate the hosting of Local, International and National institutionalized days. |  | 1st July 2012 |  | Communities have access to HIV and AIDS information. Mainstream HIV and AIDS programmes on Gender, Youth, children and people with disability to increase access to information. Accessibility of condoms to rural communities. |  | Program is currently running. |  | One distribution site per ward, and to all public/social gatherings. Host one integrated event per quarter. Two or more condom sites per ward. 100% of institutionalized days |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 3 visits per quarter | 3 visits per quarter |  | 3 visits per quarter | 3 visits per quarter |
| Number of Wards with access to Information. SPU Programmes integrated with HIV and AIDS. No of rural user-friendly sites established with regular supply of condoms. HIV & AIDS events coordinated and hosted. |  | 1st July 2012 |  | All communities of the district are well informed about HIV and AIDS with positive living life styles. |  | 30th June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 500 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Draw a plan for Awareness Outreach programmes. | 1st July 2012 |  | 31st July 2012 |  | - | - | - |  |  | - |  |  |
| Identification of suitable user friendly sites and distribution of condom sites | 1st August 2012 |  | 30th August 2013 |  | 2 000 | 2 000 | 2 000 |  |  | 2 000 |  |  |
| Establish High Transmission intervention Sites (HTA). | 1st September 2012 |  | 1st August 2013 |  | 10 000 | 15 000 | 15 000 |  |  | 15 000 |  |  |
| Coordinate and commemorate the HIV and AIDS Institutionalized days. | 1st Oct 2012 |  | 30th June 2013 |  | 50 000 | 50 000 | 50 000 |  |  | 50 000 |  |  |
| Conduct awareness and education campaigns. | 1st Sept 2012 |  | 30th June 2013 |  | 50 000 | 50 000 | 50 000 |  |  | 50 000 |  |  |
| Attend provincial, National and International HIV and AIDS Workshops /conferences. | 1st Sept 2012 |  | 30th June 2013 |  | 10 000 | 30 000 | 10 000 |  |  | 10 000 |  |  |
| TOTAL |  |  |  |  | 122 000 | 147 000 | 127 000 |  |  | - 0 |  |  |

1.6.7	 DISTRCT AIDS COUNCIL AND LOCAL AIDS SUPPORT PROGRAMME

| NATIONAL KEY PERFORMANCE AREA |  | Service Delivery |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Special Groups |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager SPU |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |
| District AIDS and Local AIDS Council Support |  | Coordination of HIV and AIDS Programmes throughout the District. Support functioning of District AIDS Council and Local AIDS Councils of the 4 Local Municipalities |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |
| -Coordinate the re establishment and capacitate active DAC and LACs structures -Ensure availability of policies guiding working relations of all AIDS Council structures. -Implemented HIV and AIDS programs through LAC and DAC structures. -Coordinate Capacity building for District stakeholder’s (DAC / LAC members, Municipal employees, Councilors, THPs, TLs, FBOs, CBOs /NGOs). |  | 1ST July 2012 June 2013 |  | Reduced HIV and AIDS related mortality and morbidity rates. |  | 30th June 2013 |  | Well coordinated DAC with full support to local AIDS Councils |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 1 DAC meeting per quarter district and ECAC | 1 DAC meeting per quarter district and ECAC | 1 DAC meeting per quarter district and ECAC | 1 DAC meeting per quarter district and ECAC |
| Institutionalised days celebrated and commemorated |  | 30 March 2013 |  | Report |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 100 000 |  | VOTE NUMBER |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Coordinate and organize DAC Meetings | 1st July 2012 |  | 30TH June 2013 |  | 3 000 | 3 000 | 3 000 |  |  | 3 000 |  |
| Capacity building for Community Leaders and LAC and DAC Members. | 1st July 2012 |  | 30TH June 2013 |  | 20 000 | 30 000 | 10 000 |  |  | 10 000 |  |
| Facilitate the recruitment and appointment LAC coordinators by LMs. | 1st July 2012 |  | 30TH June 2013 |  | - | - | - |  |  | - |  |
| Attend Eastern Cape AIDS council meetings, workshops and events | 1st July 2012 |  | 30TH June 2013 |  | 5 000 | 5 000 | 5 000 |  |  | 5 000 |  |
| Develop plan for HIV and AIDS outreach Programme | 1st July 2012 |  | 30TH June 2013 |  | 5 000 | 5 000 | 5 000 |  |  | 5000 |  |

- INFRASTRUCTURE DEVELOPMENT AND MUNICIPAL SERVICES

2.1	WATER SERVICES AUTHORITY UNIT

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Water Safety Plan |  | To ensure safe drinking water through good water supply practices from catchments to consumer. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Water Safety Plan approved by council |  | 30 March 2013 |  |  | Provision of safet drinking water to the communities. ANDM comply with DWA requirements. |  | Water safety plan based on the old ANDM demarcation |  | ANDM Water Safety Plan completed as per Blue water services audit. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 1 | 0 |
| Council resolution obtained |  | 30 April 2013 |  |  | Improved BDS score No compliance notices from DWA |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R350 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Procurement processes | 1/07/2012 |  | 1/09/2012 | R200 000.00 |  |  |  |  |  |  |  |  |  |
| Implementation | 01 /12/2012 |  | 30/06/2013 | Nil |  | R50 000.00 |  | R25 000.00 |  |  | R25 000.00 |  |  |
| Water Proficiency testing | 31/01/2013 |  | 30/06/2013 | Nil |  | Nil |  | 25 000.00 |  |  | 25 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Implemetation of Health and Safety Plan | -To ensure compliance with occupational health and safety act. -To equip employees with the skills to identify health and safety hazards in the workplace |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Equip all water and waste water treatment works employees with skills to identify health and safety hazards | 30 March 2013 |  | Reduced number of employees suffering from health related issues |  |  | High rate of absenteeism due to health problems |  | All WTW and WWTW personnel immunised and trained on health and hygiene issues. |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | 0 |  | 0 | 0 |  | 1 |
| All WTW and WWTW personnel immunised and trained on health and hygiene issues. | 30 June 2013 |  | Good work attendance Reduced number of sick leaves |  |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R350 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| -Unpack implementation plan into workable activities |  | 01/07/ 2012 |  | 30/08/ 2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |
| -Training of Health and safety representatives |  | 1/09/2012 |  | 31/ 12/2012 |  |  | R100 000.00 |  |  |  |  |  |  |
| Procure and service the existing first aid kits |  |  |  |  |  |  |  |  | R50 000.00 |  |  |  |  |
| Establish occupational health and safety committee |  |  |  |  |  |  |  |  |  |  |  |  |  |
| -Implement the contingency/emergency evacuation plan for all the water treatment works -Induction of Staff in Health and Safety, fire safety, first Aid, general health and hygiene. |  |  |  |  |  |  |  |  |  |  |  | R50 000.00 |  |
| -Installation of Rails along walkways |  |  |  |  |  |  |  |  | R25000 .00 |  |  | R25000.00 |  |
| -Improvement of current Medical Surveillance system (procedures) |  |  |  |  |  |  | R50 000.00 |  | R25000. 00 |  |  | R25 000.00 |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER / RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Implementation of Groundwater Management Plan | To ensure a sustainable development of resources for various groundwater users. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Groundwater protocol implemented Four existing regional water supply boreholes equipped | 30 June 2013 |  | Sanitation projects comply with DWA standards Performance of Regional boreholes measured |  | Groundwater management plan and groundwater protocol at draft stage. |  | 2012/2013 VIP toilets to comply with Groundwater protocol Four regional boreholes equipped with data loggers |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| ANDM social facilitators and ISD consultants trained on groundwater protocol Four Boreholes equipped with data loggers | 30 June 2013 |  | VIP toilets not build on sensitive areas VIP toilets in partially sensitive areas will be lined. Regional boreholes not drying out without any warning. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop ANDM groundwater report archive - Integration with DWA | 30/08/2012 | 31/12/2012 |  | R100 000.00 |  |  |  |  |  |  |  |
| Refine Data Improvement Plan & implement |  |  |  |  |  | R250 000.00 |  |  | R250 000.00 |  |  |
| Refine Data Improvement Plan & implement |  |  |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Borehole equipping with data logging equipment |  |  |  |  | R300 000.00 | R300 000.00 |  |  |  |  |  |
| Develop groundwater database |  |  |  |  | R250 000.00 | R50 000.00 |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Dam Safety plan | To ensure safe drinking water through good water supply practices from catchments to consumer. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Municipal Dam Safety Plan approved by council | 30 March 2013 |  | Safe and well managed municipal water dams |  |  | Existing dam safety plan on draft stage |  | Completed dam safety plan |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Council resolution for the plan obtained | 30 April 2013 |  | Reduced siltation in ANDM dams Dams free of alien invasive species |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R300 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Submit the plan to DWA for approval | 31/08/2012 | 1/11/2012 |  | NIL |  |  |  |  |  |  |  |  |
| Removal of alien invasive plants | 30/11/2012 | 30/06/2013 |  | Nil | R100 000.00 |  | R100 000.00 |  |  | R100 000.00 |  |  |
| Installation of silt traps |  |  |  | Nil | NIL |  | NIL |  |  | NIL |  |  |
| MNR sewage investigation and replacement to be implemented. |  |  |  | Nil | NIL |  | NIL |  |  | NIL |  |  |
| Establish water sampling points within the dam basin as well as up- and downstream of the dam. |  |  |  | Nil | NIL |  | NIL |  |  | NIL |  |  |
| Erect clear signboards in and around the dams |  |  |  | Nil | Nil |  | Nil |  |  | NIL |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of Emergency Response Plan for waterborne disease outbreak |  | To have a plan that would be utilized during waterborne disease outbreak |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Communities in high risk areas workshoped on waterborne diseases |  | 30 June 2013 |  | Increased preparedness in case of waterborne disease outbreak |  |  | Draft Emergency Response Plan in place |  | Well informed communities |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 | 1 |  | 1 | 1 |
| Knowledgable communities in terms of what to do in case of the outbreak and who to contact. |  | 30 June 2013 |  | Trained outbreak response team Increased awareness amongst high risk communities |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R700 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop implementation plan | 1/09/2012 |  | 30/09/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Training of outbreak response team | 1/09/2012 |  | 30/09/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Conduct community workshops in communities varying from high potential areas to low potential areas | 1/10/2012 |  | 30/06/2013 |  | Nil | R50 000.00 |  | R50 000.00 |  |  | R50 000.00 |  |  |
| Procurement of emergency stock when necessary. | 1/10/2012 |  | 30/06/2013 |  | R100 000.00 | R100 000.00 |  | R150 000.00 |  |  | R200 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Water Quality Monitoring |  | To ensure safe drinking water through good water supply practices from catchments to consumer. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Water quality compliance samples analysed monthly on an accredited laboratory |  | 30 June 2013 |  |  | Improved water quality results on a monthly basis |  | Water quality monitoring tools are all at draft stage. |  | Improved GDS and BDS score |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Water quality sample results uploaded on the BDS and GDS system |  | 30 June 2013 |  |  | Improved Annual BDS report from national DWA |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Conduct SANS audit | 31/01/2013 |  | 30/06/2013 | nil |  | nil |  | 200 000.00 |  |  | 100 000. 00 |  |  |
| Monthly compliance sampling for drinking and waste water | 01/07/2012 |  | 30/06/2013 | 25 000 .00 |  | 25 000.00 |  | 25 000.00 |  |  | 25 000.00 |  |  |
| WWRAP implementation | 01/08/2012 |  | 30/06/2013 |  |  | 100 000.00 |  | 250 000.00 |  |  | 250 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Waste to Wood nurseries | To capacitate community members through promotion of greening. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Ntabankulu Nursery established | 30 June 2013 |  | -Enough Trees and ornamental plants produced for greening of town and schools. -Awareness by the stakeholders including school children about the importance of greening for sustainable environment |  |  | Existing nurseries in two local municipalities |  | Complete and operational nursery in Ntabankulu. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Ntabankulu Nursery structure completed Nusery handed over to project members | 30 June 2013 |  | Fenced site with necessary equipment for nursery -Well capacitated project members |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R500,000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Establishment of Project Steering Committee | 01/07/2012 | 31/07/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Establishment of legal entity | 01/08/2012 | 31/10/2012 |  | R15 000.00 | R35 000-00 |  | Nil |  |  | Nil |  |  |
| Conducting Environmental Basic Assessment | 15/07/2012 | 30/10/2012 |  | R50 000.00 | R50 000-00 |  | Nil |  |  | Nil |  |  |
| Project members training | 15/10/2012 | 15/12/2012 |  | Nil | R50 000.00 |  | Nil |  |  | Nil |  |  |
| Site preparation and construction | 15/09/2012 | 31/05/2013 |  |  | R70 000. 00 |  | R75,000.00 |  |  | R75,000.00 |  |  |
| Exposure visits | 01/04/2013 | 30/05/2013 |  | Nil | NIL |  | NIL |  |  | R30 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Implementation of Environmental Management Plan (EMP) |  | -To promote safe environmental management practices within the district. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Eradicate alien invasive plants in four local municipalities |  | 30 June 2013 |  | More land for development and for grazing | Existing EMP under review |  |  | Four local municipalities to have one alien eradication project. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 4 |
| Rehabilated land free of aliens vegetation |  | 30 June 2013 |  | Reduced problem of wattle in land that could be used for development. | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Appointment of Service Provider | 01/07/2012 |  | 30/08/2012 | R20 000-00 |  |  |  |  |  |  |  |  |
| -Establishment of Project Steering Committee | 01/10/2012 |  | 31/10/2012 |  |  |  |  |  |  |  |  |  |
| -Preparation of EMP | 01/09/2012 |  | 30/03/2013 |  |  | R100 000-00 | R200 000-00 |  |  |  |  |  |
| -Stakeholder consultation | 01/11/2012 |  | 28/02/2013 |  |  |  | R50 000-00 |  |  |  |  |  |
| -Final production of EMP | 01/04/2013 |  | 31/04/2013 |  |  |  |  |  |  | R130 000-00 |  |  |
| Appointment of Service Provider | 01/07/2012 |  | 30/08/2012 | R20 000-00 |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| IMPLEMENT INTEGRATED WASTE MANAMENT PLAN (IWMP) |  | -To integrate and optimise waste management, - To improve the quality of life of all South Africans including in the ANDM. -To promote safe environmental management practices within the district. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Clear illegal dumping sites in all four local municipalities Erect rubbish bins |  | 30June 2013 |  | Clean towns in ANDM |  | Existing IWMP under reviewal |  |  | All ANDM towns to have rubbish bins and to have less dumping sites |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 | 0 | 1 |
| Illegal dumping sites rehabilitated and greened Less waste on the streets |  | 30 June 2013 |  | Less litter in ANDM towns |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Appointment of Service providers | 01/08/2012 |  | 30/10/2012 |  |  |  | R100 000-00 | Nil |  |  | Nil |  |
| -Establishment of Project Steering Committee | 01/10/2012 |  | 31/10/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| -implementation of the projects | 01/09/2012 |  | 30/06/2013 |  | Nil |  | Nil | R200 000-00 |  |  | R200 000-00 |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Community based natural resource management (CBNRM) | -To capacitate local people in protecting their land, water, animals and plants. -To enable local people to play part in improving their quality of life: economically, culturally and spiritually. -To promote safe environment management practices within the district. -To protect natural resources and at the same time bring long lasting benefits to the community. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| One CBNRM project established in Mbizana | 30 June 2013 |  | Well established community organization/business |  | One CBNRM project established in Matatiele LM |  |  | One CBNRM project established in Mbizana LM |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  | 1 |
| CBNRM project handed over to project members | 30June 2013 |  | -Improved awareness in the community and other stakeholders about community based natural resources Wattle cleared in the catchment’s area and within the indigenous forest. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R200 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Draft terms of reference | 01/07/2012 | 30/08/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Establishment of Project Steering Committee | 01/08/2012 | 30/08/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Consultation with stakeholders | 01/08/2012 | 30/08/2012 |  | R10 000.00 |  | Nil | Nil |  |  | Nil |  |
| Facilitate Land acquisition | 01/08/2012 | 30/10/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Undertake Environmental Impact Assessments | 15/10/2012 | 31/01/2013 |  | R50 000.00 |  | R50 000-00 | R50 000-00 |  |  | Nil |  |
| Establishment of legal entities | 15/01/2013 | 15/02/2013 |  | Nil |  | Nil | R40 000-00 |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste Buy Back Centers | -To encourage community members in the district to clean up their villages - To create job opportunities for community members via waste collection - To minimize waste and its impacts within the district |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Waste buyback center established in Ntabankulu | 30 June 2013 |  |  | Landfill site will comply to Environmental Affairs standards and requirements |  | No buyback center in Ntabankulu |  |  | One complete and operational Waste buyback center in Ntabankulu LM. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |
| Storage house comleted and handed over to project members | 30 June 2013 |  |  | No burning of waste at the landfill site |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R200 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Consultation with interested recycling initiatives |  | 01/07/2011 | 30/08/2011 |  | R50 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| Land acquisition |  | 01/08/2011 | 30/10/2011 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| Establishment of Project Steering Committee |  | 31/07/2012 | 30/08/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| Conduct Community awareness campaigns |  | 15/02/2013 | 30/06/2013 |  | Nil |  | Nil | R50 000-00 |  |  | R50 000-00 |  |  |
| Registration of a cooperative |  | 15/01/2013 | 30/03/2012 |  | Nil |  | Nil | R50 000.00 |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure safe and healthy environment for ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Waste Management Training and Awareness |  | To raise awareness and to educate people on waste related issues. -To encourage community members in the district to clean up their villages - To minimize waste and its impacts within the district |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Waste awareness campaigns conducted in all four local municipalities |  | 30 June 2013 |  |  | -Well capacitated communities |  | None |  | Conduct waste awareness and traiing in all ANDM LMs |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Attendance registers and orders for awareness material |  | 30 June 2013 |  |  | -training and awareness conducted in four local municipalities |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R100 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Awareness campaign | 15/10/2011 |  | 15/12/2011 | Nil |  | R50 000-00 |  | Nil |  |  | Nil |  |  |
| Training and education workshop | 15/01/2012 |  | 30/03/2012 | Nil |  | Nil |  | R25 000-00 |  |  | Nil |  |  |
| Road shows(distribution of pamphlets) | 01/04/2012 |  | 30/06/2012 | Nil |  | Nil |  | Nil |  |  | R25 000-00 |  |  |
| Awareness campaign | 15/10/2011 |  | 15/12/2011 | Nil |  | R50 000-00 |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Exploring other revenue collection system | To seek other means of revenue collection system by 2013. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of new pay points established and functional | 30 June 2013 |  |  | Enhanced revenue collection |  | Direct deposits & over-the-counter payment. |  |  | 4 Pay point systems for the ANDM. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 2 | 2 |
| Service Level Agreements signed between Municipality and Pay point Institutions | 30 June 2013 |  |  | Section 71 reports (Monthly/ quarterly Financial Statements) |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONE2305S/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Drafting of terms of reference for submission to SCM. |  | 01July 2012 | 30 July 2012 |  | 0 |  | 0 | 0 |  |  | 0 |  |  |
| Procurement of the service provider to undertake the project. |  | 1 August 2012 | 30 September 2012 |  | R10 000.00 |  | 0 | 0 |  |  | 0 |  |  |
| Exploring of other revenue collection |  | 01 October 2012 | 15 May 2013 |  | 0 |  | 0 | R245 000 |  |  | R245 000 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Credit control and debt collection policy | To review the credit control and debt collection policy by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Approved credit control and debt collection policy by the Council. | 29 March 2013 |  |  | Increased percentage of revenue collected by the ANDM. |  | Summarized version of credit control & debt collection policy that does not address impairment. |  |  | Two reviewed policies (Credit control and Debt collection policy). |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 2 Policies | 0 |
| Council resolution on the approved credit policy and debt collection policy. | 30 June 2013 |  |  | Section 71 reports (Monthly/ quarterly Financial Statements) |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONE2305S/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Drafting of terms of reference for submission to SCM. |  | 01 October 2012 | 30 October 2012 |  | 0 |  | 0 | 0 |  |  | 0 |  |  |
| Procurement of the service provider to undertake the project. |  | 1 November 2012 | 31 December 2012 |  | R10 000.00 |  | 0 | 0 |  |  | 0 |  |  |
| Development of credit control and debt collection policy |  | 14 January 2013 | 29 March 2013 |  | 0 |  | 0 | R490 000.00 |  |  | 0 |  |  |
| Approval of the policy by the Council |  | 15 June 2013 | 30 June 2013 |  | 0 |  | 0 | 0 |  |  | 0 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation and Water demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Eradication of Alien Plants & restoration of ANDM Catchments |  | To eradicate IAP’s (Wattle) and reduce erosion effects in some ANDM Dam Catchments as one of the WCDM catchment management strategy by 2013. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number Hectare of Dam Catchment area cleared IAPs (wattle). |  | 30 June 2013 |  | Improved dam yield |  |  | Ntenetyana Dam catchments being eradicated |  | One Dam Catchment |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Quarterly progress reports and one final report. |  | 30 June 2013 |  | Bulk meter reading records at the source point. |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 000 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Procurement of a Service providers and contracted local labour. | 01 September 2012 |  | 30 November 2012 |  | R10 000.00 | 0 |  | 0 |  |  | 0 |  |  |
| Clearing of Alien Plants | 14 January 2013 |  | 31 May 2013 |  | 0 | 0 |  | R495 000.00 |  |  | R495 000.00 |  |  |
| Final report by the Service provider | 01 June 2013 |  | 15 June 2013 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Water Conservation & Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: Water Conservation Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Tariff modeling & Tariff Policy for the ANDM | To determine cost of water provisioning, policy and a Tariff Modeling Tool in the ANDM by 2013 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Approved or adopted tariff policy and tariff modeling tool by the Council. | 29 March 2013 |  | Improved cost recovery on water provision |  | No water supply scheme costed & no tariff tool. |  | One completed tariff policy and tariff modelling tool. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  | 0 | 0 |  | 1 |  |
| Council resolution that the policy has been approved. | 29 March 2013 |  | Improved revenue collection for the ANDM. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of Reference drafted & submitted to SCM. | 01 October 2012 | 30 October 2012 |  | 0 | 0 | 0 |  |  | 0 |  |  |
| Procurement of Service provider | 01 November 2012 | 15 December 2012 |  | R10 000.00 | 0 | 0 |  |  | 0 |  |  |
| Costing of water provisioning, tariff modeling tool and policy development | 14 January 2013 | 29 March 2013 |  | 0 |  | R490 000.00 |  |  | 0 |  |  |
| Approval of the Policy by the Council. | 01 June 2013 | 30 June 2013 |  | 0 | 0 | 0 |  |  | 0 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation and Water demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Water Conservation awareness campaigns in the ANDM. |  | To educate the communities of the ANDM about the importance of conserving water as a resource by 2013. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of awareness road shows undertaken in targeted communities or areas in the ANDM. |  | 30 June 2013 |  |  | Increased water use efficiency |  | None |  | 5 road shows |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 3 | 2. |
| Attendance register and progress and final report |  | 30 June 2013 |  |  | Reduced water losses |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Organising road shows | 15 January 2013 |  | 31 January 2013 | 0 |  | 0 |  | R5000.00 |  |  | 0 |  |  |
| Undertaking the road shows | 02 February 2013 |  | 31 May 2013 | 0 |  | 0 |  | R97 500.00 |  |  | R97 500.00 |  |  |
| Final Reporting on the road shows. | 01 June 2013 |  | 15 June 2013 | 0 |  | 0 |  | 0 |  |  | 0 |  |  |

| NATIONAL KEY PEFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation & Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Installation of pre-paid sales meters and devices in urban areas of ANDM. |  | To enhance revenue collection system in the ANDM. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of pre-paid meters installed in most ANDM urban households. |  | 30 June 2013 |  | Increased revenue collection due to increased number households with meters (billed) |  | Matatiele and Cedarville town house holds. |  | 1000 households served with pre-paid system. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 250 |  | 250 | 500 |
| Happy letters from households |  | 30 June 2013 |  | Monthly Statements (Section 71 report) |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 000 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of reference submitted to SCM. | 15 August 2012 |  | 31 August 2012 | 0 | 0 |  | 0 |  |  | 0 |  |  |
| Procurement of Service provider. | 01 September 2012 |  | 31 September 2012 | R10 000.00 | 0 |  | 0 |  |  | 0 |  |  |
| Installation of pre-paid meters in the ANDM town households. | 01 October 2012 |  | 15 May 2013 | 0 | R747 500.00 |  | R 747 500.00 |  |  | R1 495 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Installation of automatic data logging system in all bulk meters and telemetry system at the WWTW & WTW inlet and outlet meters. |  | To enhance water balance calculations and improve on curbing water losses by 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Installed on-site data loggers and telemetric system in the WWTW & WTW meters. |  | 30 June 2013 |  | Accurate water stock determination |  |  | None |  | 10 WWTW & WTW |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 5 | 5 |
| Close-out report by the Service provider |  | 30 June 2013 |  | Auditor General’s report |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of reference submitted to SCM. | 01 September 2012 |  | 15 September 2012 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |
| Service provider appointed | 01 October 2012 |  | 31 October 2012 |  | R10 000.00 | 0 |  | 0 |  |  | 0 |  |  |
| Installation of automatic data logger system and telemetry in the WWTW & WTW inlet and outlet meters. | 01 November 2012 |  | 30 June 2013 |  | 0 | 0 |  | R245 000.00 |  |  | R245 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Water Inventory |  | To enhance water balance calculations in the ANDM water supply schemes by 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of water schemes audited (water stock counting). |  | 30 June 2013 |  | Enhanced water stock determination |  |  | None |  | 10 water supply schemes |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 5 |  | 5 | 0 |
| Quarterly Reports |  | 30 June 2013 |  | Auditor General’s report |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of reference submitted to SCM. | 01 September 2012 |  | 15 September 2012 |  | 0 | 0 |  | 0 |  |  | 0 |  |  |
| Service provider appointed | 01 October 2012 |  | 31 October 2012 |  | R10 000.00 | 0 |  | 0 |  |  | 0 |  |  |
| Inventory undertaken in the ANDM water supply scheme. | 01 November 2012 |  | 30 June 2013 |  | 0 | 0 |  | R490 000.00 |  |  | 0 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Water Conservation and Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Water Resource Monitoring |  | To install water monitoring devices in all ANDM water supply sources by 2013 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of water sources and storage tanks installed with water level monitoring devices. |  | 30 June 2013 |  | Enhanced water stock determination |  | None |  | 100 water sources with monitoring devices. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 0 |  | 50 | 50 |
| Progress and Quarterly Reports |  | 30 June 2013 |  | Auditor General’s report |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2 000 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of reference submitted to SCM. | 01 September 2012 |  | 15 September 2012 | 0 | 0 |  | 0 |  |  | 0 |  |  |
| Procurement of Service provider. | 01 October 2012 |  | 31 October 2012 | R10 000.00 | 0 |  | 0 |  |  | 0 |  |  |
| Installation of monitoring devices in the ANDM town water supply source. | 01 November 2012 |  | 30 June 2013 | 0 | 0 |  | R995 000.00 |  |  | R995 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Water Conservation & Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: Water Conservation Water Demand Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Review of the WCDM strategy document | To review the existing WCDM strategy document to include Ntabankulu & Bizana LMs by 2013 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Approved Water Conversation and Demand Management Strategy. | 29 March 2013 |  | Increased area of WCDM application in the ANDM. |  | Existing WCDM strategy document. |  |  | One WCDM |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 0 | 1 | 0 |
| Council resolution of the adopted WCDM strategy document. | 29 March 2013 |  | Water Schemes for Mbizana and Ntabankulu incorporated in the Strategy |  | 29 March 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Terms of reference submitted to SCM. | 01 September 2012 | 15 September 2012 |  | 0 |  | 0 | 0 |  |  | 0 |  |
| Procurement of the Service provider. | 01 October 2012 | 31 October 2012 |  | R10 000.00 |  | 0 | 0 |  |  | 0 |  |
| Review WCDM strategy document in the ANDM. | 01 November 2012 | 29 March 2013 |  | 0 |  | 0 | R490 000.00 |  |  | 0 |  |
| Adopted WCDM strategy document for the ANDM. | 15 June 2013 | 30 June 2013 |  | 0 |  | 0 | 0 |  |  | 0 |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | To assess the existing ability of the municipality |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Section 78 (1) |  | To assess the existing ability of the municipality To assess the needs and abilities within the municipality To decide on the optimal service delivery mechanisms |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Approved S78(1) |  | 30 March 2013 |  |  | Projects as per S78 (1) incorporated in the IDP and budgeted for. |  | Nil |  | S78 (1) completed as per Advertised Specification |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Council Resolution |  | 20 June 2013 |  |  | Draft IDP 2013/14 |  | 20 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Development of Plan | 02/07/2012 |  | 23/08/2012 | R600,000.00 |  | Nil |  | Nil |  |  | Nil |  |  |
| Continuation of process Plan | 26/08/2012 |  | 30/08/2012 | R800,000.00 |  | Nil |  | Nil |  |  | Nil |  |  |
| Assessment of the Process Plan | 03/09/2012 |  | 30/10/2012 | Nil |  | R600,000.00 |  | Nil |  |  | Nil |  |  |
| Adoption of the Draft Plan | 01/11/2012 |  | 30/11/2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Final Plan Adoption | 04/12/2012 |  | 15/12/2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of water to Matatiele Communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| RBIG implementation : Matatiele |  | To provide water to Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Project Existence |  | 30 March 2013 |  | Projects as incorporated in the IDP and budgeted for. |  |  | RBIG (2012) |  | Project Completed as per project specification |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Completion Certificate |  | 30 June 2013 |  | Draft IDP 2013/14 |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R25,000,000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop Terms of Reference | 1/07/2012 |  | 1/09/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Procurement Processes | 01 /11/2012 |  | 01/01/2013 |  | Nil | R10,000.00 |  | Nil |  |  | Nil |  |  |
| Project Implementation | 08/01/2013 |  | 30/03/2013 |  | Nil | Nil |  | R20,990.000.00 |  |  | Nil |  |  |
| Completion Certificate | 10/04/2013 |  | 29/06/2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of water to Mount Ayliff Communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| RBIG implementation : Mount Ayliff |  | To provide water to Mount Ayliff and Peri-Urban area |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Project Existence |  | 30 March 2013 |  |  | Projects as incorporated in the IDP and budgeted for. |  | 4353 |  | Complete construction of Wiers and raw water gravity line |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Monthly Progress reports Completion Certificates |  | 20 June 2013 |  |  | Draft IDP 2013/14 |  | 20 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R59,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Construction | Feb 2012 |  | Mar 2012 |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Provision of Water for the Mbizana Communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| RBIG implementation : Mbizana |  | To provide water to Mbizana |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Project Existence |  | 30 March 2013 |  |  | Projects as incorporated in the IDP and budgeted for. |  |  |  | Project Completed as per project specification |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Completion Certificate |  | 20 June 2013 |  |  | Draft IDP 2013/14 |  | 20 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R50,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop Terms of Reference | 1/07/2012 |  | 1/09/2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Procurement Processes | 01 /11/2012 |  | 01/01/2013 | Nil |  | R10,000.00 |  | Nil |  |  | Nil |  |  |
| Project Implementation | 08/01/2013 |  | 30/03/2013 | Nil |  | Nil |  | R50,990,000.00 |  |  |  |  |  |
| Completion Certificate | 10/04/2013 |  | 29/06/2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | To Provide Bulk Storage Infrastructure |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Water Services Authority Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| RBIG dam feasibility studies for Kinira, Sirhoqobeni, Mkhemane & Ntabankulu bulk. |  | To construct 3 Regional Bulk storage by 2017 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Project Existence |  | 30 march 2013 |  |  | Projects as incorporated in the IDP and budgeted for. |  | Nil |  | Project Completed as per project specification |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1 |
| Completion Certificate |  | 20 June 2013 |  |  | Draft IDP 2013/14 |  | 20 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R59m |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop Terms of Reference | 1/07/2012 |  | 1/09/2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Procurement Processes | 01 /11/2012 |  | 01/01/2013 |  |  | R10,000.00 |  | Nil |  |  | Nil |  |  |
| Project Implementation | 08/01/2013 |  | 30/03/2013 | Nil |  | Nil |  | R15,990.000.00 |  |  | Nil |  |  |
| Completion Certificate | 10/04/2013 |  | 29/06/2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |

  - PROJECT MANAGEMENT UNIT

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Caba-Mdeni Water Supply |  | To provide 2305 households with basic water services by Septermber 2012 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Phase 1 & phase 2 both completed. |  | 30 September 2012 |  |  | Number of Households served with water |  | 2305 Households |  | 2305 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 2305 |  |  |  |  |
| Practical completion report |  | 30 September 2012 |  |  | Practical completion certificate for both contracts |  | 30 September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R600 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  | August 2012 | 600 000.00 |  | 0 |  | 0 |  |  | 0 |  |  |
| Project Handover |  |  | September 2012 |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Cabazana Water Supply |  | To provide 3756 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Advertise tender for construction, award tender & commence construction. |  | 30 July 2012 |  |  | Number of Households served with water |  | 3756 Households |  | 751 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 751 |
| Contractor appointed, contract signed and construction commenced. |  | 31 August 2012 |  |  | Contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R11 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONE2305S/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | May 2012 |  | July 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | September 2012 |  | June 2013 | 500 000.00 |  | 5 000 000.00 |  | 5 000 000.00 |  |  | 4 500 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Cabazi Water Supply |  | To provide 980 households in Cabazi with basic water services by June 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of Households served with basic water services |  | 30 July 2012 |  |  | Number of Households served with water |  | 980 Households |  | 490 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 490 |
| Contractor appointed, contract signed and construction commenced. |  | 31 August 2012 |  |  | Contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R11 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | June 2012 |  | July 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | September 2012 |  | June 2013 | 500 000.00 |  | 3 000 000.00 |  | 5 000 000.00 |  |  | 3 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Fobane Water Supply (A,B,C,E,F,G) & Phase 2 |  | To provide 2305 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction (for current phase 1 A to G). Advertise tender for construction for phase 2, award tender & commence construction. |  | 30 July 2012 30 June 2012 |  |  | Number of Households served with water |  | 2305 Households |  | 576 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 576 |
| Complete construction for current work Contractor appointed, contract signed and construction commenced. |  | 30 November 2012 30 August 2012 |  |  | Contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R15 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | May 2012 |  | July 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 3 000 000.00 |  | 5 000 000.00 |  | 5 000 000.00 |  |  | 2 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Greater Mbizana Water Supply - Reticulation |  | To provide 13 405 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Register project on MIG MIS by August 2012, finalise designs, advertise & award tender and commence construction by December 2012 |  | 31 December 2012 |  |  | Number of Households served with water |  | 13405 Households |  | 2681 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 670 |
| Project registered, designs approved, contractor appointed, contract signed and construction commenced. |  | 31 December 2012 |  |  | Design documentation, contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R6 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | April 2012 |  | August 2012 |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | September 2012 |  | December 2012 | 500 000.00 |  | 500 000.00 |  |  |  |  |  |  |  |
| Construction | January 2012 |  | March 2013 | 500 000.00 |  | 500 000.00 |  |  |  |  |  |  |  |
| Project Handover | April 2013 |  | June 2013 |  |  |  |  | 2 500 000.00 |  |  | 1 500 000.00 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Hlane Water Supply |  | To provide 2337 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Advertise tender for the bulk pipeline (phase3) from Qumrha borehole, award tender & commence construction. |  | 30 June 2012 |  |  | Number of Households served with water |  | 2337 Households |  | 2337 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 2337 |
| Contractor appointed, contract signed and construction commenced. |  | 30 August 2012 |  |  | Contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R12 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | June 2012 |  | August 2012 | 500 000.00 |  |  |  |  |  |  |  |  |  |
| Construction | September 2012 |  | June 2013 | 500 000.00 |  | 2 5 00 000.00 |  | 5 000 000.00 |  |  | 4 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| KwaBhaca Bulk Water Supply |  | To provide 16 667 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue with construction (upon court decision Award contract for the housing contract) |  | 30 July 2012 |  |  | Number of Households served with water |  | 16 667Households |  | 980 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 980 |
| Contract signed, construction commenced pending outcome of court case. |  | 30 July 2012 |  |  | Contract document and progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R26 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | July 2012 |  | September 2012 | 2 500 000.00 |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 6 000 000.00 |  | 6 000 000.00 |  | 5 000 000.00 |  |  | 6 500 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Maluti/Matatiele/Ramohlakoana Water Supply |  | To augment water supply to the Maluti/ Ramohlakoana area with a total household population of 2810 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Finalize designs, advertise tender for construction, award tender & commence construction. |  | August 2012 |  |  | Number of Households served with water |  | 2810 Households |  | 2810 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 702 |
| Contractor appointed, contract signed and construction commenced. |  | November 2012 |  |  | Design documentation, contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R8 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | June 2012 |  | August 2012 | 500 000.00 |  | 500 000.00 |  |  |  |  |  |  |  |
| Tendering Process | September 2012 |  | November 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | February 2013 |  | June 2013 |  |  | 800 000.00 |  | 4 000 000.00 |  |  | 2 200 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mvenyane Water Supply |  | To provide 2305 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Project fully complete by December 2012 |  | 30 December 2012 |  |  | Number of Households served with water |  | 2305 Households |  | 2305 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 2305 |  | 0 | 0 |
| Continue construction under phase 1 part 1, terminate contract for phase 3 part 2. |  | 30 December 2012 |  |  | Practical completion (ZanaManzi), Termination letter (Corpclo) and appointment new Contractor |  | 30 December 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | June 2012 |  | December 2012 | 1 200 000.00 |  | 1 300 000.00 |  | 0 |  |  | 0 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Bomvini Nyokweni Bulk Water Supply |  | To provide 5126 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Finalize Design by June 2012. Advertise tender for source development award tender & commence construction by September 2012. |  | September 2012 |  |  | Number of Households served with water |  | 5126 Households |  | 2500 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 2500 |
| Contractor appointed, contract signed and construction commenced. |  | October 2012 |  |  | Contract document, site handover minutes & progress reports |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R10 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | April 2012 |  | September 2012 |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | April 2012 |  | September 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | October 2012 |  | June 2013 | 1 800 000.00 |  | 2 200 000.00 |  | 3 000 000.00 |  |  | 3 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntibane Water Supply |  | To provide 2925 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Complete construction Manqilweni and Ntibane village scheme. Finalise designs, advertise tender for construction, award tender & commence construction. |  | 30 June 2012 31 August 2012 |  |  | Number of Households served with water |  | 2925 Households |  | 731 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 731 |
| Practical completion certificates Tender adverts and appointment letters. |  | 30 June 2012 31 October 2012 |  |  | Practical completion certificates, tender adverts and appointment letters |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R9 700 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | March 2012 |  | June 2012 | 1 200 000.00 |  |  |  |  |  |  |  |  |  |
| Tendering Process | June 2012 |  | September 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | October 2012 |  | June 2013 |  |  | 2 500 000.00 |  | 3 500 000.00 |  |  | 2 500 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Qwidlana Water Supply |  | To provide 1198 households with basic water services by 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Completion of current construction. Advertise tender for new construction within area 1&2, award tender & commence construction. |  | 30 September 2012 31 August 2012 |  |  | Number of Households served with water |  | 1198 Households |  | 1198 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1198 | 0 |  | 0 | 0 |
| Area 1 and 2(Bulk) completed Adverts, appointment letters and contracts signed |  | 31 August 2012 |  |  | Practical completion certificates for current construction and Contract document, site handover minutes & progress reports |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R12 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | February 2012 |  | June 2013 | 3 000 000.00 |  | 3 000 000.00 |  | 3 000 000.00 |  |  | 3 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Siqhingeni Water Supply |  | To provide 2529 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Finalise designs, advertise tender for construction, award tender & commence construction. |  | 30 September 2012 |  |  | Number of Households served with water |  | 2529 Households |  | 632 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 632 |
| Contractor appointed, contract signed and construction commenced. |  | 30 October 2012 |  |  | Contract document, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R5 800 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | April 2012 |  | May 2012 | 500 000.00 |  |  |  |  |  |  |  |  |  |
| Tendering Process | June 2012 |  | October 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | November 2012 |  | June 2013 |  |  | 1 500 000.00 |  | 2 000 000.00 |  |  | 1 800 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Tholamela Water Supply |  | To provide 4112 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue and complete construction of the current contract. Advertise tender for construction for next stage, award tender & commence construction. |  | 31 November 2012 30 September 2012 |  |  | Number of Households served with water |  | 4112 Households |  | 1028 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 751 |
| Continue construction (depending on the outcome of S24G application). Practical Completion reached Tender adverts and appointment letter |  | 30 August 2012 |  |  | Approval for S24G, Practical completion certificate. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R11 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | June 2012 |  | August 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | September 2012 |  | June 2013 | 2 500 000.00 |  | 3 000 000.00 |  | 3 000 000.00 |  |  | 3 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WORK IN THIS PROJECT DEPENDS ON THE OUTCOME (APPROVAL) OF THE SECTION 24 G APPLICATION TO DEDEA |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Tholang Water Supply |  | To provide 615 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Implement project in-house |  | July 2012 |  |  | Number of Households served with water |  | 615 Households |  | 615 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 615 | 0 |  | 0 | 0 |
| Awaiting verification of outstanding work from consultants |  | July 2012 |  |  | Contract document, site handover minutes & progress reports |  | September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 518 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  | . |  |  |  |  |  |  |  |
| Construction | June 2012 |  | September 2012 | 518 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Waterborne Sewer Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Cederville Sewer Upgrade |  | To provide 1208 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Complete construction by July 2012 |  | 30 July 2012 |  |  | Number of Households served with sanitation |  | 1208 Households |  | 1208 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1208 | 0 |  | 0 | 0 |
| Project finally completed |  | 30 July 2012 |  |  | Practical Completion Certificate |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 400 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  | July 2012 | 1 400 000.00 |  | 8 670 193.75 |  | 8 670 193.75 |  |  | 8 670 193.75 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Waterborne Sewer Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Maluti Ramohlakoana Sewer |  | To provide 1220 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Complete construction of current phase by September 2012. Extend appointment of consultant to accommodate the Ramohlakoana village Advertise tender, award and commence construction of Ramohlakoana village sewer. |  | 30 September 2012 |  |  | Number of Households served with sanitation |  | 1220 Households |  | 1220 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1220 |
| Practical Completion Certificate for current phase. Appointment letter for Ramohlakaoana village sewer |  | 30 September 2012 |  |  | Practical Completion Certificate for current phase. Appointment letter for Ramohlakaoana village sewer |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 800 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | July 2012 |  | September 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 1 000 000.00 |  | 800 000.00 |  | 0 |  |  | 0 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water & Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mt. Ayliff Peri-Urban Water & Sanitation project |  | To provide 500 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Complete designs, advertise tender, award and commence construction. |  | 30 July 2012 |  |  | Number of Households served with water |  | 500 Households |  | 500 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | 0 |  | 0 | 500 |
| Design reports, adverts and appointment letter |  | 30 September 2012 |  |  | Design reports, adverts and appointment letter |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | July 2012 |  | December 2012 |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | February 2012 |  | June 2013 | 800 00.00 |  | 1 200 000.00 |  | 500 000.00 |  |  | 0.00 |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water & Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mt. Frere Peri-Urban Water & Sanitation project |  | To provide 4553 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Commence with feasibility study and designs up to June 2013 |  | 1 July 2012 |  |  | Number of Households served with water |  | 4553 Households |  | 4553 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Feasibility study report and design reports. |  | 30 June 2013 |  |  | Feasibility study report and design reports. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility study | July 2012 |  | June 2013 | 250 000.00 |  | - 0.00 |  |  |  |  |  |  |  |
| Project design |  |  |  |  |  | 200 000.00 |  | 600 000.00 |  |  | - 0.00 |  |  |
| Tendering / SCM Processes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commissioning & Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Waterborne Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of Ntabankulu Town Sewer |  | To provide 759 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of the sewer project and advertise tender for WWTW. |  | 30 July 2012 |  |  | Number of Households served with water |  | 759 Households |  | 759 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 759 |
| Complete current phase of constructions. |  | 30 June 2013 |  |  | Completion certificates & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R18 501 288.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering / SCM Processes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | May 2012 |  | June 2013 | 4 625 322.00 |  | 4 625 322.00 |  | 4 625 322.00 |  |  | 4 625 322.00 |  |  |
| Commissioning & Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Waterborne Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of Mbizana Town Sewer |  | To provide 1036 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Appoint service provider to prepare business plan/technical report and register project on MIG MIS |  | 30 June 2012 |  |  | Number of Households served with water |  | 1026 households |  | 1036 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Appointed service provider to commence with technical report |  | 30 August 2012 |  |  | Appointment letter and approved technical report |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility study /technical report | July 2012 |  | June 2013 | 250 000.00 |  | 500 000.00 |  | 500 000.00 |  |  | - 0.00 |  |  |
| Project design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering / SCM Processes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commissioning & Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Alfred Nzo District Sanitation (Matatiele LM Area) |  | To provide 3600 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs with existing service providers (contract expires in October 2012). Advertise tender for new service providers to commence construction by November 2012. |  | 30 July 2012 |  |  | Number of Households served with water |  | 3600 Households |  | 3600 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 900 | 900 |  | 900 | 900 |
| Completed VIP toilets. Tender adverts for new service providers |  | 30 June 2013 31 July 2012 |  |  | Happy letters & Progress report New contract document for new PSPs, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R34 680 775.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/ Technical reports |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 8 670 194.00 |  | 8 670 194.00 |  | 8 670 194.00 |  |  | 8 670 194.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Alfred Nzo District Sanitation (Umzimvubu LM Area) |  | To provide 4800 households with basic water services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs with existing service providers (contract expires in October 2012). Advertise tender for new service providers to commence construction by November 2012. |  | 30 July 2012 |  |  | Number of Households served with water |  | 4800 Households |  | 4800 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1200 | 1200 |  | 1200 | 1200 |
| Completed VIP toilets. Tender adverts for new service providers |  | 30 June 2013 31 July 2012 |  |  | Happy letters & Progress report New contract document for new PSPs, site handover minutes & progress reports |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R32 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 8 000 000.00 |  | 8 000 000.00 |  | 8 000 000.00 |  |  | 8 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu LM Area Sanitation Project |  | To provide 1060 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Advertise and appoint Service Providers for business plan preparation for un-served areas. |  | 30 September 2012 |  |  | Number of Households served with water |  | 1060 Households |  | 1060 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 265 | 265 |  | 265 | 265 |
| Approved business plan and loaded on MIG MIS, advertise tender for construction, award & commence construction. |  | 31 December 2012 |  |  | Approved business plan, contractor appointment letter |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R8 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 |  |  |  |  | 4 000 000.00 |  |  | 4 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana LM Area Sanitation project |  | To provide 2600 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Advertise and appoint Service Providers for business plan preparation for un-served areas. |  | 30 September 2012 |  |  | Number of Households served with water |  | 2600 Households |  | 2600 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 650 | 650 |  | 650 | 650 |
| Approved business plan and loaded on MIG MIS, advertise tender for construction, award & commence construction. |  | 31 December 2012 |  |  | Approved business plan, contractor appointment letter |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R20 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 |  |  |  |  | 10 000 000.00 |  |  | 10 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana Ward 4 VIP sanitation project |  | To provide 993 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs for existing contracts. |  | 1 July 2012 |  |  | Number of Households served with VIP toilets |  | 993 Households |  | 993 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 993 | 0 |  | 0 | 0 |
| Completed 993 VIP toilets |  | 30 July 2012 |  |  | Happy letters, completion certificates |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R540 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Processes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | November 2011 |  | June 2012 | 540 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana Ward 12 Sanitation project |  | To provide 923 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs for existing contracts. |  | 1 July 2012 |  |  | Number of Households served with VIP toilets |  | 923 Households |  | 923 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 923 | 0 |  | 0 | 0 |
| Completion of 923 VIP toilets |  | 30 July 2012 |  |  | Happy letters, completion certificates |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R400 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | November 2011 |  | July 2012 | 400 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana Ward 14 Sanitation Project |  | To provide 1237 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs for existing contracts. |  | 1 July 2012 |  |  | Number of Households served with VIP toilets |  | 1237 Households |  | 1237 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1237 |  |  |  |  |
| Completion of 1237 VIP toilets |  | 30 July 2012 |  |  | Happy letters, completion certificates |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R960 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | July 2012 | 960 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana Ward 18 VIP toilets |  | To provide 2061 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs for existing contracts. |  | 1 July 2012 |  |  | Number of Households served with VIP toilets |  | 2061 Households |  | 2061 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 2061 | 2061 |  | 2061 | 2061 |
| Completion of 2061 VIP toilets |  | 30 July 2012 |  |  | Happy letters, completion certificates |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R150 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | November 2011 |  | July 2012 | 150 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mbizana Ward 21 VIP toilets |  | To provide 766 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction of VIPs for existing contracts. |  | 1 July 2012 |  |  | Number of Households served with VIP toilets |  | 766 Households |  | 766 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 766 |  |  |  |  |
| Completion of 766 VIP toilets |  | 30 July 2012 |  |  | Happy letters, completion certificates |  | 30 July 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R700 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | November 2011 |  | July 2012 | 700 000.00 |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 1 VIP toilets |  | To provide 3374 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Award tender and commence construction |  | August 2012 |  |  | Number of Households served with VIP toilets |  | 3374 Households |  | 1800 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 450 | 450 |
| Completion of 1800 VIP toilets |  | 30 June 2013 |  |  | Happy letters, completion certificates |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R4 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | May 2012 |  | July 2012 | 0 |  | 0 |  | 0 |  |  | 0 |  |  |
| Construction | August 2012 |  | June 2013 | 1 000 000.00 |  | 1 500 000.00 |  | 15000 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 3 VIP toilets |  | To provide 736 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 736 Households |  | 736 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 400 | 336 |  | 0 | 0 |
| Completion of 736 VIP toilets by November 2012 |  | November 2012 |  |  | Happy letters, completion certificates |  | 30 November 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 357 200.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | November 2012 | 1 800 000.00 |  | 1 557 200.00 |  | 0 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 4 VIP toilets |  | To provide 1059 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue Construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 1059 Households |  | 1059 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 159 |  |
| Completion of 1059 VIP toilets |  | January 2013 |  |  | Happy letters, completion certificates |  | January 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R5 840 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | January 2013 | 2 500 000.00 |  | 2 500 000.00 |  | 840 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 5 VIP toilets |  | To provide 1171 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue Construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 1171 Households |  | 1171 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 271 |  |
| Completion of 1059 VIP toilets |  | February 2013 |  |  | Happy letters, completion certificates |  | February 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R6 700 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | February 2013 | 2 500 000.00 |  | 2 500 000.00 |  | 1 700 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 8 VIP toilets |  | To provide 3374 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Award tender and commence construction |  | August 2012 |  |  | Number of Households served with VIP toilets |  | 3374 Households |  | 1800 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 450 | 450 |
| Completion of 1800 VIP toilets |  | June 2013 |  |  | Happy letters, completion certificates |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R6 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | May 2012 |  | August 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | February 2013 | 1 000 000.00 |  | 2 000 000.00 |  | 2 000 000.00 |  |  | - 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 9 VIP toilets |  | To provide 782 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Award tender and commence construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 782 Households |  | 782 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 282 |  |
| Completion of 4711 VIP toilets |  | January 2013 |  |  | Happy letters, completion certificates |  | January 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 700 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | January 2013 | 1 500 000.00 |  | 1 500 000.00 |  | 700 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 12 VIP toilets |  | To provide 1026 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Award tender and commence construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 1026 Households |  | 1026 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 126 |  |
| Completion of 1026 VIP toilets |  | February 2013 |  |  | Happy letters, completion certificates |  | February 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R5 600 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | February 2013 | 2 500 000.00 |  | 2 500 000.00 |  | 1 600 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 14 VIP toilets |  | To provide 2212 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 2212 Households |  | 2212 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1800 | 412 |  |  |  |
| Completion of 2212 VIP toilets |  | November 2012 |  |  | Happy letters, completion certificates |  | November 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R14 700 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | November 2012 | 10 000 000.00 |  | 4 700 000.00 |  | 0.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 15 VIP toilets |  | To provide 1268 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Commence construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 1268 Households |  | 1268 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 450 | 450 |  | 368 |  |
| Completion of 1268 VIP toilets |  | March 2013 |  |  | Happy letters, completion certificates |  | March 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R7 450 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | March 2013 | 3 000 000.00 |  | 3 000 000.00 |  | 1 450 000.00 |  |  | 0.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Sanitation Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu Ward 18 VIP toilets |  | To provide 1472 households with basic sanitation services |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue construction |  | July 2012 |  |  | Number of Households served with VIP toilets |  | 1472 Households |  | 1472 households to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1350 | 122 |  | 0 | 0 |
| Completion of 1472 VIP toilets |  | November 2012 |  |  | Happy letters, completion certificates |  | November 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R9 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | November 2012 | 4 500 000.00 |  | 4 500 000.00 |  | 0 |  |  | 0 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Umzimvubu Ward 6 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 6 in Umzimvubu |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Umzimvubu Ward 13 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 13 in Umzimvubu |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 1 500 000.00 |  | 0 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Umzimvubu Ward 14 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 14 in Umzimvubu |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 1 000 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Umzimvubu Ward 22 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 22 in Umzimvubu |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 5000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Umzimvubu Ward 24 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 24 in Umzimvubu |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 5000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Ward 5 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 5 in Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 5000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Ward 7 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 7 in Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 5000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Ward 15 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 15 in Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 5000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 0 |  |  | 0 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Ward 16 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 16 in Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Conduct feasibility |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | July 2012 |  | June 2013 | 500 000.00 |  | 1 000 000.00 |  | 1 000 000.00 |  |  | - .00 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Ward 17 &18 Water Feasibility Study |  | Conduct feasibility study for the supply of water to ward 17 & 18 (Fobane Phase 2) in Matatiele |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Complete feasibility study, technical report, design and tendering. |  | July 2012 |  |  | Planned number of Households to be served with water |  | Study currently under development. |  | No households yet, feasibility should address this. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 0 |
| Completion of feasibility study report |  | June 2013 |  |  | Feasibility study report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R7 500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Feasibility Study/Technical Report | April 2012 |  | June 2012 |  |  |  |  |  |  |  |  |  |  |
| Project Design | July 2013 |  | August 2012 | - 0.00 |  |  |  |  |  |  |  |  |  |
| Tendering Process | September 2012 |  | November 2012 |  |  |  |  |  |  |  |  |  |  |
| Construction | January 2012 |  | June 2013 |  |  |  |  | 3 000 000.00 |  |  | - 000 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Bulk Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele Bulk Water Supply Project (RBIG) |  | Provision of Bulk Water Services to 1343 households Matatiele town |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Finalise designs, advertise tender, award and commence construction |  | July 2012 |  |  | Number of households served with water |  | 1343 Households |  | 1343 households served with water |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 1343 |
| Design report & drawings, tender advert and appointment letter |  | June 2013 |  |  | Design report and appointment letter |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 8 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design | April 2012 |  | June 2012 |  |  |  |  |  |  |  |  |  |  |
| Tendering Process | July 2012 |  | September 2012 | - 0.00 |  |  |  |  |  |  |  |  |  |
| Construction | November 2012 |  | June 2013 |  |  | 4 500 000.00 |  | 3 000 000.00 |  |  | 0 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Bulk Water Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mt. Ayliff Bulk Water Supply Project (RBIG) |  | Provision of Bulk Water Services to 588 households Mt. Ayliff |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Continue with construction. |  | July 2012 |  |  | Number of households served with water |  | 588 Households |  | 588 households served with water |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 588 |
| Finally completed project, project reached practical completion |  | June 2013 |  |  | Practical completion certificates and progress report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 42 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction | July 2012 |  | June 2013 | 19 000 000.00 |  | 10 500 000.00 |  | 10 200 000.00 |  |  | 10 300 000.00 |  |  |
| Project Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Ntabankulu WTW refurbishment and augmentation |  | Develop, cost & implement the refurbishment and augmentation of Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| To ensure improved WTW operation, to ensure water quality that meets standards, to provide accommodation for process controllers |  | June 2013 |  |  |  | Efficient operations of the WTW, management Completed project |  | 1 WTW to benefit from the refurbishment and augmentation (Ntabankulu town and Mbangweni village |  | 1 WTW to be refurbished and augmented. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | 1111 | 111 |  |  |  |
| Monthly reports, Completion certificates and financial reports. |  | 01 July 2012 |  |  |  | Monthly reports, Completion certificates and financial reports. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 2,000,000.00 |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment and augmentation of WTW infrastructure | 01 July 2012 |  | 31 December 2012 |  | R 1,000,000.00 |  | R 1,000,000.00 |  |  |  |  |  |  |  |
| Construct two sludge ponds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A collector chamber will be constructed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adequate office space for administrative and operational functions A 90mm Class 12 uPVC pipe will be laid from the sump to the head of works The existing perimeter fencing is to be extended to enclose the proposed sludge ponds. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Matatiele WTW refurbishment and augmentation |  | Develop, cost & implement the refurbishment and augmentation of Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| To ensure improved water services asset management; To ensure updated refurbishment and replacement plan and asset register; Appointment of service providers |  | 30 June 2013 |  |  |  | --Efficient operations of the WTW, management -Completed project implementation of the refurbishment plan |  | 1 WTW to benefit from the refurbishment and augmentation (Matatiele town, Harry Gwala and Itsokolele) |  | 1 WTW refurbishment and augmentation to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | 1 | 1 |  | 1 | 1 |
| Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints |  | 01 July 2012 |  |  |  | Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Vehicle logbooks -Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 7,000,000.00 |  |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 30 June 2013 |  | R 1,750,000.00 |  | R 1,750,000.00 |  | R 1,750,000.00 |  |  | R 1,750,000.00 |  |  |
| Testing and equipping of existing boreholes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction of new bulk line between Harry Gwala tank |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of WTW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Dam and Lake assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Water & Sewer pipeline model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Maluti Regional refurbishment and Pipe replacement |  | Develop, cost & implement the refurbishment of Maluti regional scheme and pipe replacement. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - To ensure improved WTW operation -To ensure water quality that meets standards -To provide accommodation for process controllers. -To ensure that dilapidated infrastructure is replaced. |  | 30 June 2013 |  |  | -Efficient operations of the WTW, management -Completed project |  | 16 number of villages to benefit from the refurbishment (Belfort, Mafube, La Grange, Matewu, De Schuur,Lokshin, Nchodu,Jabavu, Mtsekuwa, Malubalube, Maluti township,Thulang,Skiti, Ramohloakoana and Malubelube |  | 16 villages to benefit from the WS |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 4 | 4 |  | 4 | 4 |
| Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  |  |  |  | Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 9,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 30 June 2013 | R 2,250,000.00 |  | R 2,250,000.00 |  | R 2,250,000.00 |  |  | R 2,250,000.00 |  |  |
| Replacement of bulk line from Dam to WTW |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Replacement of bulk feed line from WTW to Maluti town |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of Belfort WTW |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Isolation of bulk main to Military base and equipping of borehole. |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Kwa-Bhaca Southern leg refurbishment and augmentation |  |  | Develop, cost & implement the refurbishment and augmentation of Kwa –Bhaca Southern leg. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - To identify additional water source; -To ensure access provision of potable water services; -Appointment of service providers; |  |  | 30 June 2013 |  |  |  | -Availability of water to 11 villages -refurbishment, replacement and provision of water as per SANS 241 standards; -Appointment letters |  | 9 Villages to benefit from the refurbishment (Mhlanganisweni, Essck Farm, Toleni A, Dangwana A & C, Tina Hill 1 & 2, Ngxabaxha, Majuba, Mawusheni, Lucingweni) |  |  | 9 Villages to benefit from the WS |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  | 3 | 3 |
| Monthly report -Standing committee -Completion certificates -Expenditure reports -Vehicle logbooks -Refurbishment Contract -Refurbishment Plan |  |  | 01 July 2012 |  |  |  | Progress report -Standing committee approval -As-built drawings -Project progress |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | R 7,000,000.00 |  |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  |  | START DATE |  |  | END DATE |  | QUARTER 1 | QUARTER 2 |  |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure |  | 01 July 2012 |  |  | 30 June 2013 |  | R 1,750,000.00 | R 1,750,000.00 |  |  | R 1,750,000.00 |  |  | R 1,750,000.00 |  |  |
| Verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mt Ayliff WTW augmentation and refurbishment of infrastructure |  |  | Develop, cost & implement the refurbishment and augmentation of Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure improved water supply to high line areas; -To ensure refurbishment of sand filters, extension of the settling tank; To ensure the provision of a reservoir for the supply high line areas and pump station and pumping main -Turn Key project implementation |  |  | 01 June 2013 |  |  | -Uninterrupted water supply to highline areas -To accommodate Peri urban sanitation project -Produce good quality water with increased yields -Availability of adequate level storage -Completed project in a short period of time |  |  |  | 1 WTW to benefit from the refurbishment and augmentation (Mt Ayliff town, Santombe village and 1 Peri urban village) |  | 1 WTW refurbishment and augmentation to be served |  |  |  |  |
| 1 WTW to benefit from the refurbishment and augmentation (Matatiele town, Harry Gwala and Itsokolele) |  |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 |  | 1 | 1 |
| Monthly report -Standing committee -Monthly technical meetings -Completion certificates -Expenditure reports -Term Tenders -Refurbishment Plan -Customer Complaints |  |  | 01 July 2012 |  |  | -Progress report -Standing committee approval -Monitoring tool report -Monthly technical meetings minutes -Site attendance -Reduced no of Customer Complaints |  |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | R 7,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  |  | END DATE |  |  | QUARTER 1 | QUARTER 2 |  |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  |  | 30 June 2013 |  |  | R 1,750,000.00 | R 1,750,000.00 |  |  | R 1,750,000.00 |  |  | R 1,750,000.00 |  |  |
| Tendering Process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project handover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of WTWs |  | Develop, cost & implement the refurbishment of Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - To ensure improved WTW operation -To ensure water quality that meets standards -To provide accommodation for process controllers. -To ensure that dilapidated infrastructure is replaced |  | 30 June 2013 |  |  | --Efficient operations of the WTW, management -Completed project |  | 7 WTW to benefit from the refurbishment |  | 7 WTW Refurbishment to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 7 | 7 |  | 7 | 7 |
| Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 01 July 2012 |  |  | Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 1,000,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of WTW | 01 July 2012 |  | 30 June 2013 | R 250,000.00 |  | R 250,000.00 |  | R 250,000.00 |  |  | R 250,000.00 |  |  |
| Replacement of filter nozzles and sand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cleaning of Sludge lagoons |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Security fencing |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | EXPANDED PUBLIC WORK PROGRAMME (EPWP) |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Expanded Public Works Programme | To ensure that projects that are being implemented within ANDM are Labour Intensive |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| To create 3077 work opportunities | June 2013 |  | Planned number of persons employed |  | 4000 work opportunities created |  | 3077 |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | 770 |  | 770 | 770 |  | 770 |
| Non-financial report | June 2013 |  | Non-financial report |  | June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R9 604 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| MIS Registration of EPWP Projects |  | July 2012 | June 2013 | R 2 250 000.00 |  | R 2 250 000.00 |  | R 2 250 000.00 |  |  | R 2 250 000.00 |  |
| MIS Reporting on ANDM Solid Waste Removal and Disposal |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on MIG Projects |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on Disaster and Fire Management Project |  | July 2012 | January 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on Ntabankulu Internal Roads Surfacing |  | July 2012 | March 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on ANDM Youth Service |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on Ntenentyana Catchment Clearing Project |  | July 2012 | November 2012 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on ANDM Home Based Care Givers |  | July 2012 | January 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on ANDM Water Services Beneficiaries |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on ANDM EPWP Interns |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on Maintenance at OR Thambo Garden of Remembrance (Nkantolo) |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |
| MIS Reporting on Mfundisweni Greening project |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | ALL INFRASTRUCTURE DEVELOPMENT AND MUNICIPAL SERVICES DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Social Facilitation |  | To promote Public participation and Community ownership of projects |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| To create a conducive working environment for IDMSD Projects. To promote public participation and create sense of ownership To promote Community involvement in all IDMSD Projects and to ensure that the Batho Pele Principles are adhered to. |  | July 2012 |  |  | The involvement of Relevant Stake Holders. Community sense of ownership Established and capacitated PSC’s. |  | All current and complete projects do have capacitated PSC’s. |  | Achievement of Outcomes |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| Non-financial report |  | June 2013 |  |  | Non-financial report |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Community Mobilization | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |  |
| Capacitated and establish PSC’s |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure Community satisfaction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure Project sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | IDMSD FINANCIAL CONTROLLING |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: Project Management Unit |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Financial Controlling |  | To Manage and report expenditure on MIG (Municipal Infrastructure Grant) |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Managing and reporting on Grant and Equitable Share funds |  | July 2012 |  | Expenditure reports on R465 million |  | Expenditure reports on R308 million |  | Proof of payments capturing R465 million expenditures |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | R149.8 | R140.7 |  | R73.7 | R100.8 |
| Proof of payments, MIS (EPWP & RBIG) and DORA reports to Province |  | June 2013 |  | Proof of payments and DORA reports from Province |  | June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R435 000 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Timeous Payments of Suppliers | July 2012 |  | June 2013 |  | R149.8 | R140.7 | R73.7 |  |  | R100.8 |  |  |
| Capturing of payments on SAMRAS | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Proper Record Keeping | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Retention Register and WIP Update | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Risk Management and Monitoring | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Reporting to COGTA and other supporting units within the Institution (ANDM) | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Budget Monitoring | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| Prepare Reconciliations and Maintenance of General Ledger | July 2012 |  | June 2013 |  |  |  |  |  |  |  |  |  |
| REFLECTED BUDGET INCLUDES FUNDING FROM EQUITTABLE SHARE, EPWP, RBIG AND MIG GRANT FUNDING |  |  |  |  |  |  |  |  |  |  |  |  |

2.3 WATER SERVICES PROVISIONING

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Maintenance of Water Schemes |  | Develop, cost & implement the operations and maintenance of all Water & sanitation schemes. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| 30 June 2013 |  | -Operations and Maintenance reports updated on time (by 5th day of next month) -Decrease in the number of complaints received on leakages, blockages and water interruptions -Turn-around time for fixing blockages, leakages and water interruptions in a scheme. |  | 182 number of water schemes 1.Mbizana (31 Water schemes) 2.Ntabankulu(29 Water schemes) 3.Matatiele(47 Water schemes) 4.Umzimvubu (75 Water schemes) |  | 182 water schemes to be maintained to provide with portable water |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Maintenance Contract -Maintenance Plan -Customer Complaints -Monthly report -Standing committee |  | 01 July 2012 |  | -Efficient management -Completed projects -Payment of invoices -Reduction of customer complaints -Response to complaints -Travel km’s -Work completed -Effective operations -Number of complaints attended too. -Monthly action plans -Standing committee resolutions |  | 30 June 2013 |  |  | 182 | 182 |  | 183 | 184 |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 10,000,000.00 |  | VOTE NUMBER |  | 1 500 38006 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Maintain existing infrastructure in good working order, implement preventative maintenance; | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |
| Mechanical and Electrical repairs and maintenance | 01 July 2012 |  | 30 June 2013 |  | R 600 000.00 |  | R 600 000.00 | R 600 000.00 |  |  | R 600 000.00 |  |  |
| Maintenance of concrete reservoirs, weirs and springs and pipelines. | 01 July 2012 |  | 30 June 2013 |  | R 700 000.00 |  | R 700 000.00 | R 700 000.00 |  |  | R 700 000.00 |  |  |
| -Unblocking and jetting of sewer systems ; maintenance of sewer main holes | 01 July 2012 |  | 30 June 2013 |  | R 700 000.00 |  | R 700 000.00 | R 700 000.00 |  |  | R 700 000.00 |  |  |
| Honey sucking | 01 July 2012 |  | 30 June 2013 |  | R 300 000.00 |  | R 300 000.00 | R 300 000.00 |  |  | R 300 000.00 |  |  |
| Maintenance of public toilets | 01 July 2012 |  | 30 June 2013 |  | R 200 000.00 |  | R 200 000.00 | R 200 000.00 |  |  | R 200 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of water and sanitation schemes |  | Develop, cost & implement the refurbishment of Water & Sanitation schemes. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure that our water and sanitation schemes are refurbished and replaced as per plan. -Appointment of service providers |  | 30 June 2013 |  |  | -Refurbishment of 120 and town of Matatiele sewer pipeline identified villages per the financial year. -Bring existing schemes to an operational standard -Replacement of bulk pipelines with major leaks. -Re -rooting of pipelines and re positioning of standpipes. |  | 120 water schemes to be refurbished. |  | 12 water schemes to benefit from refurbished water and sanitation schemes in the financial year 2012/13 |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | 4 |  | 4 | 4 |
| Monthly report -Standing committee -Completion certificates -Expenditure reports -Effective workforce -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan |  | 01 July 2012 |  |  | -Efficient management -Completed projects -Payment of invoices -Response to complaints -Travel km’s -Work completed -Effective operations -Number of complaints attended too. -Monthly action plans -Standing committee resolutions |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 10,000,000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water and Sanitation infrastructure | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |
| Mbizana = 6 Ntshamathe, Goxempheni, Rockville, | 01 July 2012 |  | 30 June 2013 | R 625,000.00 |  | R 625,000.00 |  | R 625,000.00 |  |  | R 625,000.00 |  |  |
| Ntbankulu = 10 Gxwalweni, Mcepheni, Hlankomo | 01 July 2012 |  | 30 June 2013 | R 625,000.00 |  | R 625,000.00 |  | R 625,000.00 |  |  | R 625,000.00 |  |  |
| Matatiele = 35 9 weirs, Sgoga and Mgubo springs, Itsokolele sewer pipeline | 01 July 2012 |  | 30 June 2013 | R 625,000.00 |  | R 625,000.00 |  | R 625,000.00 |  |  | R 625,000.00 |  |  |
| Umzimvubu = 69 Marwaqa, Lutshikini, Lovu | 01 July 2012 |  | 30 June 2013 | R 625,000.00 |  | R 625,000.00 |  | R 625,000.00 |  |  | R 625,000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mnceba WSS refurbishment and augmentation |  | Develop, cost & implement the refurbishment and augmentation of Mnceba regional water scheme. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure that all Jojo tanks are replaced with increased capacity; -To ensure augmentation of bulk pipelines; -Refurbishment of water infrastructure -Appointment of service providers for the supply of materials and pre-fabricated reservoirs; - Replacing pipeline with lot of bursts |  | 30 June 2013 |  |  | -Improved water supply and storage on 32 villages; -Reduced water losses; -Scheme efficiency will increase; -Appointment letter; |  | 32 villages under Mnceba W/S to benefit from the augmentation and refurbishment of the existing Mnceba WSS (Sugar bush, luxwesa, Goso, Mhlizini, Dityini, Siphundu, Mzalwaneni, Ndlantaka, Skhumbeni, Cingweni-Bhakubha, Dikathole, Saphukanduku, Manzamnyama, Tshamanzi, Noxhungushe, Tsita, Mngazana, lubala, Bagqozini, Mgqumangwe, Cedarville, Nyiweni, Lufafa, Mpendlamoya, mpemba, Skhulu, Siyaya, Cacadu, Voveni, Rode, Mnceba Ext and Nyosini |  | 32 villages under the Mnceba w/s to benefit from the augmented and refurbished of the water scheme |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 4 | 8 |  | 10 | 10 |
| Monthly report -Standing committee -Fort nightly report -Completion certificates -Expenditure reports -Job cards -Vehicle logbooks -Internal, Term Tenders -Refurbishment Plan -Customer Complaints |  | 01 July 2012 |  |  | -Progress report -Standing committee approval -Monitoring tool report -Site verification report on refurbishment and augmentation -Suppliers, Service providers and labor payments -Site attendance by technicians to refurbishment and augmentation program me -7 days’ notice for projects less that R 200,000.00 -Reduced no of Customer Complaints |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 3,000,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 30 June 2013 | R 750,000.00 |  | R 750,000.00 |  | R 750,000.00 |  |  | R 750,000.00 |  |  |
| Project Design |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commissioning & handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Drought Relief |  | Develop and cost, implementation plan of Drought relief projects |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure access to basic water supply; -To ensure adequate water supply; -To ensure that the drought response plan -Appointment of service providers; |  | 01 July 2012 |  |  | -Improved water supply; -Access to basic water supply to drought stricken areas; -Reduced no of complaints around lack of access to water supply; -Appointment letter; |  | 7 villages to benefit from the augmentation and refurbishment of the existing Mciphongweni, Nyanzela, Mdeni, Nkalweni, Marhelane, Xolobeni, Sfolweni. |  | 7 villages to benefit from the augmentation and refurbishment to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 | 2 |  | 3 | 1 |
| Monthly report -Standing committee -Fort nightly report -Completion certificates -Expenditure reports -Job cards -Vehicle logbooks -Internal, Term Tenders -Drought Relief implementation plan -Customer Complaints register |  | 01 July 2012 |  |  | -Progress report -Standing committee approval -Monitoring tool report -Site verification report on Drought relief intervention -Suppliers, Service providers and labor payments -Site attendance by technicians to the Drought Relief program me -7 days’ notice for projects less than R 200,000.00 -Reduced no of Customer Complaints |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 3,000,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 30 June 2013 | R 750,000.00 |  | R 750,000.00 |  | R 750,000.00 |  |  | R 750,000.00 |  |  |
| -Verification & scope of works |  |  |  |  |  |  |  |  |  |  |  |  |  |
| – tendering |  |  |  |  |  |  |  |  |  |  |  |  |  |
| – Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| – Project handover |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of WTWs |  | Develop, cost & implement the refurbishment of Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - To ensure improved WTW operation -To ensure water quality that meets standards -To provide accommodation for process controllers. -To ensure that dilapidated infrastructure is replaced. |  | 30 June 2013 |  |  | --Efficient operations of the WTW, management -Completed project |  | 7 WTW to benefit from the refurbishment |  | 7 WTW Refurbishment to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 7 | 7 |  | 7 | 7 |
| Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 01 July 2012 |  |  | Monthly report -Standing committee -Daily report -Completion certificates -Expenditure reports -Effective workforce -Job cards -Vehicle logbooks -Internal, Term Tenders, on Refurbishment Contract -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 1,000,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of WTW | 01 July 2012 |  | 30 June 2013 | R 250,000.00 |  | R 250,000.00 |  | R 250,000.00 |  |  | R 250,000.00 |  |  |
| Replacement of filter nozzles and sand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cleaning of Sludge lagoons |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Security fencing |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Refurbishment of WWTWs |  | Develop, cost & implement the effluent management plan and refurbishment of Waste Water Treatment work. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - To ensure improved WWTW operation -To ensure effluent quality that meets standards -To provide accommodation for process controllers. -To ensure that dilapidated infrastructure is replaced |  | 30 June 2013 |  |  | -Achieved quality effluent; -prevent raw effluent discharge; -WWTW efficiency will increase; -Appointment letter; |  | 2 x WWTW refurbishment |  | 2 x WWTW refurbishment to be served |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 2 | 2 |  | 2 | 2 |
| Monthly report -Standing committee -Daily reports -Completion certificates -Expenditure reports -Job cards -Vehicle logbooks -Internal, Term Tenders -Refurbishment Plan -Customer Complaints |  | 01 July 2012 |  |  | -Progress report -Standing committee approval -Monitoring tool report -Site verification report on refurbishment and augmentation -Suppliers, Service providers and labor payments -Site attendance by technicians to refurbishment and augmentation program me -7 days’ notice for projects less that R 200,000.00 -Reduced no of Customer Complaints |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 600,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 30 June 2013 | R 150,000.00 |  | R 150,000.00 |  | R 150,000.00 |  |  | R 150,000.00 |  |  |
| Fencing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Electronic flow meters |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maturation ponds |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Drying baskets and beds |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of the effluent management plan |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Mechanical and Electrical infrastructure replacement and augmentation |  | Develop, cost & implement the replacement and augmentation of Mechanical and Electrical infrastructure |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure reduced operational cost of carting fuel to pump stations, -To ensure reduced breakdowns -To ensure efficient management of Eskom accounts compared to diesel deliveries. |  | 30 June 2013 |  |  | Optimize the exiting budget to be utilized elsewhere. Improved uninterrupted service to the consumers |  | 163 number of pump installations which serve (Mbizana, Ntabankulu, Matatiele, Umzimvubu) |  | 63 pump installations to be installed |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 20 | 20 |  | 20 | 23 |
| Monthly report -Standing committee -Completion certification -Expenditure reports -Job cards -Vehicle logbooks -Term Tenders -Augmentation Plan -Some of the diesel driven installations electrified -Customer Complaints |  | 01 July 2012 |  |  | -Progress report -Standing committee approval -Site verification report on augmentation -Suppliers, Service providers payments -Site attendance by technicians to refurbishment and augmentation program me -Reduced no of Customer Complaints |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 4,000,000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Conversion of diesel pump stations to electrical powered motors | 01 July 2012 |  | 30 June 2013 | R 1,000,000.00 |  | R 1,000,000.00 |  | R 1,000,000.00 |  |  | R 1,000,000.00 |  |  |
| List all diesel operated pump stations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Eskom applications |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tendering for special mechanical and electrical works |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Rehabilitation of Mbizana and Ntabankulu ponds |  | Develop, cost & implement the rehabilitation of Mbizana and Ntabankulu ponds. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |
| - To ensure improved pond operation -To improve the effluent quality that meets standards -To provide controlled access -Appointment of contractor |  | 30 June 2013 |  | -Achieved good quality effluent; -prevent raw effluent and uncontrolled dumping -Pond efficiency will increase; -Appointment letter; |  |  | 2 Pond is serving Mbizana and Ntabankulu urban and rural |  | 2 x pond refurbishment to be served |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 | 1 |  |  |
| Monthly report -Standing committee -MHS Report -Completion certificates -Expenditure reports -Job cards -Vehicle logbooks -Internal, Term Tenders -Refurbishment Plan -Customer Complaints |  | 01 July 2012 |  | -Progress report -Standing committee approval -Monitoring and water quality management tool report -Site verification report on refurbishment and augmentation -Suppliers, Service providers and labor payments -Site attendance by technicians to refurbishment and augmentation program me -EIA assessment and approval -7 days’ notice for projects less that R 200,000.00 -Reduced no of Customer Complaints |  |  | 31 December 2012 |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 2,500,000.00 |  | VOTE NUMBER |  |  | ???? |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Refurbishment of water infrastructure | 01 July 2012 |  | 31 December 2012 |  | R 250,000.00 | R 1 250,000.00 |  | R 1 000,000.00 |  |  |  |  |
| Terms of reference | 25 May 2012 |  | 31 May 2012 |  |  |  |  |  |  |  |  |  |
| Tendering | 01 June 2012 |  | 31 August 2012 |  |  |  |  |  |  |  |  |  |
| Construction | 15 September 2012 |  | 28 February 2013 |  |  |  |  |  |  |  |  |  |
| -Completion and Project Handover | 28 February 2012 |  | 15 March 2013 |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Plant Process Audit |  | Develop, cost & implement the Plant Process Audits. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -To ensure improved WTW & WWTW operation -To ensure water quality that meets standards. -To ensure that dilapidated infrastructure is replaced. -To ensure skills gap is audited |  | 01 July 2012 |  |  | -Efficient operations of the WTW & WWTW, management -Improved BDS &GDS requirements |  | 9 WTW & WWTW |  | 9 x WTW & WWTW |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 2 | 3 |  | 3 | 1 |
| Monthly report -Standing committee -Completion certificates -Expenditure reports -Effective workforce -Term Tenders -Refurbishment Plan -Customer Complaints -Blue & Green Drop Certification |  | 01 July 2012 |  |  | -Monthly Progress report -Standing committee approval -Completed project -Payment of invoices -Improved water quality -Tender awarded and project completed -Response Complaints -Improved BDS & GDS accreditation |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 3,000 000.00 |  |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Plant Process Audit | 01 July 2012 |  | 30 June 2013 | R 675 000.00 |  | R 675 000.00 |  | R 675 000.00 |  |  | R 675 000.00 |  |  |
| Replacement of filter nozzles and sand |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cleaning of Sludge lagoons |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Security fencing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Register of skills gap |  |  |  |  |  |  |  |  |  |  |  |  |  |
| On site training of process controllers |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Water Bulk Infrastructure Development |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Owen Ngubende Hlazo – Executive Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Cedarville Tank |  | Develop, cost & implement the construction of an additional reservoir. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| - To ensure improved water storage -To ensure water quantity that meets demand. -To ensure that dilapidated infrastructure is replaced. |  | 01 July 2012 |  | --Efficient supply meets the demand - Improved supply storage |  | 300kl storage available of the |  |  | Construction of 300kl reservoir |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 | 1 |  |  |
| Monthly report -Standing committee -Completion certificates -Expenditure reports -Effective workforce -Term Tenders -Replacement Plan |  | 01 July 2012 |  | -Monthly Progress report -Standing committee approval -Completed project -Payment of invoices -Improved water quality -Tender awarded project completed |  | 30 June 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 600 000.00 |  | VOTE NUMBER |  | ???? |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Replacement of Reservoir | 01 July 2012 |  | 30 November 2012 |  | R 300 000.00 |  | R 300 000.00 |  |  |  |  |  |
| Tendering | 01 July 2012 |  | 30 September 2012 |  |  |  |  |  |  |  |  |  |
| Construction | 30 November 2012 |  | 15 January 2013 |  |  |  |  |  |  |  |  |  |
| Project hand over | 30 November 2012 |  | 30 January 2013 |  |  |  |  |  |  |  |  |  |

3. DEVELOPMENT AND ECONOMIC PLANNING

  - DEVELOPMENT PLANNING UNIT

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Small Town Restructuring and Revitalization |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Development of Guidelines for Small Towns Restructuring |  | To facilitate Urban Renewal of all Small Towns within the district by 2017 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Adopted Guidelines Across the District |  | 31 March 2013 |  | Uniform Urban Centres Development with standard Land use Management Schemes Across the District. |  | None |  | Guidelines for Small Towns restructuring |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  | Guidelines |  |
| Council Resolution |  | 31 March 2013 |  | Approved Urban Design Plans/ Land Use Schemes |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R450 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Formulation of Terms of Reference | 01 August 2012 |  | 15 August 2012 |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Procurement process | 15 August 2012 |  | 30 September 2012 |  | R10 000.00 | Nil | Nil |  |  | Nil |  |  |
| Situational Analysis | 01 October 2012 |  | 15 November 2012 |  | Nil | R130 000.00 | Nil |  |  | Nil |  |  |
| Guidelines formulation and Designs | 01 December 2012 |  | 31 March 2013 |  | Nil | Nil | R300 000.00 |  |  | Nil |  |  |
| Approval of Guidelines | 01 June 2013 |  | 30 June 2013 |  | Nil | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Spatial planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Beach to Berg Corridor Development Plan |  | To facilitate economic development through Tourism Corridor |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Adopted Development Plan |  | 31 March 2013 |  | Detailed Corridor Development Plan to facilitate tourism development. |  | Spatial Development Framework 2012 |  |  | Detailed Corridor Development plan |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  |  | Detailed plan |  |
| Council Resolution |  | 31 March 2013 |  | Approved Urban Design Plans/ Land Use Schemes |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R350 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Formulation of Terms of Reference | 01 August 2012 |  | 15 August 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| Procurement process | 15 August 2012 |  | 30 September 2012 |  | R10 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| Situational Analysis | 01 October 2012 |  | 15 November 2012 |  | Nil |  | R130 000.00 | Nil |  |  | Nil |  |  |
| Formulation of Corridor Development Plan | 01 December 2012 |  | 31 March 2013 |  | Nil |  | Nil | R210 000.00 |  |  | Nil |  |  |
| Approval of the Plan | 01 June 2013 |  | 30 June 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Spatial planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Nodal Development Frameworks |  | To facilitate planning that guides future development of nodes |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of Local Municipalities with Nodal Development Frameworks |  | 30 June 2013 |  | Sustainable Nodal Development |  |  | Spatial Development Framework 2012 |  | Two local Municipalities |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 2 |
| Approved Nodal Development plans |  | 30 June 2013 |  | Detailed design Plans for nodes |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R800 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Formulation of Terms of Reference | 15 July 2012 |  | 01 August 2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Procurement process | 15 August 2012 |  | 30 September 2012 |  | R10 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Situational Analysis | 01 October 2012 |  | 15 November 2012 |  | Nil | Nil |  | R240 000.00 |  |  | Nil |  |  |
| Formulation of Nodal Development Plans | 01 December 2012 |  | 30 June 2013 |  | Nil | Nil |  | R350 000.00 |  |  | R200 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Integrated Development Planning |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Development Planning |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |
| IDP Review and Strategic Planning Session | To facilitate planning that guides future development of nodes |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |
| Number of IDPs Produced | 30 June 2013 |  | Integrated and aligned development | 5 IDPs (District and LMs) |  | 5 IDPs |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q1 |
|  |  |  |  |  |  | 0 | 0 | 5 | 5 |
| Approved Nodal Development plans | 30 June 2013 |  | Council Resolutions and comments by DLGTA MEC’s Comments | 30 June 2013 |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1 000 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE | END DATE | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  | QUARTER 4 |  |
| Development of IDP Process Plan and facilitate adoption process by Council. | 15 July 2012 | 30 August 2012 | R10 000.00 |  | Nil | Nil |  | Nil |  |
| Formulation of Committees (IDP Representative and Steering) | 01 September 2012 | 30 September 2012 | R10 000.00 |  | Nil | Nil |  | Nil |  |
| Situational Analysis/ Research | 01 October 2012 | 30 October 2012 | Nil |  | R600 000.00 | Nil |  | Nil |  |
| Meetings (Rep and Steering Committees) | 15 September 2012 | 15 May 2013 | R10 000.00 |  | R10 000.00 | R10 000.00 |  | R10 000.00 |  |
| Strategies Formulation and Projects Prioritisation | 01 November 2012 | 15 December 2012 | Nil |  | R200 000.00 |  |  |  |  |
| Integration and Alignment of projects and programmes | 15 January 2013 | 15 March 2013 | Nil |  | Nil | Nil |  | Nil |  |
| Facilitate adoption of First Draft IDP and assessment by DLGTA | 15 March 2013 | 10 April 2013 | Nil |  | Nil | Nil |  | Nil |  |
| Community and Stakeholders Consultation on Draft IDP | 15 April 2013 | 30 April 2013 | Nil |  | Nil | Nil |  | R140 000.00 |  |
| SDBIP Drafting | 15 April 2013 | 15 May 2013 | Nil |  | Nil | Nil |  | Nil |  |
| Facilitate approval process of Final IDP (Documentation) | 15 May 2013 | 31 May 2013 | Nil |  | Nil | Nil |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Spatial Planning Capacity to LMs |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Spatial Planning (Capacity Support to LMs on SDF Reviews) |  | To facilitate development or review of Spatial Development Frameworks for LMs to guides future development in LMs. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of SDFs for LMs Produced |  | 30 June 2013 |  | Spatial Development Frameworks for all LMs |  | 2 LMs |  | 2 SDFs |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 0 | 0 |  | 0 | 2 |
| Approved Development plans Nodal |  | 30 June 2013 |  | Council Resolutions and comments by DLGTA MEC’s Comments |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R1 100 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Formulation of Terms of Reference | 15 July 2012 |  | 01 August 2012 | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Procurement process | 15 August 2012 |  | 30 September 2012 | R10 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Situational Analysis | 01 October 2012 |  | 15 November 2012 | Nil | Nil |  | R480 000.00 |  |  | Nil |  |  |
| Formulation of SDFs for Mbizana and Ntabankulu LMs | 01 December 2012 |  | 30 June 2013 | Nil | Nil |  | R320 000.00 |  |  | R290 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Settlement of Land Claims and Implementation of SDFs |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Establishment of District Land Claims Task Team |  | To facilitate a 25% settlement of Land Claims in ANDM by 2017 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of Meetings held by Task Team and Agreements resolved |  | 30 June 2013 |  | Number of Claims settled or Number of Agreements with Claimants signed to release land for development |  | None |  | 4 Meeting and 5 Claims Settled |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 1 Meeting | 1 Meeting |  | 2 Claims 1 Meeting | 3 Claims. 1 Meeting |
| Minutes and Signed Agreements |  | 30 June 2013 |  | Settlement Agreements signed |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R250 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Formulation of Terms of Reference | 15 July 2012 |  | 01 August 2012 | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Establishment of the Task Team Session | 15 August 2012 |  | 30 August 2012 | R150 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Task Team Meetings | 01 September 2012 |  | 15 June 2013 | R25 000.00 | R25 000.00 |  | R25 000.00 |  |  | R25 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Spatial Development Framework |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Spatial and Statutory Planning across the district |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Development Planning |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |
| Establishment of District Planning Forum |  | To have a functional Planning Forum by 2013 that will coordinate Development Planning Activities across the district. |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of Meetings held by Task Team and plans evaluated and approved |  | 30 June 2013 |  | Number of Development Plans approved |  | None | 4 Meetings |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  | 1 Meeting |  | 1 Meeting | 1 Meeting | 1 Meeting |
| Minutes and Resolutions |  | 30 June 2013 |  | Settlement Agreements signed |  | 30 June 2013 |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R150 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Formulation of Terms of Reference | 15 July 2012 |  | 01 August 2012 |  | Nil | Nil |  | Nil |  | Nil |  |
| Establishment of the District Planning Forum Session | 15 August 2012 |  | 30 August 2012 |  | R120 000.00 | Nil |  | Nil |  | Nil |  |
| Forum Meetings | 01 September 2012 |  | 15 June 2013 |  | R10 000.00 | R10 000.00 |  | R10 000.00 |  | R10 000.00 |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Institutional Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Development Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institutional Performance (Quarterly and Mid-Term Assessment Reports) 2012/13 | To ensure proper reporting on performance by the municipality. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |
| Number of performance Report produced and submitted to Management and Council | 30 June 2013 |  |  |  | Improved levels of accountability on Municipal Performance |  | 4 Quarterly Reports and Mid-term Assessment Report for 2011/12 |  |  | 4 reports |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 | Q3 |  | Q1 |
|  |  |  |  |  |  |  |  |  |  | 1 |  |  | 1 | 1 |  | 1 |
| Council Resolutions | 30 June 2013 |  |  |  | Audit outcomes for 2012/13 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R0 |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| -Collection of departmental quarterly reports and consolidation of reports for submission to Mayoral and Council and submission to organs of state |  | 01 October 2012 |  | 31 October 2012 |  | Nil |  | Nil |  |  | Nil |  |  | Nil |  |  |
| -Collection of departmental mid-term performance reports and get them consolidated for submission to Mayoral and Council |  | 06 January 2013 |  | 13 January 2013 |  | Nil |  | Nil |  |  | Nil |  |  | Nil |  |  |
| -Facilitate adoption process of Mid-term reports by Mayoral and Council and submission to organs of state |  | 16 January 2013 |  | 25 January 2013 |  | Nil |  | Nil |  |  | Nil |  |  | Nil |  |  |
| -Collection of departmental quarterly reports and consolidation of reports for submission to Mayoral and Council and to organs of state |  | 01 April 2013 |  | 30 April 2013 |  | Nil |  | Nil |  |  | Nil |  |  | Nil |  |  |
| -Collection of departmental quarterly reports and consolidation of reports for submission to Mayoral and Council and to organs of state |  | 01 July 2013 |  | 31 July 2013 |  | Nil |  | Nil |  |  | R5 000-00 |  |  | Nil |  |  |
| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA | Annual Performance Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Development Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual Report for 2011/12 | To ensure proper reporting on performance and compliance by the municipality. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |
| Approved Annual Report by Council and MPAC | 31 March 2013 |  |  |  | Approved Annual Report by Council and MPAC and considered by Provincial Legislature |  | 2 Reports (Annual Performance and Annual Report0 |  |  | 2 Reports |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 | Q3 |  | Q1 |
|  |  |  |  |  |  |  |  |  |  | 1 |  |  | 0 | 1 |  | 0 |
| Council Resolution | 31 March 2013 |  |  |  | Council Resolution |  | 31 March 2013 |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R0 |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE | END DATE |  | QUARTER 1 |  |  | QUARTER 2 |  |  | QUARTER 3 |  |  | QUARTER 4 |  |
| -Collection of departmental Annual Reports and Formulation of Annual Performance Report for 2011/12 |  |  | 15 July 2012 | 31 August 2012 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |
| Drafting of Municipal Annual Report 2011/12 |  |  | 01 September 2012 | 30 October 2012 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |
| Tabling of Draft Annual 2011/12 |  |  | 02 January 2013 | 25 January 2013 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |
| -Submission of Draft Annual Report to organs of state |  |  | 01 February 2013 | 10 February 2013 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |
| Undertake Public participation on Draft Annual report |  |  | 01 February 2013 | 10 March 2013 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |
| Facilitate approval of Final Draft Annual Report |  |  | 10 March 2013 | 31 March 2012 |  | Nil |  |  | Nil |  |  | Nil |  |  | Nil |  |

  - ECONOMIC PLANNING UNIT

| NATIONAL KEY PERFORMANCE AREA |  |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  |  |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of Investment Attraction Strategy |  |  |  | To develop and implement an Investment Attraction Strategy by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  |  | TARGET DATE |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |
| Approved Investment Attraction Strategy |  |  |  | 30th June 2013 |  |  |  | Increase in the level of investment in ANDM |  |  |  |  |  | None |  |  |  | 1 Approved Plan |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  |  | TARGET DATE |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Procurement Process |  |  | Situational Analysis |  |  | Strategic Framework |  |  | 1 Plan |
| Council Resolution |  |  |  | 30th June 2013 |  |  |  | Increase in the level of investment |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | 500 000 |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  | TIMEFRAMES |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | START DATE |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |
| Development of Terms of Reference |  |  |  | 1st July 2012 |  |  |  | 30th July 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |
| Incorporation of the project into the DST Work Plan |  |  |  | 1st July 2012 |  |  |  | 30th July 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |
| Procurement Process |  |  |  | 1st August 2012 |  |  |  | 30th September 2012 |  |  |  | 20000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  |  | 1st July 2012 |  |  |  | 30th September 2012 |  |  |  |  |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |
| Confirming the drivers and launching the process: Inception Report |  |  |  | 1st October 2012 |  |  |  | 30th November 2012 |  |  |  | - |  |  |  | 40000 |  |  |  | - |  |  |  |  |  | - |  |
| Investigation and analysis of the development context, challenges, possibilities and constraints: Situational Analysis |  |  |  | 1st January 2013 |  |  |  | 30th March 2013 |  |  |  | - |  |  |  | - |  |  |  | 250000 |  |  |  |  |  | - |  |
| Establish priorities, framing choices, setting strategic goals and objectives: Strategic Framework |  |  |  | 1st February 2013 |  |  |  | 31st April 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |  | 150000 |  |
| Implementation Plan including Final LED Strategy |  |  |  | 1st May 2013 |  |  |  | 31st May 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | 40000 |  |
| NATIONAL KEY PERFORMANCE AREA |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of LED Strategy Outcomes |  | To reduce the level of unemployment from 70% to 40% by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |
| LED Feasibility Study Report |  | 30th June 2013 |  |  |  |  |  | Identified key projects for funding coupled by key estimates |  |  |  |  |  | LED Strategy currently underway |  |  |  |  | LED Feasibility Study Report |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 |  | Q3 |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Inception Report |  |  | First Draft Report |  | Second Draft Report |  |  | Final Report |
| LED Feasibility Study Report |  | 30th June 2013 |  |  |  |  |  | Key interventions budgeted for |  |  |  |  |  | 30th June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000 |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |  |  |
| Development of Terms of Reference | 1st Sept 2012 |  |  |  | 30th Sept 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |
| Incorporation of the project into the DST Work Plan | 1st Sept 2012 |  |  |  | 30th Sept 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |  |  |
| Procurement Process | 1st October 2012 |  |  |  | 30th Nov 2012 |  |  |  | R20 000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project | 1st Dec 2012 |  |  |  | 30th Jan 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |  |  |
| Confirming the drivers and launching the process: Inception Report | 1st Dec 2012 |  |  |  | 30th Jan 2013 |  |  |  | R40 000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |
| First Draft Feasibility Assessment Report | 1st February 2012 |  |  |  | 28th February 2013 |  |  |  | - |  |  |  | - |  |  |  | R150 000 |  |  |  |  |  | - |  |  |  |  |
| Consultative Workshop | 1st Feb 2012 |  |  |  | 28th Feb 2013 |  |  |  | - |  |  |  | - |  |  |  | R50 000 |  |  |  |  |  | - |  |  |  |  |
| Second Draft Feasibility Assessment Report | 1st March 2013 |  |  |  | 31th March 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | R120 000 |  |  |  |  |
| Final Draft Feasibility Assessment Report | 1st April 2013 |  |  |  | 30st April 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | R120 000 |  |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of District Energy Regeneration Strategy |  |  | To develop and implement a District Energy Regeneration Strategy by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |
| Approved District Energy Regeneration Strategy |  |  | 30th June 2013 |  |  |  |  | Number implemented energy regeneration interventions |  |  |  |  |  | None |  |  |  |  | District Energy Regeneration Strategy |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 |  | Q3 |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Procurement Process |  |  | Inception Report |  | Status Quo Report |  |  | Final Report |
| Council Resolution |  |  | 30th June 2013 |  |  |  |  | Number implemented energy regeneration interventions |  |  |  |  |  | 30th June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | R500 000 |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |
| Development of Terms of Reference |  |  | 1st July 2012 |  |  |  | 31st July 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Incorporation of the project into the DST Work Plan |  |  | 1st July 2012 |  |  |  | 31st July 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Procurement Process |  |  | 1st August 2012 |  |  |  | 30th September 2012 |  |  |  | 20 000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  | 1st July 2012 |  |  |  | 30th September 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Confirming the drivers and launching the process: Inception Report |  |  | 1st October 2012 |  |  |  | 30th November 2012 |  |  |  | - |  |  |  | 40 000 |  |  |  | - |  |  |  |  |  | - |  |  |
| Investigation and analysis of the district energy regeneration development context, challenges, possibilities and constraints: Situational Analysis including SWOT Analysis |  |  | 1st December 2012 |  |  |  | 31st March 2013 |  |  |  | - |  |  |  | - |  |  |  | 250 000 |  |  |  |  |  |  |  |  |
| Development of :Strategic Framework |  |  | 1st April 2013 |  |  |  | 31th May 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | 150 000 |  |  |
| Implementation Plan including Final District Energy Regeneration Strategy |  |  | 1st June 2013 |  |  |  | 30th June 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | 40 000 |  |  |
| NATIONAL KEY PERFORMANCE AREA |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of Tourism Plan |  |  | To implement the outcomes of the Tourism Sector Plan by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |
| Tourism Feasibility Study Report |  |  | 30th June 2013 |  |  |  |  | Identified key projects for funding coupled by key estimates |  |  |  |  |  | Tourism Plan currently underway |  |  |  |  | Tourism Feasibility Study Report |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 |  | Q3 |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Inception Report |  |  | First Draft Report |  | Second Draft Report |  |  | Final Report |
| Tourism Feasibility Study Report |  |  | 30th June 2013 |  |  |  |  | Key interventions budgeted for |  |  |  |  |  | 30th June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | 500 000 |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |
| Development of Terms of Reference |  |  | 1st Sept 2012 |  |  | 30th Sept 2012 |  |  |  | - |  |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Incorporation of the project into the DST Work Plan |  |  | 1st Sept 2012 |  |  | 30th Sept 2012 |  |  |  | - |  |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |
| Procurement Process |  |  | 1st October 2012 |  |  | 30th November 2012 |  |  |  | 20 000 |  |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  | 1st December 2012 |  |  | 30th January 2013 |  |  |  | - |  |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |
| Confirming the drivers and launching the process: Inception Report |  |  | 1st December 2012 |  |  | 30th January 2013 |  |  |  | 40 000 |  |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |
| First Draft Feasibility Assessment Report |  |  | 1st February 2012 |  |  | 28th February 2013 |  |  |  | - |  |  |  |  | - |  |  |  | 150 000 |  |  |  |  |  | - |  |  |
| Consultative Workshop |  |  | 1st February 2012 |  |  | 28th t February 2013 |  |  |  | - |  |  |  |  | - |  |  |  | 50 000 |  |  |  |  |  | - |  |  |
| Second Draft Feasibility Assessment Report |  |  | 1st March 2013 |  |  | 31th March 2013 |  |  |  | - |  |  |  |  | - |  |  |  | - |  |  |  |  |  | 120 000 |  |  |
| Final Draft Feasibility Assessment Report |  |  | 1st April 2013 |  |  | 30th April 2013 |  |  |  | - |  |  |  |  | - |  |  |  | - |  |  |  |  |  | 120 000 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of SMME Plan |  | To implement the outcomes of the SMME Sector Plan by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |
| SMME Feasibility Study Report |  | 30th June 2013 |  |  |  |  |  |  | Identified key projects for funding coupled by key estimates |  |  |  |  |  | SMME Plan currently underway |  |  |  |  |  |  | SMME Feasibility Study Report |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |
| SMME Feasibility Study Report |  | 30th June 2013 |  |  |  |  |  |  | Key interventions budgeted for |  |  |  |  |  | 30th June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 500 000 |  |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  | TIMEFRAMES |  |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | START DATE |  |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |  |  |  |
| Development of Terms of Reference |  |  |  | 1st Sept 2012 |  |  |  |  | 30th Sept 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |
| Incorporation of the project into the DST Work Plan |  |  |  | 1st Sept 2012 |  |  |  |  | 30th Sept 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |
| Procurement Process |  |  |  | 1st October 2012 |  |  |  |  | 30th November 2012 |  |  |  | 20 000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  |  | 1st December 2012 |  |  |  |  | 30th January 2012 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  |
| Confirming the drivers and launching the process: Inception Report |  |  |  | 1st December 2012 |  |  |  |  | 30th January 2013 |  |  |  | 40 000 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |
| First Draft Feasibility Assessment Report |  |  |  | 1st February 2012 |  |  |  |  | 28th February 2013 |  |  |  | - |  |  |  | - |  |  |  | 150 000 |  |  |  |  |  | - |  |  |  |  |  |
| Consultative Workshop |  |  |  | 1st February 2012 |  |  |  |  | 28st February 2013 |  |  |  | - |  |  |  | - |  |  |  | 50 000 |  |  |  |  |  | - |  |  |  |  |  |
| Second Draft Feasibility Assessment Report |  |  |  | 1st March 2013 |  |  |  |  | 31st March 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | 120 000 |  |  |  |  |  |
| Final Draft Feasibility Assessment Report |  |  |  | 1st April 2013 |  |  |  |  | 30th April 2013 |  |  |  | - |  |  |  | - |  |  |  | - |  |  |  |  |  | 120 000 |  |  |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of Rural Development Strategy |  | To develop and implement the District Rural Development Strategy by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |
| Approved District Rural Development Strategy |  | 30th June 2013 |  |  |  |  |  |  | Number of rural development initiatives implemented |  |  |  |  |  |  | None |  |  |  |  |  | 1 Approved Plan |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  |  | TARGET DATE |  |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Procurement Process |  |  |  | Situational Analysis |  | Strategic Framework |  |  |  | Final Report |
| Council Resolution |  | 30th June 2013 |  |  |  |  |  |  | Number of rural development initiatives implemented |  |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 500 000 |  |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  |  |  |  | TIMEFRAMES |  |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | START DATE |  |  |  | END DATE |  |  |  |  | QUARTER 1 |  |  | QUARTER 2 |  |  |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |
| Development of Terms of Reference |  |  |  |  |  |  | 1st July 2012 |  |  |  | 30th July 2012 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |
| Incorporation of the project into the DST Work Plan |  |  |  |  |  |  | 1st July 2012 |  |  |  | 30th July 2012 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |
| Procurement Process |  |  |  |  |  |  | 1st August 2012 |  |  |  | 30th September 2012 |  |  |  |  | 20 000 |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  |  |  |  |  | 1st July 2012 |  |  |  | 30th September 2012 |  |  |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |
| Confirming the drivers and launching the process: Inception Report |  |  |  |  |  |  | 1st October 2012 |  |  |  | 30th November 2012 |  |  |  |  | - |  |  | 40 000 |  |  |  |  |  | - |  |  |  |  |  | - |  |
| Investigation and analysis of the development context, challenges, possibilities and constraints: Situational Analysis |  |  |  |  |  |  | 1st January 2013 |  |  |  | 31st March 2013 |  |  |  |  | - |  |  | - |  |  |  |  |  | 250 000 |  |  |  |  |  | - |  |
| Establish priorities, framing choices, setting strategic goals and objectives: Strategic Framework |  |  |  |  |  |  | 1st April 2013 |  |  |  | 31st May 2013 |  |  |  |  | - |  |  | - |  |  |  |  |  |  |  |  |  |  |  | 150 000 |  |
| Implementation Plan including Final District Rural Development Strategy |  |  |  |  |  |  | 1st May 2013 |  |  |  | 31st May 2013 |  |  |  |  | - |  |  | - |  |  |  |  |  | - |  |  |  |  |  | 40 000 |  |
| NATIONAL KEY PERFORMANCE AREA |  |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  |  |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of Agricultural Production Business Plan |  |  |  | To develop and implement a grain production Business Plan which will enable access to markets for the agricultural sector by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  |  | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |
| Agricultural Production Business Plan |  |  |  | 30th June 2013 |  |  |  |  | Increase in the level of production within the agricultural sector |  |  |  |  |  | Feasibility Study currently underway |  |  |  |  |  |  | Agricultural Production Business Plan |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  |  | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Procurement Process |  |  |  | Inception Report |  | First Draft Report |  |  |  | Final Report |
| Agricultural Production Business Plan |  |  |  | 30th June 2013 |  |  |  |  | Number of agricultural production interventions implemented |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | 500 000 |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  |  | TIMEFRAMES |  |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | START DATE |  |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |
| Development of Terms of Reference |  |  |  |  | 1st Dec 2012 |  |  |  |  | 31st Dec 2012 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |
| Incorporation of the project into the DST Work Plan |  |  |  |  | 1st Dec 2012 |  |  |  |  | 31st Dec 2012 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Procurement Process |  |  |  |  | 1st July 2013 |  |  |  |  | 28th February 2013 |  |  |  | 20 000 |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  |  |  | 1st March 2012 |  |  |  |  | 30th March 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Confirming the drivers and launching the process: Inception Report |  |  |  |  | 1st March 2013 |  |  |  |  | 30th March 2013 |  |  |  | 40 000 |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |
| First Draft Business Plan Report |  |  |  |  | 1st April 2012 |  |  |  |  | 30th April 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  | 150 000 |  |  |  |  |  | - |  |  |
| Consultative Workshop |  |  |  |  | 1st April 2013 |  |  |  |  | 30th April 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  | 50 000 |  |  |  |  |  | - |  |  |
| Second Draft Business Plan Report |  |  |  |  | 1st May 2013 |  |  |  |  | 31th May 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | 120 000 |  |  |
| Final Draft Business Plan Report |  |  |  |  | 1st June 2013 |  |  |  |  | 30th June 2013 |  |  |  | - |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | 120 000 |  |  |
| NATIONAL KEY PERFORMANCE AREA |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rural Development Summit |  |  | To ensure that there is continued dialogue of rural development issues and integration in terms of planning, implementation and monitoring and evaluation by 2016/17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  |  | TARGET DATE |  |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |
| Rural Development Summit Outcomes Report |  |  | 30th June 2013 |  |  |  |  |  | Number of rural development summit initiatives implemented |  |  |  |  |  | None |  |  |  |  |  |  | 1 Approved Plan |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  |  | TARGET DATE |  |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Procurement Process |  |  |  | Situational Analysis |  | Strategic Framework |  |  |  | 1 Plan |
| Council Resolution |  |  | 30th June 2013 |  |  |  |  |  | Number of rural development summit initiatives implemented |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | 500 000 |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE |  |  |  |  | END DATE |  |  |  | QUARTER 1 |  |  |  |  | QUARTER 2 |  |  |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |  |
| Development of Terms of Reference |  |  | 1st July 2012 |  |  |  |  | 30th July 2012 |  |  |  | - |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |
| Incorporation of the project into the DST Work Plan |  |  | 1st July 2012 |  |  |  |  | 31st July 2012 |  |  |  | - |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |
| Procurement Process |  |  | 1st August 2012 |  |  |  |  | 30th September 2012 |  |  |  | 20 000 |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project |  |  | 1st July 2012 |  |  |  |  | 30th September 2012 |  |  |  |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |
| Confirming the drivers and launching the process: Inception Report |  |  | 1st October 2012 |  |  |  |  | 30th November 2012 |  |  |  | - |  |  |  |  | 40 000 |  |  |  |  |  | - |  |  |  |  |  | - |  |  |  |
| Development of Concept Document |  |  | 1st December 2013 |  |  |  |  | 28th February 2013 |  |  |  | - |  |  |  |  | - |  |  |  |  |  | 150 000 |  |  |  |  |  | - |  |  |  |
| Rural Development Summit |  |  | 1st March 2013 |  |  |  |  | 31st March 2013 |  |  |  | - |  |  |  |  | - |  |  |  |  |  | 250 000 |  |  |  |  |  | - |  |  |  |
| Submission of Final Report |  |  | 1st April 2013 |  |  |  |  | 30th April 2013 |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  |  | 40 000 |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishment of LED Fora |  | To facilitate and coordinate the establishment and strengthening of all functional IGR LED structures by 2012/13 financial year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |
| Established LED For a |  | 30th June 2013 |  |  |  |  |  |  | Number LED Fora |  |  |  |  |  | District Support Team |  |  |  |  |  |  | 5 LED Fora |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  |  | TARGET DATE |  |  |  |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Work Planning |  |  |  | Quarterly Meetings |  | Quarterly Meetings |  |  |  | Quarterly Meetings |
| Terms of Reference and Quarterly Progress Reports |  | 30th June 2013 |  |  |  |  |  |  | Number LED Fora |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | 150 000 |  |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  |  |  |  | END DATE |  |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  |  | QUARTER 3 |  |  |  |  |  |  | QUARTER 4 |  |  |  |  |  |
| Development of Terms of Reference | 1st July 2012 |  |  |  |  | 30th July 2012 |  |  |  |  | - |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |
| Incorporation of the project into the DST Work Plan | 1st July 2012 |  |  |  |  | 30th July 2012 |  |  |  |  | - |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |
| Mobilising of stakeholders and establishment of Core Team of the Project | 1st July 2012 |  |  |  |  | 30th September 2012 |  |  |  |  | - |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |
| District - Wide Project Initiation Workshop Session | 1st July |  |  |  |  | 30th July 2012 |  |  |  |  | 15 000 |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |
| Work Planning Sessions | 1st August 2012 |  |  |  |  | 30th August 2012 |  |  |  |  | 50 000 |  |  |  | - |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |
| Quarterly Meetings | 1st July 2012 |  |  |  |  | 30th June 2013 |  |  |  |  | 21 250 |  |  |  | 21 250 |  |  |  |  | 21 250 |  |  |  |  |  |  | 21 250 |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Economic Planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager Economic planning |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Resource Mobilisation Intervention | To dedicate district human resource support towards the mobilisation of financial and non-financial support for local economic development at local municipal level by 2012/13 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Resource Mobilisation Plan developed and implemented | 30th June 2013 | Number of funding opportunities applied for |  |  | None |  | 16 applications submitted |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | Resource Mobilisation Strategy |  | DST Quarterly Enrichment Sessions | DST Quarterly Enrichment Sessions |  | DST Quarterly Enrichment Sessions |
| Resource mobilisation plan | 30th June 2013 | Number of funding opportunities applied for |  |  | 30th June 2017 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | 265 000 | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Development of Terms of Reference | 1st July 2012 |  | 31st July 2012 | - |  | - |  | - |  |  | - |  |
| Incorporation of the project into the DST Work Plan | 1st July 2012 |  | 31st July 2012 | - |  | - |  | - |  |  | - |  |
| Mobilising of stakeholders and establishment of Core Team of the Project | 1st July 2012 |  | 30th Sept 2012 | - |  | - |  | - |  |  | - |  |
| Development of Inventory List for funding opportunities ANDM | 1st July 2012 |  | 30th July 2012 | 20 000 |  | - |  | - |  |  | - |  |
| Awareness raising workshops regarding funding opportunities | 1st July 2012 |  | 30th August 2012 | 15 0000 |  | 15 000 |  | 15 000 |  |  | 15 0000 |  |
| DST Quarterly Enrichment Sessions for funding opportunities | 1st July 2012 |  | 30th June 2013 | 25 000 |  | 25 000 |  | 25 000 |  |  | 25 0000 |  |
| Application submissions | 1st July 2012 |  | 30th June 2013 | 16 250 |  | 16 250 |  | 16 250 |  |  | 16 250 |  |
| Impact Evaluation Session | 1st June 2012 |  | 30th June 2013 | - |  | - |  | - |  |  | 25 0000 |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Comprehensive, accurate and up-to-date Geographic Information for the ANDM |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Geographic Information Systems Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| GIS Shared Service Implementation |  | To ensure LMs within the ANDM have access to GIS data and related services. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -Number of Local Municipalities connected on GIS Services |  | 30 December 2012 |  | Fully functional GIS shared service. |  |  | GIS Server in place |  | Four local Municipalities on the GIS GIS Shared Service. |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 0 |  | 4 | 0 |
| Signed Service Level agreements and |  | 30 December 2012 |  | LMs being able to generate their own Maps using GIS |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Connectivity Establishment | 01 July 2012 |  | 30 August 2012 |  | R250 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Implementation | 01 September 2012 |  | 30 November 2012 |  | Nil | R200 000.00 |  | Nil |  |  | Nil |  |  |
| Training/Workshops | 01 December 2012 |  | 15 December 2012 |  | Nil | R50 000.00 |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Ensure GIS Unit has a 3 to 5 year Strategy |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Geographic Information Systems Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| GIS Strategy |  | -To have an informed guide for current functioning and future development of the GIS unit. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| - Approved GIS Strategy |  | 30 November 2012 |  | Strategic planning and decision making relating to GIS data management |  | None |  | Completed GIS Strategy |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 1 GIS strategy |  | 0 | 0 |
| Council Resolution |  | 30 November 2012 |  | Adhering and compliance with the GIS strategy & policy. |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop Terms of Reference | 01 July 2012 |  | 30 July 2012 |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Appoint Service Provider | 01 August 2012 |  | 30 August 2012 |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Strategy and Policy Development | 01 September 2012 |  | 30 November 2012 |  | R200 000.00 | Nil | Nil |  |  | Nil |  |  |
| Handover of completed GIS Strategy and approval | 01 December 2012 |  | 31 December 2012 |  | Nil | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Complete, accurate and up-to-date GIS Database for ANDM |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Geographic Information Systems Manager |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| GIS Data Maintenance |  | To ensure data on the projects are georeferrenced and are on the GIS database for planning purposes. |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Data for all relevant projects captured. Physically verified projects. |  | 30 June 2013 |  | Updated GIS database Updated service backlog data |  | GIS Database |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| A recent service backlogs wall map |  | 30 June 2013 |  |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R300 000.00 |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Water Supply Schemes Infrastructure | 01 July 2012 |  | 30 June 2013 |  | R50 000.00 | R25000.00 | R25000.00 |  |  | Nil |  |  |
| Drought Relief Projects | 01 July 2012 |  | 30 June 2013 |  | Nil | R25000.00 | R25000.00 |  |  | Nil |  |  |
| Recently installed sales meters | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | R20 000.00 |  |  | Nil |  |  |
| Bulk Meters | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Environmental Information Systems - Data | 01 July 2012 |  | 30 June 2013 |  | Nil | R20 000.00 | Nil |  |  | Nil |  |  |
| Emergency Response Plan - Data | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | R40 000.00 |  |  | R20 000.00 |  |  |
| Tourist Facilities | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | Nil |  |  | R50 000.00 |  |  |
| Sanitation | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Infrastructure Development and Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | GIS equipment maintainance |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Geographic Information Systems Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| GIS Infrastructure upgrade |  | Ensure all GIS equipment is in good condition |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Equipment in good condition |  | 30 June 2013 |  |  | Equipment in good condition |  | All equipment currently in good condition |  | Equipment in good condition |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| Equipment in good condition |  | 30 June 2013 |  |  | Equipment in good condition |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  |  | VOTE NUMBER |  | V3 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Appoint Service Provider (when necessary) |  |  |  |  |  |  |  |  |  |  |  |  |  |

4.	COMMUNITY SERVICES DEPARTMENT

4.1. MUNICIPAL HEALTH SERVICES

4.1.1 Water Quality Monitoring

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Healthy communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Water Quality Monitoring project/ programme | To reduce prevalence rate of water borne related illnesses. To monitor the quality of water supplied to the communities by ANDM WSA |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Quality of water used for domestic purposes free from any impurities. | 30 June 2013 | Water pollution controlled. Compliance with legislation. |  | 60% achieved on prevention of water pollution (40% uncovered-raw water) 52.54% compliance on blue drop |  | 750 samples taken and analysed per year |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTERLY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  | 188 samples taken 18 wards on H&H awarenesses Recommendations on interventions with regard to non- compliant water sources Coordination of development of SOPs |  | 188 samples taken 18 wards on H&H awarenesses Recommendations on interventions with regard to non- compliant water sources Drafting of SOPs |  | 188 samples 35 wards on H&H awareness Recommendations on interventions with regard to non- compliant water sources Workshops on SOPs | 186 samples 31 wards on H&H awareness Recommendations on interventions with regard to non- compliant water sources Implementation of SOPs |
| Reduced waterborne related illnesses Well informed communities Intervention done by relevant stakeholders (eg IDMS & non WSAs) Developed SOPs | 30 June 2013 01 July 2012 to 30 June 2013 | -Less incidents of water borne diseases. Availability of Basic SOPs |  | 30 June 2013 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |
| Beefing up of existing water kits & purchasing new ones for Ntabankulu & Mbizana. | 01 July 2012 |  | 30 June 2013 |  | R100,000.00 |  | R100,000.00 |  | R150,000.00 |  | R300,000.00 |
| Water samples taken & analysed | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |
| Purchasing of SANS 0241& related legislation | 01 July 2012 |  | 30 August 2012 |  |  |  |  |  |  |  |  |
| Capacity building of officials on updates of SANS 0241 & related legislations | 01 Sep 2012 |  | 30 Nov 2012 |  |  |  |  |  |  |  |  |

4.1.2. Surveillance & prevention of communicable diseases

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Healthy communities |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| a)Health & hygiene awareness campaigns b) Surveillance & prevention of communicable diseases c) Disposal of the dead/ cremation & exhumation |  | a)Promotion Monitoring and education b) Ensure that communicable diseases within Alfred Nzo are effectively prevented, and even the cross-boundary issues are properly addressed. c) To improve the quality of life of ANDM communities |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Health & hygiene Capacitated communities Surveillance & prevention of comm diseases - No of EPR plans properly co-ordinated - No of assessments & investigations conducted (after receipt of notifications) Disposal of the dead -No of exhumations reported and monitored -No of awarenesses conducted in communities (exhumations) |  | - Reviewed quarterly - 01 July 2012 to 30 June 2013 |  | Communities with healthy lifestyles. |  | -45% of communities capacitated -1 plan available -100% assessments & investigations -100% of exhumations reported & monitored - 0% of awarenesses on exhumations |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | -Review existing EPR plan Phase 1 (stakeholder engagement) on development of EPR plans 6 exhumations awareness -18 wards on H&H awareness | - Phase 2- final (on development of EPRs 4 exhumations awarenesses 18 wards on H&H awarenesses |  | Implementation &Resuscitation 6 exhumations 35 wards on H&H awareness | Implementation 6 31 wards on H&H awareness |
| ERP plans & Reports Developed SOP |  | 01 July 2012 to 30 June 2013 |  | No of cases/ Reduction rate vs reporting rate of communicable diseases. |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Epidemiological surveillance of diseases | 01 July 2012 |  | 30 June 2013 |  | 50,000.00 |  | 100,000.00 | 100,000.00 |  |  | 50,000.00 |  |  |
| DEHIS (District Environmental Health Information Systems) updated & functional | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |

4.1.3  Food Control & Safety

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Healthy communities |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Food Safety & Control |  | To monitor quality of food that reach ANDM consumers To reduce rate of food borne disease outbreaks To fight micro-malnutrition problem through food fortification & salt iodisation To monitor the food quality in ANDM |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |
| Food quality standards maintained . |  | 01 July 2012 to 30 June 2013 |  | Reduced food borne related illnesses No. of food samples taken, analysed & communicated to the relevant stakeholders No. of COAs issued Developed basic SOP |  | 70% trained food handlers (30% not yet covered) 100% of reported foodborne illnesses investigated. 100% of applications received are processed 0% of developed basic SOP |  | 850 food samples taken and analysed/year 2 SOPs developed |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 |  | Q4 |  |
|  |  |  |  |  |  |  |  | 18 wards trained on hygienic food practices 213 food samples taken, analysed & communicated Coordination of development of SOPs | 18 wards trained on hygienic food practices 213 food samples taken & analysed Drafting of SOPs |  | 35 wards trained on hygienic food practices 213 food samples taken & analysed Workshops on SOPs |  | 32 wards trained on hygienic food practices 213 food samples taken & analysed Implementation of SOPs |  |
| Capacitated communities on hygienic food handling practices Compliance with food legislation Grading of businesses in accordance with legislation |  | 01 July 2012 to 30 June 2013 |  | Less incidences of food borne illnesses |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  |  | QUARTER 3 |  | QUARTER 4 |  |  |
| 80% of businesses with CoA | 01 July 2012 |  | 30 June 2013 |  | 100,000.00 |  | 100,000.00 |  |  | 100,000.00 |  | 100,000.00 |  |  |
| 45% of businesses complying with HACCP standards | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |
| 100% of businesses comply with food fortification regulations | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |
| 30% of meat & milk suppliers comply with legislation requirements | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |
| Awareness campaigns to reduce food poisoning effects | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building of all EHPs on food-related issues (including legislation | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |

5.1.4. Waste Management

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Healthy communities |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Waste Management Monitoring | To ensure monitoring of waste management processes To improve the quality of life of ANDM communities. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Minimization of scavenging Improved infection control | Reviewed quarterly |  | Healthy environment |  |  | Established functioning DEMF 2 landfill sites with permits (3 without permits) Established Infection Control Committees 70% of HCRW Generators do not comply with HCRW legislations |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | Awarenesses to the communities around landfill site. Collect data on HCRW Generators |  | Encourage recycling Encourage segregation & proper disposal of HCRW by Private Waste Generators | Awarenesses on waste management Encourage proper disposal by an accredited service provider Monitoring of health care risk waste generators |  | Awarenesses on waste management Monitoring of health care risk waste generators |
| A clean and safe public environment. | 01 July 2012 to 30 June 2013 |  | Healthy environments (ANDM area of jurisdiction) |  |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Identification of high risk sites (Disposal sites) |  | 01 July 2012 |  | 30 June 2013 | 10,000.00 |  | 10,000.00 |  | 10,000.00 |  |  | 10,000.00 |  |
| Implementation of preventative measures (Educate nearby communities) |  | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |

4.1.5. Health surveillance of premises

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Healthy communities |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIOR YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| ANDM buildings complying with all relevant regulations and legislations |  | 01 July 2012 to 30 June 2013 |  | Healthy environment |  | 100 % of building plans submitted are scrutinized 60% of buildings are a health hazard |  | Encourage 4 LMs to demolish all buildings that are posing risk to inhabitants |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | Consistent attendance to building plan scrutinising committee | Consistent attendance to building plan scrutinising committee |  | Consistent attendance to building plan scrutinising committee | Consistent attendance to building plan scrutinising committee |
| Statistics of building plans approved and building inspections conducted |  | 01 July 2012 to 30 June 2013 |  | Buildings that are complying with building legislations |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Evaluation of buildings | 01 July 2012 |  | 30 June 2013 | 100,000.00 | 150,000.00 |  | 100,000.00 |  |  | 100,000.00 |  |  |
| Government premises (including clinics and schools - rural and urban) | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |
| Funeral undertakers that meet regulations | 01 July 2012 |  | 30 June 2013 |  |  |  |  |  |  |  |  |  |

4.2.        I.S.D AND CUSTOMER CARE

4.2.1 Community Mobilization & involvement

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Community mobilization and Involvement | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Information dissemination to communities about planned projects, and provision of detailed implementation plan, through community mobilization. | July 2012 | Informed communities and all relevant stakeholders. Mobilized communities. | 100 new ANDM Projects. | All ANDM projects mobilised by 100 % |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | 25% | 25% | 25% | 25% |
| Minutes of meetings held. Attendance registers of meetings. Weekly, monthly and quarterly reports | June 2013 | Non-financial report | June 2013 |  |  |  |  |
|  |  |  |  | 25 % of new projects |  |  |  |

4.2.2 Awareness campaigns

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Conduct Awareness Campaigns | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Conduct public education workshops Coordinate information sharing days | June 2013 | Informed and aware communities | 150 ANDM Projects | 60% of ANDM Projects |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | 23 | 23 | 23 | 23 |
| Minutes of meetings held. Attendance registers of meetings. Awareness campaign flyers Awareness Reports | June 2013 | Report | June 2013 |  |  |  |  |
|  |  |  |  | Conduct 23 Awareness Campaigns |  |  |  |

4.2.3 Social Crime Prevention Programme

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Social Crime Prevention |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |
| Social Crime Prevention Programme | To promote crime free district through crime awareness programmes |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Coordinate revival of Local Community Safety Forums Coordinate establishment of District Community Safety Forum Coordinate Local and District Community Safety Forums Develop District Safety Plan Conduct crime awareness workshops in all LMs | July 2012 | Reduce crime levels at community level and effective functioning of CSF’S at LM’s | Community Safety Forum Established in 4 Local Municipalities | 80% of awareness campaigns conducted |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 |  | Q4 |  |
| Minutes of the Local and District Community Safety Forum Meetings Attendance Registers Awareness campaign flyers District Safety Plans Awareness Reports 2.4 Community Structures Establishment | June 2013 | Regular Community Safety Meeting Community Safety Plans implemented Reduced Crime level | June 2013 | Revival of Local Community Safety Forums | Develop District Safety Plan | Conduct crime awareness workshops in 10 wards ( two LM’S) |  | Conduct crime awareness workshops in 10 wards ( two LM’S) |  |
|  |  |  |  | establish District Community Safety Forum |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Establishment of community structures | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Conduct stakeholder meetings Democratic election of community structures (PSC, VHW, VWC, CLO, VSC,) | June 2013 | Accountable, Responsible Community Structures, Effective management of projects at a local level | 100 planned projects | 100 Community structures established by June 2013 |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Establish 30 Community Structures | Establish 30 Community Structures | Establish 20 Community Structures | Establish 20 Community Structures |
| Number of established Community Structures. Contact lists and respective portfolios. | June 2013 | Progress Reports | June 2013 |  |  |  |  |

4.2.5 Community Training and Capacity Building

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Training and Capacity Building of Community structures | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Training Material development. Training plan. Conduct trainings | June 2013 | Regular stakeholders meetings. Reduction of site complaints and conflicts. PSC ,VWC,VSC,VHW,CLO,SECURITIES, plans and objectives | 100 planned projects | 100 Community structures trained by June 2013 |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Training of 30 Community Structures | Training of 30 Community Structures | Training of 20 Community Structures | Training of 20 community Structures |
| Training manuals. PSC ,VWC,VSC, site meeting minutes Attendance Registers Skilled Audit Report Training reports | June 2013 | Progress Report | June 2013 |  |  |  |  |

    - Health and Hygiene Promotion

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Health and Hygiene promotion | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Health and hygiene material development. Training Plan Establishment of village health workers Train Health and hygiene village health workers on PHAST Health and hygiene awareness campaigns. | June 2013 | Best sanitation practices. | 100 Planned projects. | 250 village health workers trained by June 2013. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Establish VHW Develop Training plan Develop Training Manual | Health and Hygiene Village Health Worker Training | Health and Hygiene promotion through door to door and awareness campaigns | Health and Hygiene promotion through door to door and awareness campaigns |
| Training manuals. Training attendance registers Certificates of Attendance Number of established VHW List of VHW and contact details Village Health Workers Reports Happy Letters | June 2013 | Report | June 2013 |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager –Community Development Services |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Site handover | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Introduction of service providers. Presentation of project implementation plan. -scope of work -project budget -wage rate -project duration Local Labor Recruitment. Project Program | June 2013 | Service providers on site. Established site office Ownership and understanding of the project. | 100 planned projects. | 100 Sites handed over by June 2013 |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Introduction of services providers to 50 projects | Introduction of services providers to 50 projects | - | - |
| Minutes of site handover meeting. Attendance register of site handover meeting | June 2013 | Report | June 2013 |  |  |  |  |

4.2.8 Site Monitoring

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Site monitoring | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| MEETING; - attend site meetings - attend PSC, VWC, VSC meetings. - attend and facilitate conflict resolution meetings - attend special meetings. Monitor progress on site. -Signed Happy letters (sanitation projects) Monitoring visits to areas where Health and Hygiene is being promoted Develop monitoring and evaluation tool - Checklist / questionnaire | June 2013 | Well attended and regular meetings. Project progress on site. | 100 Planned projects. | 100 sites monitored by June 2013 |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Ongoing | Ongoing | Ongoing | Ongoing |
| Minutes of all project related meetings. Attendance registers of all project related meetings Project progress reports. Non-financial report Happy letters | June 2013 | Report | June 2013 |  |  |  |  |

2.9 Project Handover

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Project handover | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Audit community satisfaction through community meetings. Verify outstanding payments to local labor force. Verify incidents on site Verify rehabilitation of natural resources surrounding construction site. | June 2013 | Satisfied community with final product. | 70 Sanitation projects .ready for handover 30 water projects ready for hand over | 100 projects handed over by June 2013 |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Handing over of 30 sanitation project 10 water projects | Handing over of 10 sanitation project 3 water projects | Handing over of 10 sanitation project 10 water projects | Handing over of 20 sanitation project 7 water projects |
| Hand Over Report | June 2013 | Report | June 2013 |  |  |  |  |

4.2.10 Planned Project Feasibility Studies

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Conduct feasibility studies for planned projects | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Conduct local stakeholder meetings (Cllrs, CDWs, Ward Committees, Traditional Leaders,). Introduction of service provider/s Identify community reps to assist service provider in auditing resources. | July 2013 | Informed communities. Audited community resources. | 100 Planned projects. | Conduct 100 feasibility studies by 2013. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | Facilitate local stakeholder meetings Introduction of service provider/s | Facilitate feasibility study feedbacks Monitor service providers | - | - |
| Feasibility Report. | June 2013 | ISD Business Plans | June 2013 |  |  |  |  |

4.2.11 Conflict Resolution and Development

| NATIONAL KEY PERFORMANCE AREA | Good Governance & Public Participation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Sustainable service delivery and institutional capacity |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr M.Z. Silinga |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |
| Conflict resolution and development | To promote Stakeholder participation and Community ownership of projects |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |
| Conduct relevant stakeholder meetings (Cllrs, CDWs, Ward Committees, Traditional Leaders, etc). Identify the source of the conflict. | July 2013 | Informed communities. Audited community resources. | Planned projects. | all IDMSD planned projects for 2012/2013. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTELY TARGETS |  |  |  |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  | On going | On going | On going | On going |
| Minutes of the conflict resolution meeting Attendance Registers | June 2013 | Progress Report | June 2013 |  |  |  |  |

CUSTOMER CARE ESTABLISHMENT

| NATIONAL KEY PERFORMANCE AREA |  | Good governance |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Crime free Communities in ANDM |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Community Development Services Manager-MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Crime prevention |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| •Number of Safety Forums established and revived •Number of Crime Awareness workshops conducted |  | 31 December 2012 |  | Reduced crime levels |  |  | Crime stats for 2011 |  | -Four (4) Safety Forums (2 Revival and 2 establishment. -Four (4) Awareness Workshops |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | -2 Forums. -2 Workshops | -2 Forums. -2 Workshops |  | 0 | 0 |
| -Acceptance letters of members to serve to the Forum. -Attendance registers |  | 31 December 2012 |  | Quarterly reports on crime statistics |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R100 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Establish Safety Forums in Local Municipalities | 01 July 2012 |  | 30 December 2012 |  | R10 000 | R10 000 |  | Nil |  |  | Nil |  |  |
| Development of District Community Safety Plan | 01 July 2012 |  | 30 August 2012 |  | R30 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Conduct crime awareness workshops | 01 July 2012 |  | 31 December 2012 |  | 25 000.00 | 25 000.00 |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Community Development in ANDM |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Manager: CDS |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| ISD & Customer Care Public Education & Community Awareness Programme |  | To promote maximum stakeholder participation and Community ownership of projects |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -Number of awareness programmes conducted |  | 30 June 2013 |  | Informed and aware communities |  | - |  | 8 awareness Campaigns |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 2 | 2 |  | 2 | 2 |
| Attendance registers of meetings and Awareness Reports |  | 30 June 2013 |  | Community owned and sustainable projects |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R150 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Awareness on Customer Care Call Centre | 01 August 2012 |  | 30 June 2013 |  | R35 000.00 | R35 000.00 | R35 000.00 |  |  | R35 000.00 |  |  |
| Awareness campaigns on Ground Water Protocol | 01 July 2012 |  | 30 August 2012 |  | R10 000.00 | Nil | Nil |  |  | Nil |  |  |
| Conduct Water Use education | 01 July 2012 |  | 31 December 2012 |  | Nil | Nil | Nil |  |  | Nil |  |  |
| Heath & Hygiene Promotion | 01 July 2012 |  | 30 June 2013 |  | Nil | Nil | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promotion of Community Development in ANDM |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Executive Manager: CDS |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Establishment and capacity building of community structures |  | To promote Stakeholder participation ,Community ownership and Sustainability of all ANDM projects |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -Number of Community structures established (PSCs on Water and sanitation Projects) |  | 30 June 2013 |  | -Community driven development initiatives -Sustainable projects |  | -60 Existing PSCs |  | 70 PSC established |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 10 | 25 |  | 25 | 10 |
| List and contact details of members |  | 30 June 2013 |  | Accountability of Community Members (Monthly and Quarterly Reports) |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R400 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Establishment of community structures ( Project Steering Committees) | 01 July 2012 |  | 30 June 2013 |  | R25 000.00 | R25 000.00 | R25 000.00 |  |  | R25 000.00 |  |  |
| Training of PSCs on Committee Skills | 01 July 2012 |  | 30 August 2012 |  | R50 000.00 | R50 000.00 | R50 000.00 |  |  | R50 000.00 |  |  |
| Recruitment and training of Village Health Workers | 01 July 2012 |  | 31 December 2012 |  | R25 000.00 | R25 000.00 | R25 000.00 |  |  | R25 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Effective Customer Care Management in ANDM |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: CDS |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Customer Care Centre establishment | To ensure sound customer relations with all ANDM Customers by 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -Established customer care Centre with fully functional systems and personnel | 30 June 2013 |  |  | Improved relations between ANDM and its customers and community |  | None |  | -One Customer Care Centres Established and functional. -10 Personnel Staff members |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 6 |  | 0 | 4 | 0 |
| -Hand over report by the Service providers -Appointment letters for staff personnel. | 30 June 2013 |  |  | Number of users of the Call Centre (Monthly and Quarterly Reports/ Incidents Register) |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R2 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| - Development of business specifications for Customer Relations Software( Intelligence Voice Recording System-IVR) |  | 01 July 2012 | 30 September 2012 |  | R10 000.00 |  | Nil |  | Nil |  | Nil |  |
| Implementation of Customer Relations Software |  | 01 October 2012 | 31 December 2012 |  | Nil |  | R1 800 000.00 |  | Nil |  | Nil |  |
| Training of staff personnel on System |  | 14 January 2013 | 31 January 2013 |  | Nil |  | Nil |  | R190 000.00 |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Good Governance |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Effective Customer care management in ANDM |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: CDS |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Batho Pele Programme | To ensure sound customer relations with all ANDM Customers by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| -All departments within ANDM have flagship projects on Batho Pele | 30 June 2013 |  |  | Community Satisfaction levels of ANDM services increased |  | Minimal adherence to Batho Pele Principles by ANDM |  | - ANDM Batho Pele Steering Committee established |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | ANDM Batho Pele Steering Committee established |  | Municipal Services Week implemented |  |  |  |
| .-List of ANDM Batho Pele Steering Committee reflective of all ANDM departments -Attendance registers and programmes for Municipal Services Week | 30 June 2013 |  |  | -Number of service delivery complaints reduced |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 100 000 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Establishment of Batho Pele Steering Committee |  | 01 July 2012 | 30 September 2012 |  | R 20 000 |  |  |  |  |  |  |  |  |
| Implementation of the Municipal Services Week |  | 01 September 2012 | 30 December 2012 |  |  |  | R 8 0 000 |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance & Public Participation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Effective customer care management in ANDM |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Mr. M.Z. Silinga |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Customer Care Centre marketing |  | Ensure sound customer relations |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -ANDM Customer Care Centre Advertised and Publicized regularly on local media and local radio stations -Launch of the Customer Care Centre |  | July 2013 |  | Call Centre Customer Care services known to all ANDM Customers. |  | 900 491 total ANDM population |  | 80% of ANDM Customers informed about and having access to ANDM Call Centre (720 393 people). |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | - MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
| -Newspaper articles, Slots on local radio stations -Attendance registers of launch attendance |  | June 2013 |  | - Increased number of call user |  | June 2013Secure |  | Radio slots secured brochures and flyers developed | Customer Care Centre launched |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  | QUARTER 4 |  |  |
| - Coordinate publicity of the Call Centre line through community radios, flyers, media and stakeholder engagement meetings | 01 July 2012 |  | 30 June 2013 |  | R 10 000 |  | R 10 000 | R 20 000 |  | R 10 000 |  |  |
| Launching of the Call Centre line | 01 July 2012 |  | 30 Sept 2013 |  |  |  | R 300 0000 |  |  |  |  |  |

4.3 DISASTER RISK MANAGEMENT

4.3.1 Disaster Management Capacity Building

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promotion of Disaster Management Capacity Building in ANDM |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Mr. Banzi Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Disaster Management Capacity Building |  | Promote a culture of risk avoidance among stakeholders by capacitating all role players |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of people trained on disaster risk management |  | 30 June 2013 |  | Improved level of understanding of people in terms of their roles and responsibilities in disaster risk management |  |  | New |  | - 1030 trainees |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 150 | 400 |  | 400 | 80 |
| Attendance Register/Certificates of attendance or of completion |  | 30 June 2013 |  | Number of reported incidents and level of participation in disaster management activities |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R400.000.00 |  | VOTE NUMBER |  |  | 16 0044 030 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Terms of reference drafting | 01/07/2012 |  | 14/07/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Procurement process | 15/07/2012 |  | 15/08/2012 |  | R10 000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Trainning of ward committies and officials | 20/08/2012 |  | 30/05/2013 |  | R 50,000.00 | R 150,000.00 |  | R 150,000.00 |  |  | R 40,000.00 |  |  |
| Project completion & final report compilation | 01/06/2013 |  | 15/06/2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |

4.3.2 Disaster Management Policy Framework

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Establishment of integrated institutional policy Framework for Disaster Management |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Mr. Banzi Silinga |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Disaster Management Policy Framework Development | Establish integrated institutional capacity within the ADNM to enable the effective implementation of disaster risk policy and legislation |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Adopted and revied disaster management policy framework | 30 June 2013 |  | Guideline for the implementing disaster management in ANDM |  | Disaster Management Policy Framework 2010 |  | Disaster Management Policy Framework Development (1) |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  | - | Situational analysis Report | Strategy formulation |  | Draft Frwamework Plan and adoption |
| Council Resolution | 30 June 2013 |  | Implementation framework plan incorporated in IDP and budget |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R600.000.00 |  | VOTE NUMBER |  | 16 0044 271 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Terms of reference drafting | 01/07/2012 | 14/07/2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Procurement process | 15/07/2012 | 15/08/2012 |  | R10 000.00 |  | Nil | Nil |  |  | Nil |  |
| Conduct Sitiuational analysis | 01/10/201 | 31/12/2012 |  |  |  | R 250,000.00 | R 150,000.00 |  |  | Nil |  |
| Development of Strategy plan and First Draft Framework plan | 15/01/2013 | 31/03/2013 |  | Nil |  | Nil | Nil |  |  | R 190,000.00 |  |
| Adoption of Framework Plan | 01/04/2013 | 31/05/2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |

4.3.3 Integrated Response and Recovery

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promote Integrated Response & Recovery |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Mr. Banzi Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Disaster Management integrated response and recovery |  | Ensure effective and appropriate disaster response and recovery by - Implementing uniform approach to the dissemination of disaster management information - reduce the potential impact in respect of personal injury , health, loss of life , property, infrastructure ,environment and government services - implementing immediate integrated response and relief measures when significant events or disasters occur or threatening to occur - implementing all rehabilitation strategies following a disaster in an integrated and developmental manner. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of incidents responded to and the number of people assisted |  | End June 2013 |  | Minimize impact of disaster to communities |  |  | 50 households assisted 50 homeless households |  | Improved response mechanism and minimize impact of disasters to communities. 4 Local Municipalities based Response teams establishment |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 4 Ward Based Response Teams establishment | Coducting 4 awareness programme. |  | Verification of homeless households and strategy development. | Implementation of Strategy |
| Reports on disaster incidents |  | 30 December 2012 |  | Reduced number of vulnerable and homeless households |  |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R2 000.000.00 |  | VOTE NUMBER |  |  | 16 0044 273 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Coordinate meetings with LM,s | 01/07/2012 |  | 31/08/2012 |  | 200.000.00 | Nil |  | Nil |  |  | Nil |  |  |
| Procurement of community awareness material and conduct awareness programme | 01/08/2012 |  | 31/12/2012 |  |  | R400.000.00 |  | Nil |  |  | Nil |  |  |
| Disaster reconstruction & repairs | 01/01/2013 |  | 31/06/2013 |  | Nil | Nil |  | R 1,400.000.00 |  |  | Nil |  |  |

4.4. SPORT, ARTS, CULTURE, RECREATION, HERITAGE & LIBRARIES

4.4.1 Sports and Recreation

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Promotion and development of cultural programs and industries |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Development of Sport and Recreational program | - To have four sport complex established by 2017 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Number of sport and recreational programmes implemented Amount of funding for establishment of sport facilities secured | 30 June 2013 | Improved healthy life style Reduced high level of alcohol and drug abuse |  | Participated in provincial SALGA games 2011 |  |  | All four local municipalities should have received funding for the development of sport complexes Four sporting code programmes |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 |  | Q4 |
|  |  |  |  |  |  |  | -Two business plans -Two Sports programmes | -Two business plans -One Sport programme |  | Signing of memorandum of understanding -One Sport programme |  | Initiating construction -One Sport programme |
| Reports, Attendance registers, Signed funding agreements | 30 June 2013 | Crime statistics |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1 000 000.00 |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  |  | QUARTER 3 |  | QUARTER 4 |  |
| Participate in District, Province, National and International games | 01 July 2012 |  | 30 June 2013 |  | R200 000.00 | R50 000.00 |  |  | R50 000.00 |  | R50 000.00 |  |
| Policy development | 01 July 2012 |  | 30 September 2012 |  | R150 000.00 | R0 |  |  | R0 |  | R0 |  |
| Development of four business plan for finding applications | 01 July 2012 |  | 30 September 2012 |  | R0 | R0 |  |  |  |  |  |  |
| Alfred Nzo Mayoral Cup | 01 July 2012 |  | 30 September 2012 |  | R100 000.00 | R0 |  |  | R0 |  | R0 |  |
| Conducting Sport Indaba & Workshops | 01 July 2012 |  | 30 June 2013 |  | R0 | R100 000.00 |  |  | R0 |  | R0 |  |
| Purchasing of sport equipment | 01 July 2012 |  | 30 June 2013 |  | R0 | R0 |  |  | R100 000.00 |  |  |  |
| Facilitate operation of leagues | 01 July 2012 |  | 30 June 2013 |  | R0 | R0 |  |  | R0 |  | R100 000.00 |  |
| Facilitation of horse racing | 01 July 2012 |  | 30 June 2013 |  | R0 | R0 |  |  | R0 |  | R100 000.00 |  |

4.4.2  Arts and Culture

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Promotion and development of cultural programs and industries |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Development of Arts and Culture | - To have established four cultural centres by 2017 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Facilitate promotion of performance arts Facilitate promotion of cultural activities Hosting of cultural festivals with the sole aim of financial boost to the local artists Facilitation of the development of art galleries and cultural centres for exhibitions and market Facilitation of the establishment of theatre and performing centres, art centres and craft hubs | 01 July 2012 to 30 June 2013 |  | Improved arts and culture production |  |  | Cultural festival held in 2011 |  | All four local municipalities should have received funding for the establishment of cultural centres. Three Arts and Culture programmes |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | Two business plans Auditions for Film making Cultural festival |  | Two business plans Film making | Signing of memorandum of understanding | Initiating construction |
| Reports, attendance registers Developed film maker Signed funding agreements | 01 July 2012 to 30 June 2013 |  | Number of films, art work produced |  |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1 000 000.00 |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Film skills and art development |  | 01 July 2012 |  | 30 October 2012 | R350 000.00 |  | R0 |  | R0 |  | R0 |  |
| Policy development |  | 01 July 2012 |  | 30 September 2012 | R150 000.00 |  | R0 |  | R0 |  | R0 |  |
| Development of four business plan for funding application |  | 01 July 2012 |  | 30 September 2012 | R0 |  | R0 |  | R0 |  | R0 |  |
| Cultural festivals |  | 01 September 2012 |  | 30 September 2012 | R0 |  | R400 000.00 |  | R0 |  | R0 |  |
| Awareness on promoting art & culture |  | 01 July 2012 |  | 30 June 2013 | R0 |  | R0 |  | R50 000.00 |  | R0 |  |
| Arts and Culture summit |  | 01 February 2013 |  | 30 June 2013 | R0 |  | R0 |  | R0 |  | R50 000.00 |  |

4.4.3 Heritage and Museum

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Promotion and development of cultural programs and industries |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of Heritage routes and Museum | - To develop, protect and promote heritage site by 2016 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Development of Heritage routes Research heritage sites and activities Development of grave of the fallen heroes Identification, commemoration and memorialization of National and Local heroes Identification and development of heritage sites (including Mowa turmoil) Identification of the graves of the fallen heroes | 01 July 2012 to 30 June 2013 |  | Developed heritage, sites and museum |  |  | Two existing monument, one in Matatiele and one in Mbizana |  | Documented heritage route and museum |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | Research and development |  | Research and development |  | Initiate construction of heritage site | Initiating construction of heritage sites |
| Reports Council resolution Developed Heritage routes | 01 July 2012 to 30 June 2013 |  | Reports Developed Heritage routes |  |  | 01 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R600 000.00 |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |  |
| Research on Mowa turmoil |  | 01 July 2012 |  | 30 September 2012 | R50 000.00 |  | R0 |  | R0 |  | R0 |  |  |
| Policy development |  | 01 July 2012 |  | 30 September 2012 | R150 000.00 |  | R0 |  | R0 |  | R0 |  |  |
| O.R. Tambo Legacy program |  | 01 July 2012 |  | 31 October 2012 | R0 |  | R150 000.00 |  | R0 |  | R0 |  |  |
| Development of heritage routes |  | 01 July 2012 |  | 30 June 2013 | R0 |  | R0 |  | R50 000.00 |  | R0 |  |  |
| Alfred Nzo memorial lecture |  | 01 June 2013 |  | 30 June 2013 | R0 |  | R0 |  | R0 |  | R200 000.00 |  |  |

4.5 THUSONG CENTRE

| NATIONAL KEY PERFORMANCE AREA | Good governance and public participation |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Integrated service delivery |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |
| Thusong Service centres | - promoting access to government services and information |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE | OUTCOMES KEY PERFORMANCE INDICATORS | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Increase the number of servicing centres from 1 to 8 | 30 June 2013 | Improved complete service delivery comprehensive ) | 01 service centre i.e. KwaNophoyi | Improved integrated service closer to communities |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE | MEANS OF VERIFICATION (OUTCOMES KPI) | TARGET DATE | QUARTERLY TARGETS |  |  |  |  |  |
|  |  |  |  | Q1 | Q2 |  | Q3 |  | Q4 |
|  |  |  |  | Thusong Service centre mobile service outreach to Mbizana cluster 01, Matatiele cluster 01, Ntabankulu cluster 01, Mzimvubu cluster 01 | Thusong Service centre mobile service outreach to Mbizana cluster 02, Matatiele cluster 02, Ntabankulu cluster 02, Mzimvubu cluster 02 |  | Thusong Service centre mobile service outreach to Mbizana cluster 01, Matatiele cluster 01, Ntabankulu cluster 01, Mzimvubu cluster 01 |  | Thusong Service centre mobile service outreach to Mbizana cluster 02, Matatiele cluster 02, Ntabankulu cluster 02, Mzimvubu cluster 02 |
| - Monthly reports - Quarterly reports | 30 June 2013 | Improved, integrate government services into primarily rural communities | 30 June 2013 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 | QUARTER 4 |
| Thusong Service centre mobile service outreach to 8 centres i.e. 2 per local municipality | 01 July 2012 | 30 June 2013 |  | R125 000 |  | R125 000 |  | R125 000 | R125 000 |

- FIRE AND RESCUE SERVICES

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Promote sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Fire and Rescue Service Vehicles | To promote fire safety and fire fighting to ensure sustainable fire safe environment through service delivery by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Number of Fire and Rescue vehicles procured and incorporated on the Municipal Assets Register | 30 June 2013 |  |  | Effective and efficient fire and rescue services |  | No skid unit for Mt. Ayliff, and no Fire Engine for Ntabankulu. |  | 4 Vehicles (1 Fire Engine, 1 Fire Tanker, 1 Skid Unit and 1 Rescue Vehicle) |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | 0 |  | 0 | 2 (Fire Rescue Vehicle and Skid Unit) |  | 2 (Fire Engine and Fire Tanker |
| Delivery Letters and Assets Register | 30 June 2013 |  |  | Reduced number of fatalities due to immediate response (Quartely Reports) |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 5 500 000,00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Procurement Process |  | 01/07/2012 | 30/08/2012 |  | R20 000.00 |  | Nil |  | Nil |  |  | Nil |  |
| Production phase (Service Provider) |  | 01/09/2012 | 15/03/2013 |  | R2 000 000.00 |  | R2 000 000.00 |  | R1 000 000.00 |  |  | Nil |  |
| Delivery of Vehicles (Fire Recue vehicle and Skid Unit) |  | 15/03/2013 | 30/03/2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Delivery of Fire Engine and Fire tanker |  | 01/06/2013 | 15/06/2013 |  | Nil |  | Nil |  | Nil |  |  | R480 000.00 |  |

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promote sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Training Center establishment – Mount Frere |  | To promote fire safety and fire fighting to ensure sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Adopted Feasibility Study Report |  | 31 December 2012 |  |  | Recommended projects by the Study incorporated in the 2013/14 IDP and budgeted for. |  | None |  | Approved Training Centre Establishment Feasibilty Study Report |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 1 Feasibility Study Report |  | 0 | 0 |
| Council Resolution |  | 31 December 2012 |  |  | IDP and Budget 2013/14 |  | 29 March 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Procurement Processes | 01/07/2012 |  | 30/09/2012 | R20 000.00 |  | Nil |  | Nil |  |  | Nil |  |  |
| Feasibility Study | 01/10/2012 |  | 30/11/2012 | Nil |  | R48 000.00 |  | Nil |  |  | Nil |  |  |
| Approval of the Report | Nil |  | Nil | Nil |  | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promote sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate the recruitment and support to key Fire & Rescue Service objective (Job Creation) |  | - To promote fire safety and fire fighting to ensure sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of staff personnel to improved fire safety and firefighting program recruited |  | 30/06/2013 |  | Improved services delivery through enhanced shift strength |  |  | Inadequate staff members per shift |  | 20 Staff personnel |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 0 | 20 |  | 0 | 0 |
| Signed Employment Contracts |  | 30/06/2013 |  | Shift Rooster |  |  | 30/06/2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Document production and submission for approval | 01/10/2012 |  | 30/10/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Recruitment | 01/11/2012 |  | 30/11/2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Maintenance of Shift Strength | 01/12/2012 |  | 30/06/2012 |  |  |  |  | R250 000,00 |  |  | R 250 000,00 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Promote sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Fire Safety Plan and Launch of Public Information Education and Relations (P.I.E.R.) program. | To promote fire safety and fire fighting to ensure sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Developped and approved fire safety plan Number of awareness campaigns conducted | 31/12/2012 29/03/2013 |  |  | Informed communities and improved enforcement of by laws |  | None |  | Approved Fire Safety Plan 40 awareness campaigns |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 1 fire safety plan |  | 20 awareness campaigns | 20 awareness campaigns |
| Council resolution Attendance registers | 31/12/2012 29/03/2013 |  |  | Attendance register for consultation Date and program for the launch |  | 30/06/2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 550 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Completion and approval of the Fire Safety Plan |  | 01/07/2012 | 31/12/2012 |  | Nil | R 250 000.00 | Nil |  |  | Nil |  |  |
| Awareness Campaigns |  | 15/10/2012 | 31/01/2013 |  | Nil | Nil | R 150 000.00 |  |  | Nil |  |  |
| Awareness campaigns |  | 01/02/2013 | 31/03/2013 |  | Nil | Nil | Nil |  |  | R 150 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Basic Service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Promote sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | MZ Silinga |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Strengthening of Control Center |  | To promote fire safety and fire fighting to ensure sustainable fire safe environment through service delivery |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Incident Management System installed |  | 30/06/2013 |  |  | Improved response time and statistics |  | No incident reporting system No radio communication system |  | Incident system installed |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | Nil | 1 system installed |  | Nil | Nil |
| Signed off report and maintenance plan |  | 30/06/2013 |  |  | Incident reports |  | 30/06/2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 950 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Procurement documents | 01/07/2012 |  | 31/07/2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Installation of the system | 15/08/2012 |  | 31/12/2012 | R 175 000,00 |  | R 450 000,00 |  | Nil |  |  | Nil |  |  |
| Staff training | 02/01/2013 |  | 31/01/2013 | Nil |  | Nil |  | R 75 000,00 |  |  |  |  |  |
| Project handover | 15/02/2013 |  | 15/03/2013 | Nil |  | Nil |  | Nil |  |  | R 250 000,00 |  |  |

5.	CORPORATE SERVICES

5.1 HUMAN RESOURCES MANAGEMENT

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Performance Management system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual Performance Management | - To implement the PMS across the institution - Cascading PMS to lower levels - Quarterly reviews and PMS reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |
| Number of performance agreements and promises signed by senior managers and lower level employees. | 1st, 2nd and 3rd quarter then Annually |  | Achieving IDP targets. |  |  |  | The budget set aside for skills programmes wasn’t utilized completely |  |  | Signed performance agreements and 4 performance assessments |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 |  | Q2 |  |  | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  |  |  | Signed contract and 1st assessment |  | 2nd assessment |  |  | 3rd assessment |  | 4th assessment |
| Monthly, quarterly and annual report. Audit report. | July 2012 – June 2013 |  | Monthly/ Progress reports and performance audit reports |  |  |  | On going |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R500 000 |  | VOTE NUMBER |  |  |  | V7 |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  |  | END DATE |  | QUARTER 1 |  |  | QUARTER 2 |  | QUARTER 3 |  |  |  | QUARTER 4 |  |  |
| PMS Policy and framework Workshop for all staff. | 01 July 2012 |  |  | 30 September 2012 |  | R150 000 |  |  | Nil |  | Nil |  |  |  | Nil |  |  |
| Section 57 Performance Agreements/Plans | 01 July 2012 |  |  | 30 June 2013 |  | Nil |  |  | Nil |  | Nil |  |  |  | Nil |  |  |
| All employees performance Plans | 01 July 2012 |  |  | 30 June 2013 |  | Nil |  |  | Nil |  | Nil |  |  |  | Nil |  |  |
| Performance assessments | 30 Sept 2012 |  |  | 30 June 2013 |  | 50 000 |  |  | 50 000 |  | 50 000 |  |  |  | 50 000 |  |  |
| Performance review evaluation | 01 July 2012 |  |  | 30 June 2013 |  | Nil |  |  | Nil |  | Nil |  |  |  | 150 000 |  |  |
| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA | Organisational development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of Organogram for 2013/2014 | - To have a 5 year organisational structure that is aligned with the IDP - To review and align an organizational structure - Organisational structure be adopted by Council - Productive workforce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |
| Council adopted organizational structure and recruitment plan | 1st, 2nd and 3rd quarter then Annually |  | Achieving IDP targets |  |  |  |  |  |  | Adopted structure and completed JD’s |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Q1 |  |  | Q2 | Q3 |  | Q4 |  |
|  |  |  |  |  |  |  |  |  |  | Adopted policy. Complition of JD’s for all vacant posts |  |  |  | Manco presentation |  | Council adoption |  |
| Evaluation by Office of the Premier OD section | September 2009 |  | AG report Improved HR and labour relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | 400 000 |  | VOTE NUMBER |  |  |  | V7 |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  |  | QUARTER 1 |  |  | QUARTER 2 |  |  | QUARTER 3 |  |  |  | QUARTER 4 |  |  |
| Development of the organizational structure policy | 01 July 2012 | 30 July 2012 |  |  | 100 000 |  |  | Nil |  |  | Nil |  |  |  | Nil |  |  |
| Adoption of the policy by Council | 01 Sept 2012 | 31 Sept 2012 |  |  | Nil |  |  | Nil |  |  | Nil |  |  |  | Nil |  |  |
| Data collection for organizational structure review | 01 May 2013 | 30 May 2013 |  |  | Nil |  |  | Nil |  |  | Nil |  |  |  | 50 000 |  |  |
| Presentation of the structure to Manco, LLF and Council | 15 May 2013 | 20 May 2013 |  |  | Nil |  |  | Nil |  |  | Nil |  |  |  | 100 000 |  |  |
| Adoption by LLF and council | 01 June 2013 | 31 July 2014 |  |  | Nil |  |  | Nil |  |  | Nil |  |  |  | Nil |  |  |
| Development of Job description for new posts as per the organogram | 01 July 2013 | 31 June 2014 |  |  | 50 000 |  |  | 50 000 |  |  | 50 000 |  |  |  | 50 000 |  |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Employee Wellness Program |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Employee Wellness Program | - To have a fully established EAP unit by 2013 - Sound Labour Relations - Employee Assistance - Employment of staff - Development of the EAP strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Well established and functional unit | 1st, 2nd and 3rd quarter then Annually |  | Achieving IDP targets |  |  |  |  | Employee assistance strategy and plan |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | Employment of staff. |  | EAP strategy and wellness intervention. | Wellness intervention |  |  |
| Evaluation by the Employee Assistance Programme Association | Quarterly |  | Productive employees |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1 950 000 |  | VOTE NUMBER |  |  | V7 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Employment of the EAP official |  | 01 July 2012 |  | 30 July 2012 | Nil-Personnel budget |  | Nil |  | Nil |  |  | Nil |  |
| Development of the EAP strategy |  | 01Sept 2012 |  | 30 Sept 2012 | 200 000 |  | Nil |  | Nil |  |  | Nil |  |
| Sourcing Service Providers for Employee Assistance Program |  | 01 Oct 2012 |  | 30 Oct 2012 | R50 000 |  | R50 000 |  | R100 000 |  |  | R50 000 |  |
| Preparation for bi/ annual wellness day |  | 01 January 2013 |  | 30 June 2013 | Nil |  | R50 000 |  | R50 000 |  |  | Nil |  |
| Sourcing service providers for the procurement of Protective clothing |  | 01 January 2013 |  | 30 January 2013 | Nil |  | R100 000 |  | Nil |  |  | Nil |  |
| Sourcing service providers for the procurement of first aid material |  | 01 January 2013 |  | 30 January 2013 | R10 000 |  | R20 000 |  | R20 000 |  |  | Nil |  |
| Up to date COIDA payments and adherence to payment arrangements |  | 01 July 2012 |  | 30 June 2013 | R400 000 |  | R400 000 |  | R250 000 |  |  | R200 000 |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Labour Relations |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Labour relations | - To have a fully established labour relations unit by 2013 - Sound Labour Relations - Employment of staff - Development of the HR policies and procedures |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Well established and functional unit | 1st, 2nd and 3rd quarter then Annually |  |  | Achieving IDP targets |  | Productive employees |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
| Evaluation by the Employee Assistance Programme Association | Quarterly |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R500 000 |  |  | VOTE NUMBER |  | V7 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Employment of the Labour relations official |  | 01 July 2012 | 30 August 2012 |  | Nil-Personnel budget |  | Nil |  | Nil |  |  | Nil |  |
| Development and review of HR policies and procedures |  | 01Sept 2012 | 30 Sept 2012 |  | 50 000 |  | Nil |  | 50 000 |  |  | Nil |  |
| Review of organizational policies |  | 01 May 2013 | 30 June 2013 |  | Nil |  | Nil |  | Nil |  |  | R400 000 |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Employment Equity |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Employment Equity | - To ensure representation of previously disadvantaged groups in all occupational categories by 2015. - Proper implementation of the EE plan |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Review and adoption of the EE plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
| Evaluation by Auditor General |  |  |  | Reduced exception by AG |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R200 000 |  |  | VOTE NUMBER |  | V7 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Re-establishment of the EE committee |  | 01 July 2012 | 15 July 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Workshop of the EE committee |  | 15 July 2012 | 30 July 2012 |  | R50 000 |  | Nil |  | Nil |  |  | Nil |  |
| Review of the EE plan and policy |  | 01 August 2012 | 30 Sept 2012 |  | R100 000 |  | Nil |  | Nil |  |  | Nil |  |
| Adoption of the EE plan and policy |  | 30 Sept 2012 | 15 October 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Communication of the plan and policy to staff. |  | 15 October 2012 | 30 October 2012 |  | Nil |  | R50 000 |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Staff Retention |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Retention and Career pathing | - To have a well-motivated staff - To retain good caliber employees |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Council adopted plan | 1 July 2012 to 30 June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
| Council resolution | 1 July 2009 to 30 June 2010 |  |  | Satisfaction surveys |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R100 000 |  |  | VOTE NUMBER |  | V7 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Establish the retention committee |  | 1 July 2012 | 30 July 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Development of the retention plan, policy and strategy |  | 1 July 2012 | 30 Sept 2012- |  | 80 000 |  | Nil |  | Nil |  |  | Nil |  |
| Adoption of the EE plan and policy |  | 30 Sept 2012 | 15 October 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Communication of the plan and policy to staff. |  | 15 October 2012 | 30 October 2012 |  | Nil |  | R20 000 |  | Nil |  |  | Nil |  |

5.2 HUMAN RESOURCES DEVELOPMENT UNIT

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Skills programme | - To have a centralized training unit by 2013; - To revive the training committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |  |  |
| Training of municipal employees; Training of councillors | July 2012 – June 2013 |  |  |  |  | Improved Service Delivery as a result of productive and knowledgeable employees/ councillors |  |  |  |  | The budget set aside for skills programmes wasn’t utilized completely |  |  |  | At least 80% of the budget to be utilised |  |  |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  | Q3 |  |  |  | Q4 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training |  |  |  | Training |  | Training |  |  |  | Training |  |  |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  |  |  |  | Attendance register for programmes attended, payment vouchers to providers |  |  |  |  | Quarterly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  |  | TIMEFRAMES |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | START DATE |  |  |  | END DATE |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  |  | QUARTER 4 |  |  |  |
| Ensure regular sitting of the training committee |  |  |  | 1st July 2012 |  |  |  | 30th June 2013 |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  |  | Nil |  |  |  |
| Development of the training implementation plan |  |  |  | 1st July 2012 |  |  |  | 30th September 2012 |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  |  | Nil |  |  |  |
| Conduct skills audits for all employees and councillors |  |  |  | 1st March 2013 |  |  |  | 31st May 2013 |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  |  | Nil |  |  |  |
| Preparation and submission of the workplace skills plan to the LGSeta |  |  |  | 1st April 2013 |  |  |  | 30th June 2013 |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  |  | Nil |  |  |  |
| Approval of the workplace skills plan by the training committee and Council |  |  |  | 1st May 2013 |  |  |  | 30th June 2013 |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  |  | Nil |  |  |  |
| Actual rolling out of training programmes |  |  |  | 1st July 2012 |  |  |  | 30th June 2013 |  | R625 000,00 |  |  |  | R625 000,00 |  |  |  | R625 000,00 |  |  |  |  |  | R625 000,00 |  |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Internship Programme |  | - To have a centralized training unit by 2013; - To revive the training committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |  |  |  |  |  |  |
| Placing of graduates into a work environment in giving them work exposure |  | July 2012 – June 2013 |  |  |  |  | Increased pool of employees with necessary expertise |  |  |  |  | Interns were taken for the financial year as provided for in the budget |  |  |  | Yearly |  |  |  |  |  |  |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 |  |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Internship |  |  |  | Internship |  |  | Internship |  |  | Internship |  |
| Monthly, quarterly and annual training report (ATR) |  | July 2012 – June 2013 |  |  |  |  | -Number of interns placed per department/ unit; -Percentage of interns that get to be absorbed within the municipality |  |  |  |  | Quarterly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  |  | TIMEFRAMES |  |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | START DATE |  | END DATE |  |  |  | QUARTER 1 |  |  |  | QUARTER 2 |  |  |  | QUARTER 3 |  |  |  |  | QUARTER 4 |  |  |  |  |  |
| Development and review of internship policy |  |  | 1st July 2012 |  | 30th June 2013 |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  | Nil |  |  |  |  |  |
| Preparation of yearly adverts targeting graduates with tertiary qualifications |  |  | 1st July 2012 |  | 30th June 2013 |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  | Nil |  |  |  |  |  |
| Shortlisting of graduates with different tertiary qualifications |  |  | 1st July 2012 |  | 30th June 2013 |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  | Nil |  |  |  |  |  |
| Entering into contract agreements with successful graduates |  |  | 1st July 2011 |  | 30th June 2012 |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil |  |  |  |  | Nil |  |  |  |  |  |
| Regular payment of interns placed with different municipal departments |  |  | 1st July 2012 |  | 30th June 2013 |  |  |  | R150 000,00 |  |  |  | R150 000,00 |  |  |  | R150 000,00 |  |  |  |  | R150 000,00 |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| In-service training programme | - To have a centralized training unit by 2013; - To revive the training committee |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Help students gain in-service training in order to complete formal qualifications | July 2012 – June 2013 |  | Reduce delays in the completion of tertiary studies by giving deserving students essential in-service training |  | No interns came forward seeking placement |  |  | Yearly |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | In-service training |  | In-service training | In-service training |  | In-service training |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  | -Requests from students for experiential learning; -Vouchers for stipends paid to in-service trainees |  | Quarterly |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Development and regular review of in-service training policy |  | 1st July 2012 |  | 30th June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |
| Placement of students in in-service training programme |  | 1st July 2012 |  | 30th June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |
| Drawing up of contract agreements for students accepted into the municipality’s in-service training programme |  | 1st July 2012 |  | 30th June 2013 |  | Nil | Nil |  | Nil |  |  | Nil |  |
| Regular payment of allowances/ stipends to in-service trainees |  | 1st July 2012 |  | 30th June 2013 |  | R12 500,00 | R12 500,00 |  | R12 500,00 |  |  | R12 500,00 |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Study Assistance Programme | - To have a centralized training unit by 2013; - To revive the training committee |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Put into place strategies aimed at helping employees upward labour mobility and address career pathing | July 2012 – June 2013 |  |  | Improved Service Delivery as a result of productive and knowledgeable employees/ councillors |  | A small percentage of the budget was utilized for the programme |  | Yearly |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | Study assistance |  | Study assistance | Study assistance | Study assistance |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  |  | -Applications received and processed for study assistance; -Payments made in respect of employees/ councillors participating in the programme |  | Twice a year |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Issuing out of notices calling on interested and qualifying employees/ councillors to participate in the study assistance scheme |  | 1st December 2012 | 31st March 2013 |  | Nil |  | Nil |  | Nil |  | Nil |  |
| Make requisitions and payments on behalf of the employees/ councillors approved for study assistance scheme |  | 1st January 2013 | 31st March 2013 |  | Nil |  | Nil |  | R150 000,00 |  | Nil |  |
| Make employees/ councillors taking part in the study assistance scheme produce results after sitting for exams |  | 1st July 2012 | 30th June 2013 |  | Nil |  | Nil |  | Nil |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Induction Programme | - To have a structured induction and orientation programme by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Help create a pleasant impression about the municipality to the new employees | July 2012 – June 2013 |  | Improved Service Delivery as a result of productive and knowledgeable employees/ councillors |  |  | No induction session was possible for the year |  | Quarterly |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | Induction |  | Induction | Induction |  | Induction |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  | -Memos/ invites into the induction session; -Attendance registers for the induction; -Induction packs to be given to inductees |  |  | Quarterly |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Development of induction packs with critical ANDM policies and relevant information |  | 1st June 2012 |  | 31st July 2012 | R50 000,00 |  | Nil |  | Nil |  |  | Nil |  |
| Obtain lists of new employees from Human Resource Management unit |  | 1st July 2012 |  | 30th June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Invite new employees into a formal induction session |  | 1st July 2012 |  | 30th June 2013 | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Convene induction programmes |  | 1st July 2012 |  | 30th June 2013 | R25 000,00 |  | R25 000,00 |  | R25 000,00 |  |  | R25 000,00 |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| External Bursary Scheme | - To provide financial assistance academically deserving and needy students to pursue tertiary education |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Support of academically deserving and needy children towards enrolment with tertiary institutions | July 2012 – June 2013 |  |  | Increase in the pool of potential with critical and scarce skills |  | The programme will be rolled out for the first time |  | Yearly |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | Nil |  | Nil | Bursary scheme | Nil |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  |  | -Guidelines developed for the selection of deserving students; -Payments made to tertiary institutions on behalf of accepted students; -Advert(s) made calling for deserving students to apply |  | Yearly |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Development of guidelines informing the criterion for selection of potential beneficiaries to the programme and application forms |  | 1st July 2012 | 30th September 2012 |  | Nil |  | Nil |  | Nil |  | Nil |  |
| Preparation and issuing out of notices calling for academically deserving and needy children to enrol with tertiary institutions |  | 1st October 2012 | 31st January 2013 |  | Nil |  | Nil |  | Nil |  | Nil |  |
| Processing of payments for chosen children taking part in the external bursary scheme or writing of letters to the academic institutions confirming their studies are sponsored |  | 1st December 2012 | 31st March 2013 |  | R150 000,00 |  | Nil |  | Nil |  | Nil |  |
| Ensure that children taking part in the external bursary scheme produce academic results after writing exams |  | 1st May 2013 | 31st December 2013 |  | Nil |  | Nil |  | Nil |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Executive Manager: Corporate Services/ Manager: Human Resource Development |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsistence and Travelling (Training & Development) | - To introduce necessary controls for the effective management of subsistence and travelling of employees/ councillors participating in various training and development programmes |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Effective management of the subsistence and travel so that it helps continuous training and development of employees and councillors guided by the ANDM S&T policy | July 2012 – June 2013 |  |  | Reduction in the costs relating to training and development |  | A minimal budget was set aside for the purpose of providing for subsistence and travel arising from training |  | Quarterly |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | S & T arising from training done by HRD |  | S& T arising from training done by HRD | S& T arising from training done by HRD |  | S& T arising from training done by HRD |
| Monthly, quarterly and annual training report (ATR) | July 2012 – June 2013 |  |  | -Regular reports on the bookings done by the HRD unit for employees/ councillors taking part in different training and development programmes |  | Yearly |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Centralised bookings by the HRD unit for all training and development programmes |  | 1st July 2012 | 30th June 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Regular preparation of reports showing bookings done by the unit in respect of employees and councillors taking part in training and development programmes |  | 1st July 2012 | 30th June 2013 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Payment of subsistence and travel expenses to employees/ councillors hotel accommodation, transport (flights and road transport) |  | 1st July 2012 | 30th June 2013 |  | R150 000,00 |  | R150 000,00 |  | R150 000,00 |  |  | R150 000,00 |  |

5.3 INFORMATION AND COMMUNICATIONS TECHNOLOGY

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Establishment of DMZ |  | To establish an IT platform to share information and technology resources with authorised stakeholders |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Demilitazised Zone |  | 30 September 2012 |  |  | To create a secured platform for sharing of information resources |  | None |  | DMZ |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | Design and implement DMZ platform |  |  |  |  |
| Project closeout report indicating completion of the project – with no exceptions |  | 30 September 2012 |  |  | Project Closeout Report |  | 30 September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 100 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Design and implement DMZ platform | 1 July 2012 |  | 30 September 2012 | R 100,000 |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Cabling of new offices |  | To ensure that that all users have network connectivity that meets minimum networking standards |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Networked offices |  | 31 December 2012 |  | All offices have network access points |  | Current offices with network access – there are planned office changes |  | Networked offices |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q1 |
| Networked offices and Project Closeout report |  | 31 December 2012 |  | Network test result report |  | 31 December 2012 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 350,000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Review the new office design and prepare network requirements/specification | 15 August 2012 |  | 31 September 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Purchase the services | 31 September 2012 |  | 30 October 2012 |  | Nil |  | Nil |  | Nil |  |  | Nil |  |
| Implement | 1 November 2012 |  | 31 December 2012 |  | Nil |  | R 350,000 |  | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Purchasing of additional blades |  | To ensure that the Municipality runs at around 50% capacity |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| 4 servers |  | 30 September 2012 |  |  | To have a stable environment with the necessary server capacity |  | 5 servers in the IBM rack |  | 4 Servers to be purchased |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | Prepare specification for the blades, Purchase and install servers |  |  |  |  |
| Project delivery and closeout report. All Procured Servers in the Municipal Assets Register |  | 30 September 2012 |  |  | The server shutdown log book |  | 30 September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Prepare server specification | 1 July2012 |  | 5 July 2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Purchase and install | 15 July 2012 |  | 31 July 2012 | R200,000 |  | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Purchase of Projectors and screens |  | To ensure that the council chamber and all boardrooms have the necessary equipment’s |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Mounted projectors in all boardrooms and council chambers |  | 31 September 2012 |  |  | Well-equipped boardrooms and council chamber |  | 2 mobile projectors |  | 5 Projectors and 4 Screens |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | Prepare specification, purchase and install projectors |  |  |  |  |
| Installed projectors in all boardrooms and council chamber and close out report. All projectors and Screens procured in the Municipal Assets Register. |  | 31 September 2012 |  |  | Installed projectors in all boardrooms and council chamber |  | 31 September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Prepare specification document | 1 July 2012 |  | 15 July 2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| Purchase and install Projectors | 15 July 2012 |  | 30 August 2012 | R200,000 |  | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Purchase of Business Intelligence Application |  | To build data analysis capability to support decision making |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Business intelligent application (Software) purchased |  | 30 June 2013 |  | Well analyzed Municipal data and creation of new knowledge |  | None |  |  | 1 Software package |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  | Establish project and prepare requirements | Purchase software Impelement and train users |
| Working BI application and project closeout report. Software installed for all users |  | 30 June 2013 |  | Report outputs from the BI system |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R 500,000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Establish a project including a business analyst. | 1 January 2013 |  | 31 January 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| Prepare technical and business requirements | 1 February 2013 |  | 16 February 2013 |  | Nil |  | Nil | R120,000 |  |  | Nil |  |  |
| Purchasing of software | 17 February 2013 |  | 30 May 2013 |  | Nil |  | Nil | R200,000 |  |  | Nil |  |  |
| Implementation | 1 June2013 |  | 30 June 2013 |  | Nil |  | Nil | R100,000 |  |  | Nil |  |  |
| Training. | 15 June 2013 |  | 30 June 3013 |  | Nil |  | Nil | R80,000 |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Purchase of network security monitoring application |  | To enhance network management and data security |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Network security monitoring software purchased |  | 30 September 2012 |  | Enhanced data protection and security control |  |  | 1 security proxy |  | 1 Software package |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | Prepare spec, purchase and install, train |  |  |  |  |
| Network security system with closeout report |  | 30 September 2012 |  | Effective network monitoring system, with monthly security monitoring report |  |  | 30 September 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R200,000 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Prepare technical specification | 1 July 2012 |  | 5 July 2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |
| Purchase and install | 6 July 2012 |  | 30 August 2012 |  | R200,000 | Nil |  | Nil |  |  | Nil |  |  |
| Training | 1 September 2012 |  | 30 September 2012 |  | Nil | Nil |  | Nil |  |  | Nil |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Good Governance and Public participation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Information and Communications Technology |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | IT Manager |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Business processes re-engineering |  | To document IT Business processes |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| IT procedure manual developed |  | 30 December 2012 |  |  | Well documented IT processes |  | None |  | Procedure Manual |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  | Prepare spec, appoint and implement |  |  |  |
| Minutes on approval by MANCO and IT Oversight |  | 30 December 2012 |  |  | IT procedure manual |  | 30 December 2012 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R300,000 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Appoint a project team | 1 October 2012 |  | 15 October 2012 | Nil |  | Nil |  | Nil |  |  | Nil |  |  |
| - Implementation | 15 October 2012 |  | 30 December 2012 | Nil |  | R300,000 |  | Nil |  |  | Nil |  |  |

  - ADMINISTRATION SUPPORT

| NATIONAL KEY PERFORMANCE AREA | Institutional capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Building accessibility |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Senior Manager Corporate Services |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Construction of the guard house to contain CCTV equipment | To improve security systems within the municipality by 2013 |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Completed and fully equipped Control Room | 31 December 2012 |  | Improved Security Management |  | None |  |  | 1 Control Room |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  | 0 | 1 control Room | 0 | 0 |
| Certificate of occupation by the Building Inspector | 31 December 2012 |  | Incident Security Report |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R 600 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Project Design (Building Plan and approval) | 1 July 2012 | 15 August 2012 |  | R30 000.00 |  | Nil | Nil |  |  | Nil |  |
| Procurement Processes (Contractor) | 15 August 2012 | 15 September 2012 |  | R10 000.00 |  | Nil | Nil |  |  | Nil |  |
| Construction | 1 October 2012 | 30 November 2012 |  | Nil |  | R500 000.00 | Nil |  |  | Nil |  |
| Project Handover | 01 December 2012 | 05 December 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |
| Equiping of of Control Room | 05 December 2012 | 31 December 2012 |  | Nil |  | R60 000.00 | Nil |  |  | Nil |  |
| Training of personnel to operate CCTV | 14 January 2013 | 31 January 2013 |  | Nil |  | Nil | Nil |  |  | Nil |  |

| NATIONAL KEY PERFORMANCE AREA | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Records management system |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Senior Manager Corporate services |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Business process Reengineering (Document Management0 | To have centralized records system by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| All manual documents transferred into electornic system. | 30 June 2013 |  |  | Ease of retrieval of documents/ reduced loss of documents |  | None |  |  | 6 Municipal Departments (documents tranfered to electronic system) |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 1 | 1 |  | 2 | 2 |
| Close out report | 30 June 2013 |  |  | Audit Outcome |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | 235 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Recruitment of Interns to implement the project |  | 1 July 2012 | 15 July 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |
| Training of personeel to implent the project |  | 15 July 2012 | 31 July 2012 |  | R35 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| Project Rollout |  | 01 August 2012 | 30 June 2013 |  | R50 000.00 |  | R50 000.00 | R50 000.00 |  |  | R50 000.00 |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | Institutional Capacity and Municipal Transformation |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | Office space |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | Senior Manager Corporate Services |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Office Space Provision |  | To provide two Park Homes offices by 2013 |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Number of park homes Offices purchased and equipped and provided to staff members |  | 30 September 2012 |  | Availability of more office space |  | None |  |  | 2 Park Homes (with 5 offices each) |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 2 park Homes | 0 |  | 0 | 0 |
| Invoices and occupation letters |  | 30 September 2012 |  | More office space |  | 30 June 2013 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R500 000.00 |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| - Procurement Process | 1 July 2012 |  | 15 August 2012 |  | R10 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| - Delivery and assembly of Park homes | 1 September 2012 |  | 15 September 2012 |  | R490 000.00 |  | Nil | Nil |  |  | Nil |  |  |
| - Project Handover | 29 September 2012 |  | 30 September 2012 |  | Nil |  | Nil | Nil |  |  | Nil |  |  |

  - LEGAL SERVICES

| NATIONAL KEY PERFORMANCE AREA | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | Legal Services |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | Manager Legal Services |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Administration of litigation | To ensure that litigation is minimized and Municipal resources are protected. |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Updated Litigation Register | December 2012 |  |  | Improved Litigation management |  | Outdated register |  |  | 1 updated register |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
| Litigation Register | December 2012 |  |  | Register of judgments obtained against the Municipality |  | December 2012 |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R1 000 000.00 |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Investigate all claims against the Municipality |  | 1st July 2012 | December 2012 |  |  |  |  |  |  |  |  |  |  |
| Prepare brief on behalf of the Municipality |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |  |
| Ensure that all necessary pleadings are filed |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |  |
| Attend court on behalf of the Municipality |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |  |
| Pay Legal Costs when necessary |  | July 2012 | June 2013 |  |  |  |  |  |  |  |  |  |  |
| Recover costs due to the Municipality |  | July 2012 | June 2013 |  |  |  | R300 000.00 | R300 000.00 |  |  | R400 000.00 |  |  |

6.	BUDGET AND TRESURY OFFICE

  - REVENUE MANAGEMENT

| NATIONAL KEY PERFORMANCE AREA | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | INCOME |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |
| Billing - Water Meter Readings | To ensure that customers are billed timeously and accurately |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |  |
| Customers billed accurately and timeously Updated monthly billing with correct tariffs | Weekly and Monthly |  | Exception Billing Report Accurate billing Register of all Readings |  |  | Some of the household are not billed. We are still collecting data (no. of household) |  | No. of Household billed monthly and yearly. Reading of all meters every month |  |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |
|  |  |  |  |  |  |  |  | No. of H/H |  | No. of H/H | No. of H/H |  | No. of H/H |
| Monthly Meter Reading Book / Register Monthly system meter reading reports Reports of number of billed ANDM Household Complete meter audits | Monthly |  | Service charge printout for the year - Billing Meter reading books-12 months |  |  | Monthly and Annually |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R750 000.00 |  | VOTE NUMBER |  |  | 1 400 44091 |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |
| Reading of meters |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Research and procure meter reading system |  | 01 July 2012 |  | 31 December 2012 | - |  | R150 000.00 |  | R150 000.00 |  |  | - |  |
| Readings captured on SAMRAS for billing |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Run exceptions report |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Refer unfamiliar or defective readings to technical |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Refer faulty prepaid meters to technical |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Renewal of Syntel system – prepaid water system |  | 01 July 2012 |  | 30 June 2013 | R 200 000.00 |  | - |  | - |  |  | - |  |
| End of Day reports |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Run meter reading reports |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Detailed billing reports (per consumer) |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Upgrade Billing system together with SAMRAS |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Prepare report of water leaks |  | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |
| Review of policy and procedures – Tariff Policy |  | 01 July 2012 |  | 30 June 2013 | - |  | R250 000.00 |  | - |  |  | - |  |

| NATIONAL KEY PERFORMANCE AREA | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | INCOME |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |
| Revenue Management | To ensure that all money owed to the municipality is recognized and recorded correctly |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |
| Correct customer Statements Total of Grants secured Debtors reconciliation | Monthly |  | Obtain an accurate database for billing and collection purpose Delivery of statements on time |  | Delays in delivery of statements and invoicing of debtors |  | 100% Billing performed R’ value of amount billed/invoiced |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  | 100% R’value | 100% R’val | 100% R’value | 100% R’value |
| Monthly Statements Monthly Receipts Monthly system meter reading reports Bank Statements of call accounts and investments | At the end of each month |  | Statements remitted Bank statements |  | Monthly |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | R60 000.00 |  | VOTE NUMBER |  | 1 400 44077 |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |
|  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  | QUARTER 4 |  |
| Remittance of statements on the 8th of each month. | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Quotation and Invoice from SA Post Office. | 01 July 2012 | 30 June 2013 |  | - |  | R20 000.00 | 20 000.00 |  | 20 000.00 |  |
| Print age analysis for reconciliation purposes. | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Banking of money received daily | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Receive relevant documentation from respective departments and Invoicing of Fire and plant hire debtors | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Receipts and proper allocation of Grants as per Division of Revenue Act | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Recording of interest received to income accounts | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Direct deposit reconciliation | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |
| Review of policy and procedures | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  | - |  |

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | INCOME |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Revenue Enhancement |  | To improve cash collected from customers and to identify other revenue streams |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| -Reading of the new installed meters. -Registration of the new installed prepaid water meters and issuing of tokens thereof. -Implementation of Revenue enhancement strategy VAT refund |  | Monthly |  |  | Increase in revenue collected |  | Municipality to source and secure additional funding to sustain the institution |  | R value of revenue collected yearly Fully implement credit control and by-laws |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | R’value | R’value |  | R’value | R’value |
| Improved cash collected from customers Amount Invoice billed to customers Amount of new Grants secured Approval and implementation of Revenue Strategy |  | Monthly |  |  | R’ value of invoice raised R’ value of revenue collected Date approved / implemented Amount of new grants secured |  | Monthly |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 240 000.00 |  |  | VOTE NUMBER |  | 1 400 44125 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Develop a revenue enhancement strategy | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Source additional funding – amounts of new grants secured | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Obtain register of meters installed from Technical Services | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Record installed meters on the systems | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Receipt of application form from customer and creating a job card thereof | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Installation of meter and registration of meter number – Urban Areas | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Installation of meter and registration of meter number – Rural Areas (government departments) | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Research and develop other new revenue schemes | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| VAT input claims from SARS | 01 July 2012 |  | 30 June 2013 | R240 000.00 |  | R1 000 0000.00 |  | R1 000 000.00 |  |  | R1 000 000.00 |  |  |
| To source additional grant funding |  |  |  | - |  | - |  |  |  |  | - |  |  |
| Review of policy and procedures | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |

| NATIONAL KEY PERFORMANCE AREA | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | INCOME |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Credit Control and Debt Management | To ensure that all revenue that is due to the Municipality is collected Reduction of debt owing by consumers |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Reduced Debt Meet financial obligations Data verification Effectively implement credit control policy | Monthly |  |  | Improve cash flow Reduce debt and no. of days Business 0 > 120 days Government 0 > 60 days Domestic 0 > 180 days |  | The municipal debtors book is excessively huge and credit control is not fully implemented |  | % reduced debt (90% collection - current debt and 50% collection - old debt) |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  |  | 20% Collect. |  | 30% Collect | 30% Collect. | 20% Collect. |
| Age Analysis Updated Indigent Register Payments agreements | At the end of each month |  |  | Statements remitted Indigent application forms |  | Monthly |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION | - |  |  | VOTE NUMBER |  | - |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Discount schemes (Incentives) |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Send collection letters |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Selectively make telephone calls to businesses, government departments, and capacity identified households |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Make personal visits |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Conduct a data cleansing and verification of water consumers. |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Develop indigent register which is linked with Local Municipality |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Reconciliation of all income accounts |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Reconciliation of age analysis to control accounts |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Reconciliation of age analysis to control accounts |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Review of policy and procedures - Credit Control and Debt Collection Policy |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |

6.2  EXPENDITURE MANAGEMENT

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | EXPERNDITURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Creditors Management |  | To ensure that creditors are paid within 30 days for speedy service delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Reconciliation of statements (sub-ledger) Reconciliation of control account Proper invoice Payment voucher (Order requisition, order form, GRV, Invoice, cheque details) |  | Monthly |  |  | Payment of suppliers within the timeframes in the policy Reduction of queries from other departments by 90% |  |  |  | Creditors are being paid on the 15th and 30th of every month, we are currently stamping all invoices to prove the submission date. |  |  |  | All creditors to supply monthly statements for reconciliation |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Reconciliation of statements Monitor and ensure adherence to the policy |  | Monthly |  |  | Remittance advice Audit opinion |  |  |  | Monthly |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE |  |  | QUARTER 1 |  |  | QUARTER 2 |  | QUARTER 3 |  |  |  | QUARTER 4 |  |
| Recording of invoices – sub ledger |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Reconciliation of individual creditors |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Reconciliation of Sub-Ledger to control account |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Implement a sequence filling system |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Implement and record a ACB/Cheque number filling |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Timeous payment of creditors |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Review of policy and procedures |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | EXPENDITURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payment Management |  | Prevent of fictitious creditors and staff members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Printing of creditors’ sub-ledger. Reconciliation of statements and sub-ledger Proper documentation. Obtain SLA between municipality and service provider i.e. debit orders Reconciliation of all expenditure accounts |  | Monthly |  |  | Remittance advice |  |  |  | Monthly |  |  |  | Payment of suppliers within the timeframes in the policy |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Reconciliation of Creditors |  | Monthly |  |  | Payment voucher |  |  |  | Monthly |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  |  | QUARTER 1 |  | QUARTER 2 |  |  | QUARTER 3 |  |  |  | QUARTER 4 |  |  |
| Reconciling of debit orders with sub-ledger | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Validation of all supporting documentation | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Reconciliation of Sub-Ledger to control account | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Timeous payment of creditors | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Review of policy and procedures | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | EXPERNDITURE |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Payroll Management |  | To ensure that staff and councilors are paid within their due dates with less discrepancies Pay third party payments timeously |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Processing of salaries on time Integration of VIP and SAMRAS financial system Reconciliation of statements Back up disc |  | Monthly |  | Salary payslip / advice Elimination of payroll related queries internally and externally |  | Payroll is properly administered and queries are attended within 3 days from the date of receipt. |  | Salaries paid on time |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Reconciliation of Payroll and VIP |  | Monthly |  | Date of payment Salary advice |  | Monthly |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Reconciling of debit orders with sub-ledger | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |
| Validation of all supporting documentation | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |
| Reconciliation of Sub-Ledger to control account | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |
| Timeous payment of creditors | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |
| Review of policy and procedures | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |
| Payroll query rooster development for maintenance of high standards | 01 July 2012 |  | 30 June 2013 |  | - | - | - |  |  | - |  |  |

6.3	BUDGET AND REPORTING

| NATIONAL KEY PERFORMANCE AREA | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | BUDGET AND REPORTING |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Budget Preparation | To ensure legislative compliance with MFMA. To ensure that the development of Municipal Budget is in line with the Municipal IDP priorities and the implementation thereof is monitored. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Budget timetable Link IDP with budget Departmental budget inputs Draft budget Budget advertisement Consultation with relevant stakeholders | 31 March 2013 (Draft budget) 31 May 2013 (Approved budget) |  |  | Approved budget |  | There has been a gap in budget compilation processes leading to numerous adjustments and virements during the financial year |  | 31 March 2013 (Draft budget) 31 May 2013 (Approved budget) Revenue and expenditure management in accordance with approved budget |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  |  | Ongoing |  | Ongoing | Ongoing | Ongoing |
| Tabled draft budget Approved budget Budget vs. Actual | 31 March 2013 (Draft budget) 31 May 2013 (Approved budget) |  |  | Approved budget |  | 31 March 2013 (Draft budget) 31 May 2013 (Approved budget) |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  | QUARTER 4 |  |
| Prepare a budget timetable |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Review of budget taking into account the views that were raised by relevant stakeholders |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Supporting documentation as per relevant legislation |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Obtain DORA allocation |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Convene meetings with budget steering committee |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Population of Schedule A and Schedule C |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |
| Budget Training (Samras and Budget module) |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of policy and procedure |  | 01 July 2012 | 30 June 2013 |  | - |  | - |  | - |  | - |  |

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | BUDGET AND REPORTING |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| Reporting |  | Timely submission of the Financial statements and an improved audit report. To ensure that the Municipality complies with all re reporting statutes and therefore conforming to the Batho Pele Principles |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Monthly reports Quarterly reports Mid-year reports Yearly reports Annual Financial Statements Annual reports |  | Monthly Quarterly Mid-year Annually |  | All statutory report and financial statements submitted on time reflected in the National Treasury reports |  | In year reporting in terms of Section 71 & 66 of MFMA has been complied with |  |  | All compliance matters as legislated per MFMA calendar are adhered to. Accurate reporting within timeframes Timely submission of the financial statements and an improved audit report. |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | 100% | 100% | 100% | 100% |
| Monthly reports Quarterly reports Mid-year reports Annual reports Annual Financial Statements |  | Monthly Quarterly Mid-year Annually |  | In year reporting |  | Monthly Quarterly Mid-year Annually |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 500 000.00 |  | VOTE NUMBER |  | 1 400 44027 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Prepare section 71 monthly reports | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Prepare section 72 mid-year assessment reports | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Prepare section 52 quarterly reports | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Prepare section 66 - reports | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Prepare section 11 quarterly reports | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Prepare budget monitoring report | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Fully comply with GRAP | 01 July 2012 |  | 30 June 2013 |  | R120 000.00 |  | R590 000.00 | R150 000.00 |  |  | - |  |
| Compilation and Submission of - AFS | 01 July 2012 |  | 30 June 2013 |  | R900 000.00 |  | R320 000.00 | - |  |  | R500 000.00 |  |
| Comply with section 75 of MFMA | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| SAMRAS training to staff members | 01 July 2012 |  | 30 June 2013 |  | R100 000.00 |  | R150 000.00 | R200 000.00 |  |  | R100 000.00 |  |
| Fully utilization of financial system - SAMRAS | 01 July 2012 |  | 30 June 2013 |  | R150 000.00 |  | - | R120 000.00 |  |  | - |  |
| Training of standing committee | 01 July 2012 |  | 30 June 2013 |  | R100 000.00 |  |  | - |  |  | - |  |
| Review of policy and procedure | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |

6.4 SUPPLY CHAIN MANAGEMENT

| NATIONAL KEY PERFORMANCE AREA | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA | SUPPLY CHAIN MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of SCM - Acquisition | Provision of resources To ensure that the Municipal projects are implemented on time to achieve Municipal Service Delivery Objectives. To ensure that Municipal procurement is done in a cost effective and efficient manner in order to speed-up service Delivery |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |
| Tender specification Tender evaluation Tender adjudication Obtaining of valid quotations Advertised tender | Monthly, Quarterly, Mid-year and Annually |  |  | In year reporting Tenders Awarded 5-days processing period for small supplies and 60 days processing period for bigger tenders |  | The procurement process is very slow and bid committee system is not going in a proper manner as well. |  |  | 100% completion of tenders on the SDBIP |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | Ongoing | Ongoing | Ongoing | Ongoing |
| Compiling of reports (Monthly, Quarterly, Mid-year and Annual reports) Deviation reports Irregular and un-authorised expenditure reports | Monthly Quarterly Mid-year Annually |  |  | Approved reports Adverts (Newspaper and notice board) |  | Monthly Quarterly Mid-year Annually |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |
|  |  | START DATE | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |
| Report on R100K and above bids that were awarded (monthly, quarterly and annually) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Receive specification approved by head of department. (below R30K) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Obtain quotations from service providers (below R30K) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Quotations are then forwarded to procuring departments to make order requisition (R30K) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Process order upon receipt of requisition (below R30K) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Develop and Implement the automated orders |  | 01 July 2012 | 30 June 20132 |  | - |  | - | - |  |  | - |  |
| Quotation Committee evaluates all quotations from R30k to R200k |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Ensure that SCM bid committees are reviewed |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Specification committee sits and discuss specification received from procuring department |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Advert is then compiled and signed by Municipal Manager before its advertised |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Sale of tender documents |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Report on the sale of tender documents |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| On closing date, all bids received are registered |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Bids are then evaluated by bid evaluation committee and make recommendation for appointment to adjudication committee (below R10m) |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| For bids that are over R10m are referred by bid adjudication committee to the Municipal Manager |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Procuring department is then advised to prepare appointment letter that is signed by the Municipal Manager and the copy is filed at SCM Unit |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Update a register of all tenders awarded |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Proper management of Supplier Database |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide training to SCM staff and bid committee members |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Update contract register per project and asset procured |  | 01 July 2012 | 30 June 2013 |  | - |  | - | - |  |  | - |  |
| Review of the SCM process flow to improve service delivery |  | 01 July 2012 | 30 June 2013 |  |  |  |  |  |  |  |  |  |

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | SUPPLY CHAIN MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Demand Management |  | To ensure that the Municipal projects are implemented on time to achieve Municipal Service Delivery Objectives. |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Compilation of Demand management plan Project priority Schedule |  | Review the plan monthly |  | Improved and efficient SCM unit for speedy service delivery, Big tenders awarded on the first quarter |  | Tenders have been spread through the financial year and some even awarded in the last quarter of the financial year |  |  | 100% completion of tenders on the SDBIP |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q4 |
|  |  |  |  |  |  |  |  |  | 40% | 30% |  | 20% | 10% |
| Approved demand management plan |  | Monthly |  | No. of tender awarded as per the plan |  | Monthly |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | - |  | VOTE NUMBER |  | - |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  | QUARTER 1 |  | QUARTER 2 | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Compilation of Demand management plan and Project priority Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare tender documents and specifications | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |  |
| Receive specification approved by head of department. (below R30K) | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |  |
| Specification committee sits and discuss specification received from procuring department | 01 July 2012 |  | 30 June 2013 |  | - |  | - | - |  |  | - |  |  |

6.5 ASSET AND LIABILITY MANAGEMENT

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | ASSET AND LIABILITY MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inventory Management |  | Provision of resources to municipal departments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Stock movement report Stock listing Clear stores reconciliations to avoid misuse and theft |  | Monthly Quarterly Annually |  |  | Inventory listing (Items held) |  |  |  | The stores module is not yet fully implemented. |  |  |  | Monthly Quarterly Annually |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Compiling of reports (Monthly, Quarterly, Mid-year and Annual reports) |  | Monthly, Quarterly and Annually |  |  | Stock level Well managed stores |  |  |  | Monthly, Quarterly and Annually |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE |  |  | QUARTER 1 |  | QUARTER 2 |  |  | QUARTER 3 |  |  |  | QUARTER 4 |  |  |
| Establish stock re-order levels | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Print stock re-order level | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Re-Activate stores module | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Provide training to SCM staff and bid committee members | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Reconciliation between Inventory Control Account and the Inventory Sub-ledger | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Physical stock take | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| Review procedures | 01 July 2012 |  | 30 June 2013 |  |  | - |  | - |  |  | - |  |  |  | - |  |  |
| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOCUS AREA |  | ASSET AND LIABILITY MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Asset Management |  | Accounting and Safeguarding of Municipal assets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  |  |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  |  |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Properly Managed GRAP Fixed Asset Register (FAR) Clear Maintenance Plans Inventory listing |  | Monthly |  |  | Up to date GRAP FAR Approved Maintenance Plans |  |  |  | There is a GRAP Compliant Asset Register but not updated monthly. |  |  |  | 30 June 2013 |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  |  |  | TARGET DATE |  |  |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Completed fixed asset register Complete inventory listing |  | Monthly 30 June 2013 |  |  | FAR - Fully comply with the assertion of completeness, existence, valuation, accuracy, presentation and disclosure. |  |  |  | 30 June 2013. |  |  |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  |  |  |  | VOTE NUMBER |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES |  | TIMEFRAMES |  |  |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |  |
|  |  | START DATE |  | END DATE |  |  | QUARTER 1 |  |  | QUARTER 2 |  | QUARTER 3 |  |  |  | QUARTER 4 |  |
| Appoint a service provider – valuation |  | 01 May 2013 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Update and Complete fixed asset register |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | 1 000 000.00 |  |
| Conduct Asser Count |  | 01 July 2012 |  | 30 June 2013 |  |  | 10 000.00 |  |  | 10 000.00 |  | 10 000.00 |  |  |  | 10 000.00 |  |
| Activate asset management module in SAMRAS |  | 01 July 2012 |  | 31 December 2012 |  |  | -25 000.00 |  |  | - |  | - |  |  |  | 35 000.00 |  |
| Barcode all municipal fixed assets that have been procured |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Insure assets as they are purchased |  | 01 July 2012 |  | 30 June 2013 |  |  | 1 500 000.00 |  |  | - |  | - |  |  |  | - |  |
| Classify fixed assets in the general ledger |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Training of SCM staff |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Reconciliation between FAR and the Asset control account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Update and maintain Fleet records |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |
| Review of policy and procedures - Asset Management Policy - Fleet and Transport Management Policy |  | 01 July 2012 |  | 30 June 2013 |  |  | - |  |  | - |  | - |  |  |  | - |  |

| NATIONAL KEY PERFORMANCE AREA |  | FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOCUS AREA |  | ASSET AND LIABILITY MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER/ RESPONSIBLE DEPARTMENT |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT TITLE |  | IDP STRATEGIC OBJECTIVE(S)/ IDP/ PROJECT OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |
| Liability Management |  | Recognize liabilities of the municipality |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT KEY PERFORMANCE INDICATORS |  | TARGET DATE |  |  | OUTCOMES KEY PERFORMANCE INDICATORS |  | BASELINE/ PRIO YEAR PERFORMANCE/ BACKLOGS |  | ANNUAL TARGET (2012/13) |  |  |  |  |
| Liability register Existing liability contracts |  | Quarterly |  |  | Updated Liability Register |  | Up to date register |  | No. of existing and new borrowing/liability contracts |  |  |  |  |
| MEANS OF VERIFICATION (OUTPUT KPI) |  | TARGET DATE |  |  | MEANS OF VERIFICATION (OUTCOMES KPI) |  | TARGET DATE |  | QUARTELY TARGETS |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Q1 | Q2 |  | Q3 | Q1 |
|  |  |  |  |  |  |  |  |  | Ongoing | Ongoing |  | Ongoing | Ongoing |
| Liability verification and maintenance (re-payments) Signed liability contracts |  | Quarterly |  |  | Liability Register Signed contract (agreements) |  | 30 June 2013 |  |  |  |  |  |  |
| TOTAL PROJECT BUDGET ALLOCATION |  | R3 600 000.00 |  |  | VOTE NUMBER |  | 1 400 44096 |  |  |  |  |  |  |
| PROJECT MILESTONES/ INPUTS INDICATORS/ ACTIVITIES | TIMEFRAMES |  |  | QUARTELY EXPENDITURE PROJECTIONS |  |  |  |  |  |  |  |  |  |
|  | START DATE |  | END DATE | QUARTER 1 |  | QUARTER 2 |  | QUARTER 3 |  |  | QUARTER 4 |  |  |
| Update and Complete liability register | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |
| Payment of liabilities timeously | 01 July 2012 |  | 30 June 2013 | R1 800 000.00 |  | - |  | R1 800 000.00 |  |  | - |  |  |
| Develop policy and procedures - Borrowing Policy | 01 July 2012 |  | 30 June 2013 | - |  | - |  | - |  |  | - |  |  |